## Stationary
No. | PO Information |  | Key Milestone |  |  |  | Sub-Order Status | [8 empty] | Inspection Status | [5 empty] | Manufacturing Progress | [11 empty] | Shipping & Delivery
|  |  | Key Milestone | Plan | Forecast | Actual | Sub-Order Item | Q'ty | Sub-Order Issued |  |  | Sub-Order Received |  |  | Sub-Vendor | Major Inspection Plan |  |  | Inspection Application |  |  | Item No. | Item Name | Start Fabricatioin |  |  | SQR | IRC | Cargo Ready |  |  | Weight (Ton) | Remark | Material shipped |  | Shipment No. | Delivery At site |  | ROS
[9 empty] | Plan | Forecast | Actual | Plan | Forecast | Actual |  | Type | Forecast | Actual | NOI no. | Insp. Date | Result |  |  | Plan | Forecast | Actual | Transmittal no. | number # | Plan | Forecast | Actual |  |  | ETD | ATD |  | ETA | ATA
1 | M/R No. | FK7A.01 | KOM | 2025-03-12 | 2025-03-12 | 2025-03-12 | Flare stack w/ Derrick and P&F | 1 | 2025-06-25 | 2025-08-22 | 2025-08-20 | 2026-03-07 | 2025-02-13 | 2025-02-13 | Werim , Korea | Final inspection for Template and Anchor Bolt | 2025-08-01 | 2025-08-01 | N-5000106972-001 | 2025-08-01 | pass | COMMON | Template and Anchor Bolt |  |  |  |  | IR-5000106972-0001 | 2025-08-05 | 2025-08-05 | 2025-08-06 |  |  | 2025-08-16 | 2025-08-16 | SC7128C-P1-KC043-CS | 2025-09-22 | 2025-09-22 | 2025-09-10
| M/R Name | Elevated Flare | Key V/P | 2025-04-25 | 2025-04-25 | 2025-04-25 | Blowers (HP & LP) | 4 | 2025-02-07 | 2025-04-16 | 2025-04-16 | 2026-03-07 | 2026-03-07 | 2025-02-13 Final | Suewon , KOREA | PIM | 2025-10-22 | 2025-10-22 | N-5000106972-002 | 2025-10-22 | pass | 40-PKF-9100 | ELEVATED CRYOGENIC LP FLARE | [5 empty] | 2026-03-07 | 2026-03-07 |  |  |  | refer to below |  |  | refer to below |  | 2026-04-06
| P/O No. | 5000106972 | Sub-order Issued | 2025-05-30 | 2025-08-22 | 2025-08-20 | Instrucments (PG, PT..etc) | 1 Lot | 2025-06-20 | 2025-10-24 | 2025-10-24 | 2026-03-07 | 2025-02-15 | 2025-02-15 | Rueger , Korea | Material inspection | 2025-10-28 | 2025-10-28 2025-11-10 2025-11-19 | N-5000106972-003 N-5000106972-005 N-5000106972-007 | 2025-10-28 2025-11-10 2025-11-19 | pass | 40-PKF-9101 | ELEVATED CRYOGENIC HP FLARE | [5 empty] | 2026-03-07 | 2026-03-07 |  |  |  | refer to below |  |  | refer to below |  | 2026-04-06
| Q'ty(Item/Set) | 2 | Receive Main material | 2025-07-21 | 2025-10-23 | 2025-10-23 | UCP Panel | 2 | 2025-06-19 | 2025-12-16 | 2025-12-16 | 2026-03-07 | 2026-03-07 | 2026-03-05 | JS and/or Hanshin - FAT/iFAT on 3/3~3/6 - to REI shop by end of Mar, 2026 | PA-UT Demonstration | 2025-11-20 | 2025-11-20 | N-5000106972-006 | 2025-11-20 | pass |  | HP Air Riser 5 ea, LP Air Riser 4 ea, HP Duct, A/B |  |  |  |  | IR-5000106972-0002 | [5 empty] | Anchor Bolt
| Vendor Name | Zeeco Asia | PIM | 2025-07-08 | 2025-10-22 | 2025-10-22 | ASD Panel | 4 | 2025-06-19 | 2025-08-26 | 2025-08-26 | 2026-03-07 | 2026-06-30 |  | ABB, Korea and China - LV ASD PANEL in Korea - MV ASD PANEL in China | (MV) Motor routine/performance test | 2025-11-21 | 2025-11-21 | N-5000106972-004 | 2025-11-21 | pass |  | LP Air Riser 1 ea, LP Duct, Derrick Structure, P&L, Utility Piping, Loose Part, S/P etc |  |  |  |  | IR-5000106972-0003 | [5 empty] | 2026-02-13 | 2026-02-13 | SC7128C-P1-KA159-CS | 2026-02-19 | 2026-02-19 |  | by DHL
| Delivery Date | 2026-03-07 | Start Fabrication | 2025-07-28 | 2025-10-29 | 2025-10-29 | Panels (ACWL(1)) | 4 | 2025-07-10 | 2025-12-16 | 2025-12-10 | 2026-03-07 | 2026-04-20 |  | Hanshin | DI/VI of Derreck | 2025-12-17 | 2025-12-17 | N-5000106972-008 | 2025-12-17 | pass |  | HP Blower, LP Blower |  |  |  |  | IR-5000106972-0004 | [5 empty] | 1st batch [Flare stack]
| Delivery Term | FOB | Inspection and Test | 2026-03-02 | 2025-03-09~ | 2025-03-05 | Ignition Racks | 2 | 2025-09-25 | 2025-09-25 | 2025-09-12 | 2026-03-07 | 2026-03-07 | 2025-01-20 Final | Shina Industry | DI/VI of Rack : LPG Skid 2 only | 2026-01-20 | 2026-01-20 | N-5000106972-009 | 2026-01-20 | pass |  | HP Flare Tip 2 ea, LP Flare Tip 1 ea |  |  |  |  | IR-5000106972-0005 |  |  |  |  | [Duct, Riser] 14 PKGS (BB) | 2026-03-03 | 2026-03-04 | SC7128C-P1-KB130-CS | 2026-05-29 |  | 2026-06-01 | ATA Duqm, Oman 4/29
| Delivery Location |  | Packing | 2026-03-05 | 2025-03-17~28 | 2025-03-05 | Flare Tips (including Pilots) | 3 | 2025-08-05 | 2025-09-12 | 2025-09-12 | 2026-03-07 | 2026-03-07 | 2025-02-25 Final | Zeeco Asia | DI/VI of Ignition rack + LPG rack | 2026-02-24 | 2026-02-24 | N-5000106972-009 rev | 2026-02-24 | pass | [11 empty] | [Derrick structure] 21*40 HQ | 2026-04-29 | 2026-04-29 | SC7128C-P1-KC131-CS | 2026-07-10 |  | 2026-06-01 | ETA Jeddah, KSA 6/17 | 2026-03-10 booking cancelled
| Inspection Level | 3 | Cargo ready | 2025-03-07 | 2025-03-24~ | 2025-03-03 | Manual valve (Gate, Ball, Check) | 1 Lot | 2025-06-20 | 2025-09-12 | 2025-09-08 | 2026-03-07 | 2026-02-15 | 2026-02-15 | Myungsung Tech | DI/VI of remaining part | 2026-01-14, 15 | 2026-01-14, 15 | N-5000106972-010 | 2026-01-14, 15 | pass | [11 empty] | [ladder & platform] 4*40 FR (OW) | 2026-05-02 | 2026-05-03 | SC7128C-P1-KC157-CS | 2026-07-20 |  | 2026-06-01 | ETA Jeddah, KSA 6/28 | 2026-03-10 booking cancelled
| Vendor PIC | Simon Lee |  |  |  |  | Shut off valve and Sol valve | 1 Lot | 2025-06-20 | 2025-09-12 | 2025-09-12 | 2026-03-07 | 2026-01-30 | 2026-01-30 | Cohands | Blower MRT/Performance/DIVI | 2026-01-19, 20 | 2026-01-20 | N-5000106972-011 | 2026-01-20 | pass | [11 empty] | 2*40 FR (IG) | 2026-05-13 | 2026-05-13 | SC7128C-P1-KC211-CS | 2026-07-10 |  | 2026-06-01 | ETA Jeddah, KSA 6/15 | 2026-03-10 booking cancelled
| SCJV PE | Michelle Chen |  |  |  |  | Anchor & Template | 1 Lot | 2025-07-07 | 2025-07-07 | 2025-07-03 | 2025-08-31 | 2025-08-04 | 2025-08-04 | Werim , Korea | MI/NDE/VIDI for Duct and LP Riser | 2026-01-21 | 2026-01-21 | N-5000106972-012 | 2026-01-21 | pass
| SCJV RE | Ryan Chou |  |  |  |  | Combsution air duct w/ Supprot | 1 Lot | 2025-08-22 | 2025-08-22 | 2025-08-20 | 2026-03-07 | 2026-03-07 | 2025-02-26 Final | Werim , Korea | Surface Preparation for LP Riser | 2026-01-23 | 2026-01-23 | N-5000106972-013 | 2026-01-23 | pass | [12 empty] | 2nd batch [Blower (+ Flare Tip)]
| SCJV Expeditor | Derek Chen (Heesun Park support) |  |  |  |  | EHT panel (1) | 1 | 2025-10-28 | 2025-10-27 | 2025-10-27 | 2026-03-07 | 2026-03-07 | 2026-02-28 | Geodong , Korea | [No W point] Trial Assembly of Derreck | 2026-01-26 | 2026-01-26 | N-5000106972-014 | 2026-01-26 | not W point | [11 empty] | 5*40 HQ | 2026-04-20 | 2026-04-20 | SC7128C-P1-KC164-CS | 2026-06-25 |  |  | ETA Jeddah, KSA 6/05
[7 empty] | JB and LP | 1 Lot | 2025-12-03 | 2026-01-02 | 2026-01-02 | 2026-03-07 | 2026-02-13 | 2026-02-13 |  | MI/NDE/VIDI for HP Riser, PI for LP Riser, Surface Preparation for Duct | 2026-01-26~29 | 2026-01-26~28 | N-5000106972-014 | 2026-01-26~28 | pass | [11 empty] | [Ignition Rack]2*40 OT | 2026-05-02 | 2026-05-03 | SC7128C-P1-KC212-CS | 2026-07-25 |  |  | ETA Jeddah, KSA 6/27
[16 empty] | Surface Preparation for HP Riser | 2026-01-30 | 2026-01-30 | N-5000106972-015 | 2026-01-30 | pass | [11 empty] | [HP blower] 4*40 FR (OWOH) | 2026-05-02 | 2026-05-03 | SC7128C-P1-KC165-CS | 2026-07-25 |  |  | ETA Jeddah, KSA 6/27
[16 empty] | PI for Duct, MI/PMI/VI etc for Utility Piping | 2026-02-02 | 2026-02-02 | N-5000106972-015 | 2026-02-02 | pass | [11 empty] | [LP blower] 3*40 FR (OWOH) | 2026-05-17 | 2026-05-17 | SC7128C-P1-KC226-CS | 2026-07-31 |  |  | ETA Jeddah, KSA 7/11
[16 empty] | PI for HP Riser | 2026-02-05 | 2026-02-05 | N-5000106972-015 | 2026-02-05 | pass | [11 empty] | [LP blower] 4*40 FR (OW) | 2026-05-23 |  | SC7128C-P1-KC227-CS | 2026-08-08 |  |  | ETA Jeddah, KSA 7/18
[16 empty] | Galv. Inspection for P&L, HDG for Derrick | 2026-02-04 | 2026-02-04 | N-5000106972-016 | 2026-02-04 | pass | [11 empty] | [Pipe, Duct] 4*40 FR (OH) | 2026-05-23 |  | SC7128C-P1-KC228-CS | 2026-08-08 |  |  | ETA Jeddah, KSA 7/18
[16 empty] | Packing Inspection for 1st batch (LP/HP Riser and Duct - four out of five) | 2026-02-12 | 2026-02-12 | N-5000106972-017 | 2026-02-12 | pass | [11 empty] | [Rain Hood Support, Cable] 1*40FR (OW) | 2026-05-11 | 2026-05-12 | SC7128C-P1-KC229-CS | 2026-07-05 |  |  | ETA Jeddah, KSA 6/15, request change POD to Hamad with carrier
[16 empty] | Painting Inspection for HP/LP Blower | 2026-2-12,13 | 2026-2-12,13 | N-5000106972-018 | 2026-2-12,13 | pass
[16 empty] | Final VIDI for JB | 2026-02-11 | 2026-02-11 | N-5000106972-020 | 2026-02-11 | pass | [12 empty] | 3rd batch (Paint)
[16 empty] | Function and VIDI for EHT Panel | 2026-02-23 | 2026-02-23 | N-5000106972-019 | 2026-02-23 | pass | [11 empty] | [Paint] 1*20 GP | TBC |  | SC7128C-P1-KC160-CS | TBC |  |  | 1. DG cargo 2. Checking import requirements and import license with GWC
[16 empty] | Function and VIDI for Local Panels | 2026-02-25 | 2026-02-25 | N-5000106972-021 | 2026-02-25 | pass
[16 empty] | VIDI, PI, PA for HP/LP Flare Tip | 2026-02-25~27 | 2026-02-25~27 | N-5000106972-022 | 2026-02-25~27 | pass | [12 empty] | UCP Delivery
[16 empty] | FAT/iFAT of UCP **hardware | 2026-03-10~12 | 2026-03-11~13 | N-5000106972-026 | 2026-03-11~13 | wiring issue | [11 empty] | to RIE shop | 2026-05-09 | 2026-05-09 | SC7128C-P1-KT168-V | 2026-05-09 | 2026-05-09
[16 empty] | FAT/iFAT of UCP **software | 2026-04-20~24 | 2026-04-20~23 | N-5000106972-028 | 2026-04-20~23 | pass | [11 empty] | to site | Mid June
[16 empty] | FAT/iFAT of ASD Panel (LV) in Korea | 2026-04-30 | 2026-04-30 | N-5000106972-029 | 2026-04-30 | pass
[16 empty] | FAT/iFAT of ASD Panel (MV) in China | 2026-05-14~16 | 2026-05-14 | N-5000106972-030 | 2026-05-14 | pass
[16 empty] | Packing Inspection of UCP, ASD Panel etc | 2026-03-07 TBD | to be postponded
[16 empty] | Packing Inspection for Duct etc. | 2026-02-26~27 | 2026-02-26~27 | N-5000106972-023 | 2026-02-26~27 | pass
[16 empty] | Packing Inspection for HP/LP Blower | 2026-02-26~27 2026-03-03~05 | 2026-02-26~27 2026-03-03~05 | N-5000106972-024 | 2026-02-26~27 2026-03-03~05 | pass
[16 empty] | PA for Rack | 2026-03-03 | 2026-03-03 | N-5000106972-025 | 2026-03-03 | pass
[16 empty] | PA for EHT panel | 2026-04-17 | 2026-04-17 | N-5000106972-027 | 2026-04-17 | pass
| Main Issue | 1/29 MPR ① UCP fabrication delay due to N₂ Rich and Purge cases open ② ASD under clarification | 10/23 NOI for MI submitted and scheduled on Oct 28th |  |  |  | 8/14 Zeeco hold the sub order due to additional case (N2 rich case) study which can affect the design of TIp, Blower, Duct Design etc 8/20 Zeeco is preparing internal process. After that, sub order can be issued by Aug 22 9/3 sub order for instrument under preparation" 9/30 current status and progres check at vendor office : about a month delayed 12/9 ① Zeeco visit Taiwan to close PLC issue ② verbal information : VFD panel delayed and details can be provided later
2 | M/R No. | EH2A.01 | KOM | 2025-03-20 | 2025-03-20 | 2025-03-20 | Heater 40-E-9000 | [8 empty] | Heater PIM | 2025-10-15 | 2025-10-15 | N-5000106450-001 |  |  | 40-E-9000 | HP FLARE KO DRUM ELECTRIC HEATER | 2025-08-25 | 2025-10-15 | 2025-10-27 | FAT report uploaded |  | 2025-11-24 | 2026-05-30 |  |  |  | 2026-06-20 |  | SC7128C-P1-EC161-CS | 2026-08-09 |  | 2026-05-16 | update ROS: 8/15, port: Bilbao,Spain
| M/R Name | Electrical Heater | Key V/P | 2025-03-28 | 2025-04-02 | 2025-04-16 | 304/304L Seemless Tube for Element Pockets | batch | 2025-04-09 | 2025-04-09 | 2025-04-09 | 2025-08-08 | 2025-06-13 | 2025-06-10 | Marphil - France | Heater E-9000 Electrical FAT and Hydrotest | 2026-03-05 | 2026-03-05 | N-5000106450-003 | 2026-03-05 | pass | 40-E-9001 | HP Flare KO Drum Boot Electric Heater | 2025-09-15 | 2025-11-13 | 2025-11-13 | FAT report uploaded |  | 2025-12-23 | 2026-05-30 |  |  |  | 2026-06-20 |  | SC7128C-P1-EC161-CS | 2026-08-09 |  | 2026-05-16 | update ROS: 8/15
| P/O No. | 5000106450 | Sub-order Issued | 2025-05-05 | 2025-05-23 | 2025-05-06 | Incoloy 800 element material | batch | 2025-05-06 | 2025-05-23 | 2025-04-28 | 2025-08-08 | 2025-10-20 | 2025-10-16 | Vulcanic - France | Heater E-9000 Final Inspection | 2026-03-12 | 2026-03-05 | N-5000106450-003 | 2026-03-05 | pass |  | CP for Heaters | 2025-08-25 | 2025-10-15 | 2025-11-13 |  |  | 2025-12-23 | 2026-06-20 |  |  |  | 2026-06-20 |  | SC7128C-P1-EC161-CS | 2026-08-09 |  | 2026-09-05
| Q'ty(Item/Set) | 1 | Receive Main material | 2025-08-22 | 2025-10-30 | 2025-10-16 | SS304 Flange | 1 | 2025-05-06 | 2025-05-06 | 2025-05-06 | 2025-08-08 | 2025-09-01 | 2025-05-19 | Special Flanges S.p.A. - Italy | Control Panel E-9000 Electrical FAT | 2026-05-04 | 2026-05-04 | N-5000106450-004 | 2026-05-04 | punch closing
| Vendor Name | Vulcanic Thermoelectrica SLU | PIM | 2025-08-18 | 2025-10-15 | 2025-10-15 | Temp Transmitters | 5 | 2025-06-16 | 2025-07-31 | 2025-07-21 | 2025-08-08 | 2025-09-01 | 2025-08-07 | Rosemount Emerson - France | Control Panel E-9000 Final and Packing Inspection | TBC
| Delivery Date | 2026-01-31 | Start Fabrication | 2025-08-25 | 2025-10-15 | 2025-10-15 | Sensors (Type K TC Duplex) | 5 | 2025-06-30 | 2025-07-31 | 2025-06-24 | 2025-08-08 | 2025-08-08 | 2025-07-21 | H&B Sensors - UK | Heater E-9001 Electrical FAT and Hydrotest | 2026-03-05 | 2026-03-05 | N-5000106450-003 | 2026-03-05 | pass
| Delivery Term | FOB | Finish Fabrication | 2025-11-04 | 2026-02-28 | 2026-03-01 | Thyristor | 2 | 2025-05-15 | 2025-05-15 | 2025-06-09 | 2025-09-03 | 2025-09-03 | 2025-08-30 | CD Automation - UK | Heater E-9001 Final Inspection | 2026-04-06 | 2026-04-06 | N-5000106450-002 | 2026-04-06 | punch closing
| Delivery Location | Spain | Inspection and Test | 2025-11-07 | 2026-03-05 | 2026-03-05 | Cabinet Enclosure Compartments | 4 | 2025-05-15 | 2025-07-31 | 2025-06-10 | 2025-08-13 | 2025-11-13 | 2025-11-13 | Rittal - France | Control Panel E-9001 Electrical FAT | 2026-05-04 | 2026-05-04 | N-5000106450-004 | 2026-05-04 | punch closing
| Inspection Level | 3 | Packing E-9000 | 2025-01-23 | 2026-05-25 |  | Gaskets | 3 | 2025-11-01 | 2025-11-01 | 2025-10-16 | 2025-12-17 | 2025-12-11 | 2025-11-20 | CALVO SEALING - Spain | Control Panel E-9001 Final and Packing Inspection | TBC
| Vendor PIC | Daniel Rose | Cargo ready E-9000 | 2026-01-30 | 2026-05-25 |  | Studbolts | 2 | 2025-11-01 | 2025-11-01 | 2025-10-15 | 2025-12-17 | 2025-12-11 | 2025-11-11 | BECK PROSPER - UK
| SCJV PE | Michelle Chen | Packing E-9001 | 2025-01-23 | 2026-05-25 |  | Heater 40-E-9001
| SCJV RE | Tawatchai Tarseekum | Cargo ready E-9001 | 2026-01-30 | 2026-05-25 |  | 304/304L Seemless Tube for Element Pockets | batch | 2025-09-19 | 2025-10-20 | 2025-09-05 | 2025-10-31 | 2025-10-31 | 2025-10-16 | Marphil - France
| SCJV Expeditor | Andrew Zheng->Willy Wang | Cargo ready (Panels) | 2026-01-30 | 2026-05-25 |  | Incoloy 800 element material | batch | 2025-09-05 | 2025-09-26 | 2025-09-05 | 2025-11-18 | 2025-11-11 | 2025-10-16 | Vulcanic - France
[7 empty] | SS304 Flange | 1 | 2025-09-19 | 2025-10-15 | 2025-09-05 | 2025-10-31 | 2025-10-30 | 2025-10-16 | Special Flanges S.p.A. - Italy
[7 empty] | Temp Transmitters | 3 | 2025-09-19 | 2025-10-15 | 2025-09-08 | 2025-12-08 | 2025-10-23 | 2025-09-30 | Rosemount Emerson - France
[7 empty] | Sensors (Type K TC Duplex) | 3 | 2025-09-19 | 2025-10-15 | 2025-09-22 | 2025-12-08 | 2025-11-23 | 2025-10-28 | H&B Sensors - UK
[7 empty] | Cabinet Enclosure Compartments | 1 | 2025-09-12 | 2025-11-05 | 2025-10-23 | 2025-10-24 | 2026-01-09 | 2026-01-09 | Rittal - France
[7 empty] | Gaskets | 3 | 2025-10-01 | 2025-11-05 | 2025-10-16 | 2025-12-17 | 2025-12-11 | 2025-11-20 | CALVO SEALING - Spain
[7 empty] | Studbolts | 1 | 2025-10-01 | 2025-11-05 | 2025-10-15 | 2025-12-17 | 2025-12-11 | 2025-11-11 | BECK PROSPER - UK
Main Issue
3 | M/R No. | ED1A.01 | KOM | 2025-04-22 | 2025-04-22 | 2025-04-22 | for Main | [8 empty] | Final inspection for template and anchor bolt | 2025-06-19 | 2025-06-19 | N-5000106900-001 | 2025-06-19 | pass | ALL | Anchor Bolt, Template, Sole Plate | 2025-06-01 | 2025-06-01 | 2025-06-01 |  | IRC-5000106900-0001 | 2025-06-30 | 2025-06-25 | 2025-06-25 |  |  | 2025-07-12 | 2025-07-12 | SC7128C-P1-KC017-CS | 2025-08-30 | 2025-08-17 | 2025-11-01
| M/R Name | Drum | Key V/P | 2025-04-15 | 2025-04-15 | 2025-04-15 | - Plate SA240-304/304L | 7 sheets | 2025-04-25 | 2025-04-25 | 2025-04-25 | 2025-06-18 | 2025-06-20 | 2025-06-20 | DKC, SM Steel / Korea | PIM | 2025-06-25 | 2025-06-25 | N-5000106900-002 | 2025-06-25 | pass | 40-V-9000 | HP FLARE KO DRUM ELECTRIC HEATER | 2025-06-19 | 2025-06-24 | 2025-06-24 |  | IRC-5000106900-0002 | 2026-01-26 | 2026-01-26 | 2026-01-26 |  |  | 2026-02-07 | 2026-02-08 | SC7128C-P1-KC116-CS | 2026-05-30 |  | 2026-03-07 | ATA Khor Fakkan port 4/25 - all except 40' HQ x1, POD Sohar, Oman
| P/O No. | 5000106900 | Sub-order Issued | 2025-04-25 | 2025-04-25 | 2025-04-25 | - Plate SA516-70 | 12 sheets | 2025-04-25 | 2025-04-25 | 2025-04-25 | 2025-06-18 | 2025-07-11 | 2025-07-11 | DONGKUK / Korea | Material inspection | 2025-07-01 2025-07-21 | 2025-07-01 2025-07-21 | N-5000106900-004 N-5000106900-005 | 2025-07-01 2025-07-21 | pass | 40-V-8501 | PLANT AIR BUFFER DRUM | 2025-06-19 | 2025-06-24 | 2025-06-24 |  | IRC-5000106900-0002 | 2026-01-26 | 2026-01-26 | 2026-01-26 |  |  | 2026-02-07 | 2026-02-08 | SC7128C-P1-KC116-CS | 2026-05-30 |  | 2026-05-09
| Q'ty(Item/Set) | 3 | Receive Main material | 2025-06-18 | 2025-06-18 | 2025-06-18 | for Nozzle | [8 empty] | Bevel NDE,FIT UP, Pipe marking | 2025-07-22 | 2025-07-22 | N-5000106900-006 | 2025-07-22 | pass | 40-V-8502 | INSTRUMENT AIR BUFFER DRUM | 2025-06-19 | 2025-06-24 | 2025-06-24 |  | IRC-5000106900-0002 | 2026-01-26 | 2026-01-26 | 2026-01-26 |  |  | 2026-02-07 | 2026-02-08 | SC7128C-P1-KC116-CS | 2026-05-30 |  | 2026-03-07
| Vendor Name | Shin Hwa M-Teech Co., Ltd. | PIM | 2025-06-02 | 2025-06-23 | 2025-06-23 | - Forging & Flange | 46 | 2025-05-30 | 2025-05-30 | 2025-06-05 | 2025-07-01 | 2025-07-01 | 2025-07-01 | KUMHO FORING / Korea | Nozzle, Head,FIT UP inspection | 2025-07-29 2025-08-04~07 2025-08-12~15 | 2025-07-29 2025-08-04~07 2025-08-12~15 | N-5000106900-007 N-5000106900-008 N-5000106900-009 | 2025-07-29 2025-08-04~07 2025-08-12~15 | pass pass pass
| Delivery Date | 2026-01-26 | Start Fabrication | 2025-06-19 | 2025-06-23 | 2025-06-24 | - Pipe SA312-TP304 | 3 | 2025-05-30 | 2025-05-30 | 2025-06-05 | 2025-07-01 | 2025-07-01 | 2025-07-01 | VARIOUS / Japan, Europe | Nozzle,Fit Up, Bevel, NDE inspection | 2025-08-18~21 | 2025-08-18~21 | N-5000106900-010 | 2025-08-18~21 | pass
| Delivery Term | FOB | Cargo ready | 2026-01-26 | 2026-01-26 | 2026-01-26 | - Pipe SA106-B | 8 | 2025-05-30 | 2025-05-30 | 2025-06-05 | 2025-07-01 | 2025-07-01 | 2025-07-01 | VARIOUS / Japan, Europe | Nozzle,Head,Shell,Fit Up,Bevel,NDE inspection | 2025-08-25~29 | 2025-08-25~29 | N-5000106900-011 | 2025-08-25~29 | pass
| Delivery Location | Busan, Korea |  |  |  |  | - Fitting SA403-304 | 7 | 2025-04-15 | 2025-04-15 | 2025-04-15 | 2025-08-30 | 2025-08-01 | 2025-08-01 | Busan Fitting, DK Bend / Kore | Pressure Vessel Drum_Inspection | 2025-09-01~05 2025-09-10~12 2025-09.18~19 2025-09-23~26 2025-09-30 2025-10-13 2025-10-22 2025-11-06~07 2025-11-13 & 17 2025-12-05 2025-12-31 | 2025-09-01~05 2025-09-10~12 2025-09.18~19 2025-09-23~26 2025-09-30 2025-10-13 2025-10-22 2025-11-06~07 2025-11-13 & 17 2025-12-05 2025-12-31 | N-5000106900-012 N-5000106900-013 N-5000106900-014 N-5000106900-015 N-5000106900-016 N-5000106900-017 N-5000106900-018 N-5000106900-019 N-5000106900-021 N-5000106900-022 N-5000106900-025 | 2025-09-01~05 2025-09-10~12 2025-09.18~19 2025-09-23~26 2025-09-30 2025-10-13 2025-10-22 2025-11-06~07 2025-11-13 & 17 2025-12-05 2025-12-31 | Pass Pass Pass Pass Pass Pass Pass Pass Pass Pass Pass
| Inspection Level | 3 |  |  |  |  | for Internal | [8 empty] | Hydro | 11/18~20 for 40-V-8501/8502 11/25, 28 for 40-V-9000 | 2025-11-18~28 | N-5000106900-020 | 2025-11-18~20.25.28 | Pass
| Vendor PIC | Dong Hoo Shin |  |  |  |  | - Demister 316LSS | 1 | 2025-04-15 | 2025-04-15 | 2025-04-15 | 2025-08-30 | 2025-08-30 | 2025-08-30 | MTT / Korea | Painting Inspection | 12/17~19 40-V-8501 12/23 40-V-8502 | 12/17~19 40-V-8501 12/23 40-V-8502 | N-5000106900-023 N-5000106900-024 | 12/17~19 40-V-8501 12/23 40-V-8502 | Pass
| SCJV PE | Michelle Chen |  |  |  |  | Accessory | [8 empty] | Blast/SQR and Packing Inspection of 40-V-8501/8502 | 2026-01-06, 09 | 2026-01-06, 09 | N-5000106900-026 | 2026-01-06, 09 | Pass
| SCJV RE | Michelle Chen |  |  |  |  | - Plate CS & SS | 13 | 2025-05-30 | 2025-05-30 | 2025-06-05 | 2025-07-30 | 2025-08-30 | 2025-08-30 | VARIOUS / Korea | After Coating 40-V-9000 Packing for P&L | 2026-01-15~16 | 2026-01-15~16 | N-5000106900-027 | 2026-01-15~16 | Pass
| SCJV Expeditor | Heesun Park |  |  |  |  | - Bolt & Nuts |  | 2025-08-15 | 2025-09-24 | 2025-09-24 | 2025-10-30 | 2025-11-15 | 2025-11-15 |  | Gasket Surface and Packing for 40-V-9000 + remaining box of 40-V-8501/8502 | 2026-01-21~23 | 2026-01-21~23 | N-5000106900-028 | 2026-01-21~23 | Pass
| SCJV Buyer | Daniel Hsieh |  |  |  |  | - Gasket |  | 2025-08-15 | 2025-09-24 | 2025-09-24 | 2025-10-30 | 2025-11-15 | 2025-11-15 |  | SQR Review | 2026-02-02 | no TPI and via VP | N-5000106900-029 | N/A | pass
| Main Issue | [14 empty] | PIM 6/23 | [5 empty] | Template - Fabrication will be completed on June 10th, 2025. Anchor Bolt – It will be delivered to our shop on June 17th, 2025 Sole Plate,Template and anchor bolt: inspection on Jun 19 2025
Formulas:
Delivery At site = [Shipping & Delivery]+50

## Rotating
No. | PO information |  | Key Milestone |  |  |  | Sub-Order Status | [8 empty] | Inspection Status | [5 empty] | Manufacturing Progress | [9 empty] | Shipping & Delivery
|  |  | Key Milestone | Plan | Forecast | Actual | Sub-Order Item | Q'ty | Sub-Order Issued |  |  | Sub-Order Received |  |  | Sub-Vendor | Major Inspection Plan |  |  | Inspection Application |  |  | Item No. | Item Name | Start Fabricatioin |  |  | SQR | IRC | Cargo Ready |  |  | Material shipped |  | Shipment No. | Delivery At site |  | ROS (Baseline)
[9 empty] | Plan | Forecast | Actual | Plan | Forecast | Actual |  | Type | Forecast | Actual | NOI no. | Insp. Date | Result |  |  | Plan | Forecast | Actual | Transmittal no. | number # | Plan | Forecast | Actual | ETD | ATD |  | ETA | ATA
1 | M/R No. | FW2A.01 | KOM | 2025-03-04 | 2025-03-04 | 2025-03-04 | METERING PUMP(API675) | 10 | 2025-04-30 | 2025-05-12 | 2025-03-26 | 2025-10-16 | 2025-08-31 | 2025-08-14 | Milton Roy/China | PIM | 2025-08-05 | 2025-08-05 | N-5000106307-001 | 2025-08-05 | pass | 40-PK-8301 | Remineralization Package | 2025-07-15 | 2025-10-13 | 2025-10-13 | IN-SCJV5000106307-1-VT088 | IRC-5000106307-0001 | 2026-02-07 | 2026-02-26 | 2026-02-26 | 2026-05-02 | 2026-05-03 | SC7128C-P2-KC117-CS | 2026-07-18 |  | 2026-04-09 | FR: space confirmed, ETA Jeddah, KSA 6/28 | 2026-03-10 booking cancelled
| M/R Name | Chemical Injection Package | Key V/P Submission | 2025-03-11 | 2025-03-18 | 2025-03-14 | METERING PUMP(API675) | 1 | 2025-04-30 | 2025-05-12 | 2025-03-26 | 2025-10-16 | 2025-11-12 | 2025-11-07 | Milton Roy/China | FRP Tank Full Water Test | 2025-11-17 | 2025-11-17 | N-5000106307-002 | 2025-11-17 | pass | 40-PK-8302 | Sodium Hypochlorite Package | 2025-07-15 | 2025-10-13 | 2025-10-13 | IN-SCJV5000106307-1-VT088 | IRC-5000106307-0001 | 2026-02-07 | 2026-02-26 | 2026-02-26 | 2026-05-02 | 2026-05-03 | SC7128C-P2-KC117-CS | 2026-07-18 |  | 2026-04-02 | FR: space confirmed, ETA Jeddah, KSA 6/28 | 2026-03-10 booking cancelled
| P/O No. | 5000106307 | Sub-order Issued | 2025-04-30 | 2025-05-12 | 2025-05-12 | LV-MOTOR | 11 | 2025-04-30 | 2025-05-12 | 2025-05-12 | 2025-09-27 | 2025-11-30 | 2025-11-20 | Hyundai/Korea (5/23 PO rev) | Tank Hydrostatic Test | 2025-12-26 | 2025-12-26 | N-5000106307-003 | 2025-12-26 | pass | [16 empty] | updated ROS = 2026-07-30
| Q'ty(Item/Set) | 2 | Sub-order completed | 2025-09-10 | 2025-10-20 | TBD | PRESSURE SAFETY(RELIEF) VALVE | 4 | 2025-03-20 | 2025-05-12 | 2025-04-23 | 2025-10-16 | 2025-10-20 | 2025-10-10 | Tai Milano/Italy | Piping Hydrostatic Test | 2025-12-26 | 2025-12-26 | N-5000106307-003 | 2025-12-26 | pass
| Vendor Name | Decatech | Receive Main material | 2025-10-16 | 2025-10-16 | Pump 8/14~ PSV 10/10~ Motor 10/30 | PSV(CS+Lined) | 7 | 2025-07-25 | 2025-06-30 | 2025-06-26 | 2025-09-23 | 2025-11-09 | 2025-11-04 | Leser | Steel Structure VI/DI | 2025-12-30 | 2025-12-30 | N-5000106307-004 | 2025-12-30 | pass
| Delivery Date | 2026-02-17 | PIM | 2025-07-01 | 2025-08-05 | 2025-08-05 | PULSATION DAMPENER | 11 | 2025-06-25 | 2025-06-25 | 2025-05-28 | 2025-10-23 | 2025-12-24 | 2025-12-17 | Fox/Italy | PTFE lining Hydro | 2026-01-12 | 2026-01-12 | N-5000106307-005 | 2026-01-12 | pass
| Delivery Term | FOB | Start Fabrication | 2025-07-15 | 2025-10-21 | 2025-10-13 | CALIBRATION POT | 11 | 2025-07-25 | 2025-07-30 | 2025-07-14 | 2025-09-23 | 2025-10-20 | 2025-09-22 | Viewtech/Korea | FAT | 2026-02-12~13 | 2026-02-12~13 | N-5000106307-006 | 2026-02-12~13 | pass
| Delivery Location | Busan | Final Inspection | 2026-01-21 | 2026-02-13 | 2026-02-13 | LEVEL GAUGE | 3 | 2025-07-25 | 2025-07-30 | 2025-07-07 | 2025-09-15 | 2025-09-15 | 2025-08-29 | Wise/Korea | Punch Clear, Packing | 2026-02-26~27 | 2026-02-26~27 | N-5000106307-007 | 2026-02-26~27 | pass
| Inspection Level | 3 | Cargo ready | 2026-02-07 | 2026-02-26 | 2026-02-27 | PRESSURE GAUGE | 22 | 2025-06-25 | 2025-07-30 | 2025-07-07 | 2025-10-23 | 2025-09-15 | 2025-08-29 | Wise/Korea
| Vendor PIC | Do-Hyun Lee |  |  |  |  | LEVEL TRANSMITTER | 3 | 2025-06-25 | 2025-06-04 | 2025-06-04 | 2025-10-23 | 2025-09-18 | 2025-08-28 | Yokogawa
| SCJV PE | Michelle Chen |  |  |  |  | PRESSURE TRANSMITTER (Rupture) | 11 | 2025-06-25 | 2025-07-15 | 2025-07-01 | 2025-10-23 | 2025-10-20 | 2025-09-16 | Yokogawa
| SCJV RE | Steven Chen |  |  |  |  | Junction Box | 1 LOT | 2025-08-30 | 2025-09-15 | 2025-09-02 | 2025-12-30 | 2025-12-04 | 2025-10-22 | TM Solution
| SCJV Expeditor | Heesun Park |  |  |  |  | CABLE TRAY |  | 2025-09-10 | 2025-10-13 | 2025-09-29 | 2026-01-08 | 2026-01-08 | 2025-10-22 | Dae Han Tray Industry
| SCJV Buyer | Derek Chen |  |  |  |  | ANGLE, PIPING, C-CHANEL, PLATE etc | 1 LOT | 2025-05-15 | 2025-09-15 | 2025-09-29 | 2025-06-14 | 2025-10-15 | 2025-10-15 | 9/8 skid frame fab start
[7 empty] | PLATE for TANK, DRIP PAN | 1 LOT | 2025-08-25 | 2025-09-15 | TBD | 2025-09-24 | 2025-09-30
[7 empty] | FLANGE & FITTING | 1 LOT | 2025-06-01 | 2025-07-25 | 2025-07-17 | 2025-09-29 | 2025-10-20 | 2025-09-11
[7 empty] | PIPE (SS) | 1 LOT | 2025-08-01 | 2025-07-16 | 2025-07-16 | 2025-10-24 | 2025-07-23 | 2025-07-23
[7 empty] | FRP TANK | 1 LOT | 2025-08-10 | 2025-08-10 | 2025-07-23 | 2025-10-08 | 2025-11-21 | hydro completed | Namyung e&g
[7 empty] | BACK PRESSURE VALVE | 3 ea | 2025-10-15 | 2025-10-15 | 2025-10-15 | 2026-01-15 | 2026-01-15 | 2026-01-14 | Newin Tech
[7 empty] | CHECK/GATE/BALL VALVE and STRAINER | 1 LOT | 2025-06-01 | 2025-06-01 | 2025-05-28 | 2025-09-29 | 2025-09-04 | 2025-08-21 | KOOKJE International
[7 empty] | J/B, & CABLE TRAY FOR INSTRUMENTS |  | 2025-09-10 | 2025-09-10 | 2025-09-15 | 2026-01-08 | 2026-01-08
[7 empty] | GASKET, BOLT & NUT |  | 2025-08-10 | 2025-09-15 | 2025-09-10 | 2025-09-09 | 2025-10-15 | 2025-09-29
[7 empty] | HOOK-UP MATERIAL(TUBE&FITTING) |  | 2025-07-20 | 2025-07-20 | 2025-07-20 | 2025-10-18 | 2025-08-04 | 2025-08-04
|  |  | [General] 12/9 DCT informed one week delay |  |  |  | [Current Status and Issue] | [8 empty] | [Current Status and Issue] | [5 empty] | [Current Status and Issue] | [9 empty] | [Current Status and Issue]
2 | M/R No. | MC2A.51 | KOM | 2025-03-10 | 2025-03-10 | 2025-03-10 | Fire pump case castings | 4 | Stock | Stock | Stock | Stock | Stock | Stock | Patterson Ireland | Electric motor Performance test | 2025-08-28 | 2025-08-28 | N-5000106431-001 | 2025-07-25 | PASS | 40-P-8421A | Fire Water Pump | 2025-09-15 | 2025-09-15 | 2025-09-02 | IN-SCJV5000106431-1-VT084 | IRC-5000106431-0001 | 2025-12-24 | 2026-02-27 | 2026-02-27 | 2026-06-10 | booking pending | SC7128C-P2-EC169-CS | 2026-08-09 |  | 2026-03-07
| M/R Name | Fire Water Pump | Key V/P | 2025-03-31 | 2025-03-31 | 2025-03-31 | Fire pump impeller castings | 4 | 2025-02-15 | 2025-02-15 | 2025-02-18 | 2025-08-30 | 2025-08-30 | 2025-08-25 | Patterson Ireland | FTA/iFAT | 3~7/11/2025 | 3~7/11/2025 | N-5000106431-001 | 2025-10-16 | PASS | 40-P-8421B | Fire Water Pump | 2025-09-15 | 2025-09-15 | 2025-09-02 | IN-SCJV5000106431-1-VT084 | IRC-5000106431-0001 | 2025-12-24 | 2026-02-27 | 2026-02-27 | 2026-06-10 | booking pending | SC7128C-P2-EC169-CS | 2026-08-09 |  | 2026-03-25 | consignee issues
| P/O No. | 5000106431 | Sub-order Issued | 2025-04-30 | 2025-05-12 | 2025-02-18 | Diesel engine | 3 | 2025-02-15 | 2025-02-15 | 2025-02-18 | 2025-08-30 | 2025-08-30 | 2025-08-30 | Clarke USA | hydro, performance & MRT | 2026-02-04~05 | 2026-02-04~05 | N-5000106431-003 | 2026-02-04~05 | PASS | 40-P-8421C | Fire Water Pump | 2025-09-15 | 2025-09-15 | 2025-09-02 | IN-SCJV5000106431-1-VT084 | IRC-5000106431-0001 | 2025-12-24 | 2026-02-27 | 2026-02-27 | 2026-06-10 | booking pending | SC7128C-P2-EC169-CS | 2026-08-09 |  | 2026-04-06
| Q'ty(Item/Set) | 4 | Receive Main material | 2025-08-31 | 2025-08-31 | 2025-08-30 | Fire water electric motor (MV) | 1 | 2025-02-12 | 2025-02-12 | 2025-02-12 | 2025-11-15 | 2025-12-30 | 2025-12-30 | Hyundai Korea | DFT, Final, Packing | 2026-02-20 | 2026-02-20 | N-5000106431-004 | 2026-02-20 | PASS | 40-P-8421D | Fire Water Pump | 2025-09-15 | 2025-09-15 | 2025-09-02 | IN-SCJV5000106431-1-VT084 | IRC-5000106431-0001 | 2025-12-24 | 2026-02-27 | 2026-02-27 | 2026-06-10 | booking pending | SC7128C-P2-EC169-CS | 2026-08-09 |  | 2026-04-18
| Vendor Name | Patterson Pump Company | PIM | N/A | N/A | N/A | Diesel controller with converter | 3 | 2025-02-10 | 2025-02-10 | 2025-02-10 | 2025-11-30 | 2026-01-20 | 2026-01-20 | Firetrol USA
| Delivery Date | 2026-01-20 | Start Fabrication | 2025-09-15 | 2025-09-15 | 2025-09-02 | Electric controller with converter | 1 | 2025-02-10 | 2025-02-10 | 2025-02-10 | 2025-11-30 | 2026-01-20 | 2026-01-20 | Firetrol USA
| Delivery Term | FOB | Final Inspection | 2025-12-20 | 2026-02-20 | 2026-02-20 | Jockey controller with converter | 2 | 2025-02-10 | 2025-02-10 | 2025-02-10 | 2025-11-30 | 2026-01-20 | 2026-01-20 | Firetrol USA
| Delivery Location | Dublin | Cargo ready | 2025-12-24 | 2026-02-27 | 2026-02-27 | Diesel fire pump drive shaft | 3 | 2025-02-15 | 2025-02-15 | 2025-02-18 | 2025-08-30 | 2025-08-30 | 2025-08-30 | Clarke USA
| Inspection Level | 2 |  |  |  |  | Electric fire pump coupling | 1 | 2025-02-15 | 2025-02-15 | 2025-02-18 | 2025-08-30 | 2025-08-30 | 2025-08-25 | FALK USA
| Vendor PIC | Lampros Veliotis |  |  |  |  | Engine Exhaust Muffler | 3 | 2025-05-20 | 2025-07-04 | 2025-07-04 | 2025-08-30 | 2025-08-30 | 2025-08-30 | MulMuf Ireland
| SCJV PE | Rebecca Chen |  |  |  |  | Engine Battery (set) | 3 | Stock | Stock | Stock | Stock | Stock | Stock | AMPAC Ireland
| SCJV RE | Nick Chen |  |  |  |  | Fuel Tank | 3 | 2025-05-15 | 2025-07-07 | 2025-07-07 | 2025-10-30 | 2025-12-15 | 2025-12-15 | Patterson Ireland
| SCJV Expeditor / Buyer | Derek Chen |  |  |  |  | Magnetic side mounted fuel level gauge | 3 | 2025-05-15 | 2025-07-09 | 2025-07-09 | 2025-10-30 | 2025-12-15 | 2025-12-15 | WIKA Germany
[7 empty] | Fuel Level Switch | 3 | 2025-02-10 | 2025-02-10 | 2025-02-10 | 2025-10-30 | 2025-12-15 | 2025-12-15 | Firetrol USA
[7 empty] | MPRV | 3 | 2025-02-15 | 2025-02-15 | 2025-02-18 | 2025-08-30 | 2025-08-30 | 2025-07-15 | Claval USA
[7 empty] | Enclosed Waste cone | 3 | Stock | Stock | Stock | Stock | Stock | Stock | Patterson Ireland
[7 empty] | Flow Meter | 1 | 2025-05-15 | 2025-07-15 | 2025-07-15 | 2025-10-30 | 2025-12-15 | 2025-12-15 | Global USA
[7 empty] | Sound Enclosure | 3 | 2025-05-15 | 2025-06-27 | 2025-06-27 | 2025-08-30 | 2025-10-30 | 2025-10-30 | Patterson Ireland
[7 empty] | Air Release Valve | 4 | Stock | Stock | Stock | Stock | Stock | Stock | Claval USA
[7 empty] | Casing Relief Valve 1" for Electric fire pump | 1 | Stock | Stock | Stock | Stock | Stock | Stock | Claval USA
[7 empty] | Pressure Gauges (set) | 6 | Stock | Stock | Stock | Stock | Stock | Stock | WIKA Germany
[7 empty] | Casing Relief Valve 3/4" for Jockey pumps | 2 | Stock | Stock | Stock | Stock | Stock | Stock | CashAcme USA
| Main Issue | [20 empty] | [Current Status and Issue] | [9 empty] | [Current Status and Issue]
3 | M/R No. | FC1B.01 | KOM | 2025-04-07 | 2025-04-07 | 2025-04-07 | Air Compressor | 2 | 2025-04-25 | 2025-05-27 | 2025-05-27 | 2025-08-22 | 2025-11-07 | 2025-11-07 | Ingersoll Rand, China | Hydrotest Air end Casing | 2025-08-21 | 2025-08-21 | N-5000106483-001 | 2025-08-21 | Accepted | 40-PK-8500 A | Air Compressor Package | 2025-09-05 | 2025-09-05 | 2025-09-04 |  |  | 2025-11-21 | 2026-04-13 |  | 2026-05-25 |  | SC7128C-P2-KC196-CS | 2026-07-28 |  | 2026-03-08 | updated ROS = 2026-08-04 | ETA Jeddah 6/29
| M/R Name | Air Compressor (Include Instrument Air Dryer) | Key V/P Submission | 2025-04-10 | 2025-06-05 | 05-08~06-13 | AIR COMPRESSOR MODIFICATION |  | 2025-12-06 | 2026-01-23 | 2026-01-23 | 2026-02-21 | 2026-02-21 | 2025-12-29 | Firscomp, Korea | Hydro-static test for drying tower | 2025-09-30 | 2025-09-30 | N-5000106483-002 | 2025-09-30 | Accepted | 40-PK-8500 B | Air Compressor Package | 2025-09-05 | 2025-09-05 | 2025-09-04 |  |  | 2025-11-21 | 2026-04-13 |  | 2026-05-25 |  | SC7128C-P2-KC196-CS | 2026-07-28 |  | 2026-03-19 | OT
| P/O No. | 5000106483 | Sub-order Issued | 2025-04-18 | 2025-05-28 | 2025-05-28 | Air Dryer | 2 | 2025-04-25 | 2025-05-28 | 2025-05-28 | 2025-08-15 | 2025-11-25 | 2025-11-25 | Gastech, Korea | UCP FAT & Pre iFAT | 03-16~03-20 | 03-16~03-20 | N-5000106483-003 | 03-16~03-20 | Accepted | 40-PK-8501 A | Air Dryer Package | 2025-09-05 | 2025-09-05 | 2025-09-04 |  |  | 2025-11-21 | 2026-04-13 |  | 2026-05-25 |  | SC7128C-P2-KC196-CS | 2026-07-28 |  | 2026-04-06
| Q'ty(Item/Set) | 4 | Receive Main material | 2025-08-31 | 2025-09-30 | 2025-08-20 2025-09-04 | AIR DRYER MODIFICATION |  | 2025-12-06 | 2026-01-23 | 2026-01-23 | 2026.02.21 | 2026-02-21 | 2025-12-29 | Firscomp, Korea | FAT of Compressor/Dryer | 04-07~04-09 | 04-07~04-09 | N-5000106483-004 | 04-07~04-09 | punch closing | 40-PK-8501 B | Air Dryer Package | 2025-09-05 | 2025-09-05 | 2025-09-04 |  |  | 2025-11-21 | 2026-04-13 |  | 2026-05-25 |  | SC7128C-P2-KC196-CS | 2026-07-28 |  | 2026-04-13
| Vendor Name | Ingersoll Rand Korea Ltd. | PIM | N/A | N/A | N/A | UCP Panel |  | 2025-05-09 | 2025-05-14 | 2025-05-14 | 2025-08-15 | 2026-03-16 | 2026-03-16 | Engineers Korea | Punch Clear | 2026-05-11 | 2026-05-11 | N-5000106483-005 |  |  | 40-PK-8501 A | On/Off Valve 4 sets | [8 empty] | TBC |  |  |  |  | TBD
| Delivery Date | 2025-11-30 | Start Fabrication | 2025-09-05 | 2025-10-05 | 2025-09-04 | UCP Panel installation | 2 | 2025-04-25 | TBC |  | 2025-08-15 | 2026-03-16 | 2026-03-16 | Firscomp, Korea / fabrication by IRK | Packing | 2026-05-18 | 2026-05-18 | N-5000106483-006 |  |  | 40-PK-8501 B | On/Off Valve 4 sets | [8 empty] | TBC |  |  |  |  | TBD
| Delivery Term | FOB | Final Inspection | 2025-10-24 | Pkg FAT ~4/10 Packing TBD | Pkg FAT 4/7~4/9 | Main Motor | 2 | 2025-04-18 | 2025-05-09 | 2025-05-09 | 2025-07-18 | 2025-09-30 | 2025-10-01 | HHI_MT1, Korea | On/Off Valve 8 sets | 2026-05-22 | [5 empty] | UCP (to Yokogawa shop) | [8 empty] | UCP Delivery
| Delivery Location | Korea, China | Cargo ready | 2025-11-30 | 2026-04-30 |  | Temperature Transmitter | 10 | 2025-06-17 | 2025-06-17 | 2025-06-17 | 2025-09-20 | 2025-12-08 | 2025-12-08 | Emerson | [15 empty] | to RIE shop | 2026-04-28 | 2026-04-29 | SC7128C-P2-KT197-V | 2026-04-30 | 2026-04-30 | 2026-03-31 | DDP
| Inspection Level | 2 |  |  |  |  | Pressure Transmitter | 12 | 2025-06-17 | 2025-06-17 | 2025-06-17 | 2025-09-20 | 2025-12-08 | 2025-12-08 | Emerson | [15 empty] | to site | Mid June |  | SC7128C-P2-KC235-SS
| Vendor PIC | Pi, Kwang Hyun |  |  |  |  | Diff. Pressure Transmitter | 4 | 2025-06-17 | 2025-06-17 | 2025-06-17 | 2025-09-20 | 2025-12-08 | 2025-12-08 | Emerson
| SCJV PE | Rebecca Chen |  |  |  |  | Solenoid valve | 8 | 2025-06-17 | 2025-06-17 | 2025-06-17 | 2025-09-20 | 2025-12-08 | 2025-12-08 | Bifold
| SCJV RE | Ann-Ann Szu |  |  |  |  | LP & JB FOR AIR COMPRESSOR | 1 | 2025-12-06 | 2026-01-23 | 2026-01-23 | 2025-12-06 | 2026-03-17 | 2026-03-12 | Bartec, installation by Firscomp
| SCJV Expeditor | Heesun Park |  |  |  |  | LP & JB FOR AIR DRYER | 1 | 2025-12-06 | 2026-01-23 | 2026-01-23 | 2025-12-06 | 2026-03-17 | 2026-03-12 | Bartec, installation by Firscomp
| SCJV Buyer | Andrew Zheng->Derek Chen |  |  |  |  | On/Off Valve | [7 empty] | Assembly at Gastech shop
[7 empty] | - Actuator w.equlizing valve | 8 | 2025-11-28 | 2025-12-12 | 2025-12-10 | 2026-03-20 | 2026-04-24 | 2026-05-18 | Yudam Tech (HKC / HP-115D / Lead Time : ARO 4.5 months)
[7 empty] | - Solenoid Valve | 8 | 2025-11-28 | 2025-12-12 | 2025-12-10 | 2026-04-03 | 2026-05-15 | 2026-05-18 | Yudam Tech (ASCO / NFET8551A322 / Lead Time : ARO 4.5 months)
[7 empty] | - Limit Switch | 8 | 2025-11-28 | 2025-12-12 | 2025-12-10 | 2026-04-03 | 2026-05-15 | 2026-05-18 | Yudam Tech (TOPWORX / TXP-S21GLMM / Lead Time : ARO 4.5 months)
[7 empty] | - Regulator with filter | 8 | 2025-11-28 | 2025-12-12 | 2025-12-10 | 2026-02-13 | 2026-05-15 | 2026-05-18 | Yudam Tech
[7 empty] | - Common Regulator with Filter) | 8 | 2025-11-28 | 2025-12-12 | 2025-12-10 | 2026-02-13 | 2026-05-15 | 2026-05-18 | Yudam Tech
[7 empty] | - Valve Body | 8 | - | 2025-12-15 | 2025-12-15 | 2026-04-24 | 2026-05-15 | 2026-05-18 | Yudam Tech
[7 empty] | - Valve Assembly & Inspection | 8 | - | 2025-12-15 | 2025-12-15 | 2026-05-05 | 2026-05-22 |  | Yudam Tech
[7 empty] | - Air Compressor Modification | 2 | 2025-12-06 | 2026-01-23 | 2026-01-23 | 2026-02-21 | 2026-02-21 | 2025-12-29 | Yudam Tech
[7 empty] | - Air Dryer Modification | 2 | 2025-12-06 | 2026-01-23 | 2026-01-23 | 2026-02-21 | 2026-02-21 | 2025-12-29 | Yudam Tech
|  |  | [General] PID & Alarm List to be obtained within Aug. 29,2025. 12/9 meeting : separate delivery of on/off valve set in Apr |  |  |  | [Current Status and Issue] 1. Specific Air Dryer Nozzle is currently expecting longer lead time to procure due to less purchasing nozzle qty, and delivery delay of 1 month is currently expected 2. IRK will endeavor to limit the delivery impact to 15 days 9/16 Fan motor fabricated and main motor under fabrication, motor may not be shipped to China factory for securing delivery, Firscomp is inhouse company of IRK 10/28 JB&LP delay → IRK will send Mitigation Plan by Nov 3rd 11/5 additional delay due to on-off valve → Mitigation Plan including JB&LP received : plan A without JB&LP - FAT 2026.02.05 Packing 2026.02.18 / plan B with JB&LP - FAT 2026.05.05 Packing 2026.03.20 / on-off valve FOB 2026.05.15 | [8 empty] | wwa | [5 empty] | [Current Status and Issue] | [9 empty] | [Current Status and Issue]
4 | M/R No. | FD1E.01 | KOM | 2025-02-24 | 2025-02-24 | 2025-02-24 | Casing | 4 | 2025-02-19 | 2025-02-19 | 2025-02-19 | 2025-09-16 | 2025-09-16 | 2025-05-30 |  | Hydrostatic test | 2025-09-25 | 2025-09-25 | NOI-N-5000105913-001 | 2025-09-25 | Pass | 40-P-8301 | Utility Water Pump | 2025-09-17 | 2025-09-17 | 2025-09-04 | N-SCJV5000105913-1-VT037 | IRC-5000105913-0001 | 2025-11-28 | 2025-11-28 | 2025-11-28 | 2025-12-27 | 2025-12-28 | SC7128C-P2-KC091-CS | 2026-02-04 | 2026-02-03 | 2026-03-07
| M/R Name | Pump (ANSI OH1) | Key V/P | 2025-04-11 | 2025-04-07 | 2025-04-07 | Impeller | 4 | 2025-02-19 | 2025-02-19 | 2025-02-19 | 2025-09-16 | 2025-09-16 | 2025-05-30 |  | Performance test | 2025-10-30 | 2025-10-30 | NOI-N-5000105913-002 | 2025-10-30 | Pass | 40-P-8302A | Portable Water Pump | 2025-09-17 | 2025-09-17 | 2025-09-04 | N-SCJV5000105913-1-VT037 | IRC-5000105913-0001 | 2025-11-28 | 2025-11-28 | 2025-11-28 | 2025-12-27 | 2025-12-28 | SC7128C-P2-KC091-CS | 2026-02-04 | 2026-02-03 | 2026-03-25
| P/O No. | 5000105913 | Sub-order Issued | 2025-02-19 | 2025-02-19 | 2025-02-19 | Shaft | 4 | 2025-02-19 | 2025-02-19 | 2025-02-19 | 2025-09-16 | 2025-09-16 | 2025-09-19 |  | Final inspection | 2025-11-12 | 2025-11-12 | NOI-N-5000105913-003 | 2025-11-12 | Pass | 40-P-8302B | Portable Water Pump | 2025-09-17 | 2025-09-17 | 2025-09-04 | N-SCJV5000105913-1-VT037 | IRC-5000105913-0001 | 2025-11-28 | 2025-11-28 | 2025-11-28 | 2025-12-27 | 2025-12-28 | SC7128C-P2-KC091-CS | 2026-02-04 | 2026-02-03 | 2026-04-06
| Q'ty(Item/Set) | 4 | Receive Main material | 2025-09-16 | 2025-09-16 | 2025-09-17 | Coupling | 4 | 2025-02-19 | 2025-02-19 | 2025-02-19 | 2025-09-16 | 2025-09-16 | 2025-09-07 | [7 empty] | 40-P-8331 | Portable Water Pump | 2025-09-17 | 2025-09-17 | 2025-09-04 | N-SCJV5000105913-1-VT037 | IRC-5000105913-0001 | 2025-11-28 | 2025-11-28 | 2025-11-28 | 2025-12-27 | 2025-12-28 | SC7128C-P2-KC091-CS | 2026-02-04 | 2026-02-03 | 2026-04-18
| Vendor Name | YPPC | PIM | N/A | N/A | N/A | LV motor | 4 | 2025-02-19 | 2025-02-19 | 2025-02-19 | 2025-09-16 | 2025-09-16 | 2025-09-16
| Delivery Date | 2025-11-28 | Start Fabrication | 2025-09-17 | 2025-09-17 | 2025-09-04 | Mechanical seal | 4 | 2025-02-19 | 2025-02-19 | 2025-02-19 | 2025-09-16 | 2025-09-16 | 2025-09-17
| Delivery Term | FOB | Cargo ready | 2025-11-28 | 2025-11-28 | 2025-11-28 | Mechanical seal plan 32 panel | 1 | 2025-02-19 | 2025-02-19 | 2025-02-19 | 2025-09-16 | 2025-09-16 | 2025-09-11
| Delivery Location | Korea
| Inspection Level | 2
| Vendor PIC | Hyunbin Choi
| SCJV PE | Michelle Chen
| SCJV RE | Leo Lin
| SCJV Expeditor | Heesun Park
| SCJV Buyer | Daniel Hsieh
| Main Issue | [20 empty] | [Current Status and Issue] | [9 empty] | [Current Status and Issue]
5 | M/R No. | FD1A.01 | KOM | 2025-04-07 | 2025-04-07 | 2025-04-07 | Casing |  | 2025-04-21 | 2025-04-21 | 2025-04-21 | 2025-10-06 | 2025-08-22 | 2025-08-22 | Bokyung | Hydrostatic | 2025-09-17 | 2025-09-17 | N-5000106805-001 | 2025-09-17 | pass | 40-PK-4822A | Fire Jockey Pump | 2025-09-05 | 2025-09-05 | 2025-09-02 | IN-SCJV5000106805-1-VT034 | IRC-5000106805-001 | 2025-11-30 | 2025-10-30 | 2025-10-30 | 2025-11-29 | 2025-11-29 | SC7128C-P2-KC090-CS | 2026-01-07 | 2026-01-08 | 2026-05-11 | ATA port 1/6
| M/R Name | Fire Jockey Pump | Key V/P | 2025-04-14 | 2025-04-14 | 2025-04-14 | Impeller |  | 2025-04-21 | 2025-04-21 | 2025-04-21 | 2025-10-06 | 2025-08-11 | 2025-08-11 | JSON | Resonance, Performance & MRT | 2025-10-13/14 | 2025-10-14 | N-5000106805-002 | 2025-10-14 | pass | 40-PK-4822B | Fire Jockey Pump | 2025-09-05 | 2025-09-05 | 2025-09-02 | IN-SCJV5000106805-1-VT034 | IRC-5000106805-001 | 2025-11-30 | 2025-10-30 | 2025-10-30 | 2025-11-29 | 2025-11-29 | SC7128C-P2-KC090-CS | 2026-01-07 | 2026-01-08 | 2026-04-29
| P/O No. | 5000106805 | Sub-order Issued | 2025-04-21 | 2025-04-21 | 2025-04-21 | Shaft |  | 2025-04-21 | 2025-04-21 | 2025-04-21 | 2025-10-06 | 2025-07-24 | 2025-07-24 | Micro | Alignment Check | 2025-10-14/15 | 2025-10-15 | N-5000106805-002 | 2025-10-15 | pass
| Q'ty(Item/Set) | 2 | Receive Main material | 2025-09-30 | 2025-09-30 | 2025-08-22 | Motor |  | 2025-04-21 | 2025-04-21 | 2025-04-21 | 2025-10-22 | 2025-10-22 | 2025-09-19 | Hyundai | Hydrotest for aux. piping | 2025-10-16 | 2025-10-16 | N-5000106805-002 | 2025-10-16 | pass
| Vendor Name | Hyosung | Assembly | 2025-10-14 | 2025-10-14 | 2025-10-15 | Seal |  | 2025-04-21 | 2025-04-21 | 2025-04-21 | 2025-10-09 | 2025-10-09 | 2025-09-02 | KSM (Flowserve Korea) | Final (VI/DI, Painting) | 2025-10-23/24 | 2025-10-23/24 | N-5000106805-002 | 2025-10-23/24 | pass
| Delivery Date | 2025-11-30 | Inspection and Test (Performance & MRT) | 2025-11-18 | 2025-10-14 | 2025-10-15
| Delivery Term | FOB | Packing | 2025-11-26 | 2025-10-23 | 2025-10-23
| Delivery Location | Korea | Cargo ready | 2025-11-30 | 2025-11-30 | 2025-10-30
| Inspection Level | 2
| Vendor PIC | JK Youn
| SCJV PE | Rebecca Chen
| SCJV RE | Andy Zhang
| SCJV Expeditor | Heesun Park
| SCJV Buyer | Derek Chen
|  |  | [General] |  |  |  | [Current Status and Issue] | [8 empty] | [Current Status and Issue] | [5 empty] | [Current Status and Issue] | [9 empty] | [Current Status and Issue]
6 | M/R No. | FZ9A.01 | KOM | 2025-06-18 | 2025-06-18 | 2025-06-18 | Oil skimmer loose items ( joint, pipe, support) | lot | 2025-08-01 | 2025-08-15 | 2025-08-13 | 2025-09-15 | 2025-09-17 | 2025-09-17 |  | performance test | 2025-12-30 | 2025-12-30 | N-5000107980-001 | 2025-12-30 | pass | 40-Z-8331 | Oil skimmer | 2025-09-16 | 2025-09-29 | 2025-09-29 | IN-SCJV5000107980-1-VT021 | IRC-5000107980-0001 | 2025-11-30 | 2026-01-19 | 2026-01-19 | 2026-03-06 | 2026-02-28 | SC7128C-P2-AL138-CS | 2026-06-20 |  | 2026-03-07 | updated ROS = 2026-07-15
| M/R Name | Floating Oil Skimmer | Key V/P | 2025-07-15 | 2025-07-15 | 2025-06-20 | Frame of floating oil skimmer | 1 | 2025-08-01 | 2025-08-15 | 2025-08-13 | 2025-09-01 | 2025-09-01 | 2025-09-01 |  | Final inspection | 2025-12-30 | 2025-12-30 | N-5000107980-002 | 2025-12-30 | pass | [16 empty] | POD: TBD
| P/O No. | 5000107980 | Sub-order Issued | 2025-08-01 | 2025-08-15 | 2025-08-13 | Weir of floating oil skimmer | 1 | 2025-08-01 | 2025-08-15 | 2025-08-13 | 2025-09-01 | 2025-09-01 | 2025-09-01 |  | Cleaness check inspection | 2026-01-13 | 2026-01-13 | N-5000107980-003 | 2026-01-13 | pass
| Q'ty(Item/Set) | 1 | Receive Main material | 2025-09-15 | 2025-09-17 | 2025-09-17 | Float of floating oil skimmer | 2 | 2025-08-01 | 2025-08-15 | 2025-08-13 | 2025-09-01 | 2025-09-01 | 2025-09-01
| Vendor Name | ECO equipments Inc. | Start Fabrication | 2025-09-16 | 2025-09-20 | 2025-09-20 | End cap of floating oil skimmer | 1 | 2025-08-01 | 2025-08-15 | 2025-08-13 | 2025-09-01 | 2025-09-05 | 2025-09-05
| Delivery Date | 2025-11-30 | Cargo ready | 2025-11-30 | 2026-02-01 | 2026-02-10
| Delivery Term | FOB
| Delivery Location | Keelung, Taiwan
| Inspection Level | 3
| Vendor PIC | Jennifer Chou
| SCJV PE | Michelle Chen
| SCJV RE | Tawatchai Tarseekam
| SCJV Expeditor | Daniel Hsieh
| SCJV Buyer | Daniel Hsieh
| Main Issue |  | [General] |  |  |  | [Current Status and Issue] Material ready for shipment | [8 empty] | [Current Status and Issue] 11/25 progress inspection 12/3 Under weld repairing 1/15 Inspection completed, expedite SQR 1/22 SQR under SCJV review 2/10 IRC issued | [5 empty] | [Current Status and Issue] SQR under Company review | [9 empty] | [Current Status and Issue]
7 | M/R No. | FX2A.01 | KOM | 2025-07-01 | 2025-07-01 | 2025-07-01 | Compressors |  | 2025-07-31 | 2025-10-08 | 2025-08-06 | 2025-09-10 | 2025-10-30 | 2025-10-31 | DANFOSS FZCO | Final Inspection | 2026-05-01 |  |  |  |  | 40-PK-8300 | Safety Shower Chiller Package | 2025-10-03 | 2025-12-29 | 2025-10-30 |  |  | 2026-02-28 | 2026-06-20 |  | 2026-06-30 |  |  | 2026-07-20 |  | 2026-05-07 | updated ROS 2026-08-15
| M/R Name | Safety Shower Chiller Package | Key V/P | 2025-06-30 | 2025-06-30 | 2025-06-20 | Centrifugal Pumps |  | 2025-07-31 | 2025-10-08 | 2025-08-06 | 2025-08-30 | 2025-10-30 | 2025-11-02 | ALI MANEA AL YAMI EST.
| P/O No. | 5000107958 | Sub-order Issued | 2025-07-31 | 2025-10-08 | 2025-09-02 | CS Shell |  | 2025-07-31 | 2025-10-08 | 2025-08-10 | 2025-09-19 | 2025-10-30 | 2025-10-10 | Wieland Provides Srl
| Q'ty(Item/Set) | 1 | Receive Main material | 2025-09-12 | 2025-11-07 | 2025-11-13 | Copper Fins Condenser Coil |  | 2025-07-31 | 2025-10-08 | 2025-07-09 | 2025-10-10 | 2025-09-16 | 2025-09-16 | ZHEJIANG WINJOY NEW MATERIAL CO., LTD NINGBO JINTIAN COPPER TUBE CO., LTD.
| Vendor Name | Zamil Central Air Conditioners | Assembly | 2025-10-03 | 2025-12-29 | 2025-10-30 | Copper Fins Condenser Coil, Copper Tube |  | 2025-07-31 | 2025-10-08 | 2025-07-09 | 2025-10-10 | 2025-10-30 | 2025-10-31 | ZHEJIANG WINJOY NEW MATERIAL CO., LTD NINGBO JINTIAN COPPER TUBE CO., LTD.
| Delivery Date | 2026-02-28 | Inspection and Test | 2026-01-09 | 2026-05-19 |  | Stainless Steel Plate |  | 2025-07-31 | 2025-10-08 | 2025-08-13 | 2025-10-18 | 2025-10-30 | 2025-10-18 | AL HUWAIS TRADING COMPANY
| Delivery Term | FCA | Packing | 2026-02-13 | 2026-06-10 |  | Control Panel |  | 2025-07-31 | 2025-10-08 | 2025-06-29 | 2025-07-31 | 2025-07-31 | 2025-07-31 | MICRO CONTROL SYSTEMS, INC
| Delivery Location | Saudi Arabia | Cargo ready | 2026-02-28 | 2026-06-20
| Inspection Level | 2
| Vendor PIC | Samer Abdelnour
| SCJV PE | Rebecca Chen
| SCJV RE | Andy Zhang
| SCJV Expeditor | Andrew Zheng->Derek Chen
| SCJV Buyer | Andrew Zheng->Derek Chen
|  |  | [General] |  |  |  | [Current Status and Issue] sub-order pending for V/P approval | [8 empty] | [Current Status and Issue] | [5 empty] | [Current Status and Issue] | [9 empty] | [Current Status and Issue]
Formulas:
Delivery At site = [Shipping & Delivery]+60
Delivery At site = [Delivery At site, row above]
Forecast = [Forecast, row above]+7
Actual = [Actual, row above]+7
Note on G61: Andrew Zheng/Andreas Setiawan 鄭友安/CTCI-PROP: Forecast Submission Date: ITP for Air Dryer 2025/04/24 GA Drawing for Air Dryer 2025/04/29 Data sheet 2025/05/10

## Piping
[13 empty] | UNIT & PKG STATUS |  |  | INSPECTION STATUS | [6 empty] | SHIPMENT STATUS
Vendor (Actual) | Item Description | Contract Delivery Term | PO No. | PO Issued | PO Delivery Date | Req'n | BM Rev | Unit | Order Q'ty | Dispatch Q'ty | Balance Q'ty | Delivery Rate | Unit | AREA |  | Inspection Type | Inspection Date | IRC NO. | AREA |  | InspectionTotal Q'ty | Inspection Balance Q'ty | SHIP NO | PL NO. (*=Server Upload) | ETD | ETA (Local Port) | ATA (Site) | AREA |  | SHIPPED Q'TY
[14 empty] | SECL (4) | CTCI (8) |  |  |  | SECL (4) | CTCI (8) | [7 empty] | SECL (4) | CTCI (8)
Future Pipe Industries | FRP Piping (A/G) | DDP | 5000105243-2 | 2025-11-20 | 2026-02-15 | HA65AF_8_2 | 5 | pc | 873.2 | 873.2 | 0 | 100% | PC |  | 873.2 | INSPECTION LEVEL：3 | 2/23/2026 28-30/3/3026 | IRC-5000105243-0001 IRC-5000105243-0002 |  | 873.2 | 873.2 | 0 | SC7128C-P3-LT1183-CS |  | 2026-03-14 | 2026-03-14 | 2026-03-15 |  | 873.2 | 873.2 | 1/28 DN 350 & 600 mm pipe inspection on 28-Jan 2/12 1st lot spool inspection arranged on 21~23 Feb 2/28 vendor suspend activity due to geopolitical situation 3/12 4th change order under preparation 3/18 1st lot arrived at site 3/30 2nd lot finished inspection 4/8 2nd lot under shipping arrangement 4/14 All spools arrived at site
[21 empty] | 0 | [8 empty] | 0
|  |  | 5000105243-2 | 2025-11-20 | 2026-02-15 | HA65AP_8_3 | 1 | pc | 24 | 24 | 0 | 100% | PC |  | 24 | INSPECTION LEVEL：3 | 2/23/2026 28-30/3/3026 | IRC-5000105243-0001 IRC-5000105243-0002 |  | 24 | 24 | 0 | SC7128C-P3-LT1183-CS |  | 2026-03-14 | 2026-03-14 | 2026-03-15 |  | 24 | 24
[21 empty] | 0 | [8 empty] | 0
|  |  | 5000105243-2 | 2025-11-20 | 2026-02-15 | HA65AP_8_6 | 1 | pc | 77.6 | 77.6 | 0 | 100% | PC |  | 77.6 | INSPECTION LEVEL：3 | 28-30/3/3026 | IRC-5000105243-0003 |  | 77.6 | 77.6 | 0 | SC7128C-P3-LT200-CS |  | 2026-04-12 | 2026-04-12 | 2026-04-12 |  | 77.6 | 77.6
[21 empty] | 0 | [8 empty] | 0
|  |  | 5000105243-2 (PIPELINE) | 2025-11-20 | 2026-02-15 | HA65AP_8_2 | 2 | pc | 352.8 | 352.8 | 0 | 100% | PC |  | 352.8 | INSPECTION LEVEL：3 | 28-30/3/3026 | IRC-5000105243-0003 |  | 352.8 | 352.8 | 0 | SC7128C-P3-LT200-CS |  | 2026-04-12 | 2026-04-12 | 2026-04-12 |  | 352.8 | 352.8
[21 empty] | 0 | [8 empty] | 0
|  |  | 5000105243-3 | 2026-04-30 | 2026-06-30 |  |  | pc | 30 |  | 30 | 0% | PC |  | 30 | INSPECTION LEVEL：3 |  |  |  |  | 0 | 30 | [7 empty] | 0
[21 empty] | 0 | [8 empty] | 0
[9 empty] | 1327.6 | 897.2 | 0 | 67.58% | SUB TOTAL | 0 | 1327.6 | SUB TOTAL |  |  | 0 | 1327.6 | 1327.6 | 0 | SUB TOTAL |  |  |  |  | 0 | 1327.6 | 1327.6
[16 empty] | BALANCE |  |  | 0 | 0 |  |  | BALANCE |  |  |  |  | 0 | 0 | 0
CTA Asia Pasific Limited | Lined PTFE Piping (A/G) | FOB | 5000106211 | 2025-02-26 | 2025-07-30 | HA6400 | 0 | pc | 151 | 151 | 0 | 100% | PC |  | 151 | INSPECTION LEVEL：3 | 2025-06-25 | IRC-5000106211-001 |  | 151 | 151 | 0 | SC7128C-P3-EC045-CS |  | 2025-08-05 | 2025-10-04 | 2025-10-09 |  | 151 | 151 | 3/11 2nd CO items inspection 3/26 final lot under shipping arrangement
[21 empty] | 0 | [8 empty] | 0
|  |  | 5000106211-1 | 2025-07-10 | 2025-09-30 | HA6400 | 0 | pc | 5 | 5 | 0 | 100% | PC |  | 5 | INSPECTION LEVEL：3 |  | IRC-5000106211-002 |  | 5 | 5 | 0 | SC7128C-P3-EL071-CS |  | 2025-10-07 | 2025-11-12 | 2025-11-13 |  | 5 | 5
[21 empty] | 0 | [8 empty] | 0
|  |  | 5000106211-2 | 2025-12-15 | 2026-03-31 | HA6400 | 0 | pc | 29 | 29 | 0 | 100% | PC |  | 29 | INSPECTION LEVEL：3 | 2026-03-11 | IRC-5000106211-0003 |  | 29 | 29 | 0 | SC7128C-P3-EA192-CS |  | 2026-04-26 | 2026-04-26 | 2026-04-28 |  | 29 | 29
[21 empty] | 0 | [8 empty] | 0
[9 empty] | 185 | 156 | 0 | 84.32% | SUB TOTAL | 0 | 185 | SUB TOTAL |  |  | 0 | 185 | 185 | 0 | SUB TOTAL |  |  |  |  | 0 | 185 | 151
[16 empty] | BALANCE |  |  | 0 | 0 |  |  | BALANCE |  |  |  |  | 0 | 0 | 0
CTA Asia Pasific Limited | Groove Joint Fitting, Flange | FOB | 5000106254 | 2025-02-26 | 2025-07-30 | HB80AF | 0 | PC | 781 | 781 | 69 | 100% | PC | 781 |  | INSPECTION LEVEL：1 | 2025-06-20 2025-09-04 2025-11-28 | IRC-5000106254-001 IRC-5000106254-002 IRC-5000106254-003 | 781 |  | 781 | 0 | SC7128C-P3-EC044-SS SC7128C-P3-EL087-SS SC7128C-P3-EC114-SS |  | 2025-08-05 2025-12-07 2026-01-11 | 2025-10-04 2025-01-15 2026-02-19 | 2025-10-09 2025-01-25 2026-02-23 | 781 |  | 781 | 4/21 Materail arrived at site.
[21 empty] | 0 | [8 empty] | 0
|  |  | 5000106254-1 | 2025-06-16 | 2025-12-15 | HB80AF | 0 | PC | 559 | 559 | 559 | 100% | PC | 220 | 339 | INSPECTION LEVEL：1 | 2025-11-28 | IRC-5000106254-003 | 220 | 339 | 559 | - | SC7128C-P3-EC113-CS SC7128C-P3-EC114-SS |  | 2026-01-11 | 2026-02-19 | 2026-02-23 | 220 | 312 | 559
[21 empty] | 0 | [8 empty] | 0
|  |  | 5000106254-2 | 2025-09-02 | 2025-12-15 | HB80AF | 0 | PC | 88 | 88 | 88 | 100% | PC | 88 |  | INSPECTION LEVEL：1 | 2025-11-28 | IRC-5000106254-003 | 88 |  | 88 | - | SC7128C-P3-EC114-SS |  | 2026-01-11 | 2026-02-19 | 2026-02-23 | 88 |  | 88
[21 empty] | 0 | [8 empty] | 0
|  |  | 5000106254-3 | 2025-11-28 | 2026-04-01 | HB80AF | 0 | PC | 20 | 20 | 20 | 100% | PC | 19 | 1 | INSPECTION LEVEL：1 | 2026-03-17 | IRC-5000106254-0004 | 19 | 1 | 20 | - | SC7128C-P3-EA187-CS |  | 2026-04-18 | 2026-04-18 | 2026-04-21 | 19 | 1 | 20
[21 empty] | 0 | [8 empty] | 0
|  |  | 5000106254-4 | 2026-02-11 | 2026-04-01 | HB80AF | 0 | PC | 9 | 9 | 9 | 100% | PC | 9 |  | INSPECTION LEVEL：1 | 2026-03-17 | IRC-5000106254-0004 | 9 |  | 9 | - | SC7128C-P3-EA191-SS |  | 2026-04-18 | 2026-04-18 | 2026-04-21 | 9 |  | 9
[21 empty] | 0 | [8 empty] | 0
[9 empty] | 1457 | 1457 | 745 | 100% | SUB TOTAL | 1117 | 340 | SUB TOTAL |  |  | 1117 | 340 | 1340 | 0 | SUB TOTAL |  |  |  |  | 781 | 0 | 781
[16 empty] | BALANCE | [6 empty] | BALANCE |  |  |  |  | 336 | 340 | 676
KUMHWA INDUSTRY CO | Non-Metallic Expansion Joint | FOB | 5000107949 | 2025-06-17 | 2025-11-30 | HG9500 | 0 | PC | 8 | 8 | 0 | 100% | PC |  | 8 | INSPECTION LEVEL：1 | Rubber 2025-11-26 Sleeve: Waived | IRC-5000107949-0001 |  | 8 | 8 | 0 | SC7128C-P3-KC105-CS |  | 2026-01-05 | 2026-02-08 | 2026-02-09 |  | 8 | 8 | 2/12 Material arrived at site
[21 empty] | 0 | [8 empty] | 0
[9 empty] | 8 | 8 | 0 | 100% | SUB TOTAL | 0 | 8 | SUB TOTAL |  |  | 0 | 8 | 8 | 0 | SUB TOTAL |  |  |  |  | 0 | 8 | 8
[16 empty] | BALANCE |  |  | 0 | 0 |  |  | BALANCE |  |  |  |  | 0 | 0 | 0
Neway Valve Co. Ltd. | Ball Valve | FOB | 5000105691 5000105691-1 | 2025-06-05 | 2025-10-30 | HF4100 | 0 | PC | 5 | 5 | 0 | 100% | PC |  | 5 | INSPECTION LEVEL：3 | 2025-11-26 | IRC-5000105691-0001 |  | 5 | 5 | 0 | SC7128C-P3-CA156-CS |  | 2026-04-29 | 2026-06-09 | F 2026-06-18 |  |  | 0 | 1/29 final inspection arranged on 30-Jan 2/5 Material under packing process 2/12 Materail under shipping arrangement 3/3 check valve arrange ship from Korea to China on 3-Mar 3/12 Check valve arrived China port on 11-Mar 3/18 Prepare to arrange shipment once check valve arrived to Neway shop 3/25 All valves under shipping arrangement | ATD Korea 3/8 ATA China 3/11 | ROS: early of June 2026
[6 empty] | (check valve) | [14 empty] | 0 | [8 empty] | 0
|  |  | 5000105691-1 | 2025-08-11 | 2026-02-15 | HF4100 | 0 | PC | 5 | 5 | 5 | 100% | PC | 2 | 3 | INSPECTION LEVEL：3 | 2025-01-30 | IRC-5000105691-0002 | 2 | 3 |  | 5 | SC7128C-P3-CC142-CS & CC143-SS |  | 2026-04-29 | 2026-06-09 | F 2026-06-18 |  |  | 0 |  | booking cancelled | ROS: early of June 2026
[6 empty] | (Ball valve) | [14 empty] | 0 | [8 empty] | 0
[9 empty] | 10 | 10 | 5 | 100% | SUB TOTAL | 2 | 8 | SUB TOTAL |  |  | 2 | 8 | 5 | 0 | SUB TOTAL |  |  |  |  | 0 | 0 | 0
[16 empty] | BALANCE |  |  | 0 | 0 |  |  | BALANCE |  |  |  |  | 2 | 8 | 10
Flexitallic | Isolation Kit | FOB | 5000109214 | 2025-08-15 | 2025-11-15 | HG5000 | 0 | PC | 21 | 21 | 0 | 100% | PC |  | 21 | INSPECTION LEVEL：0 | N/A | IRC-5000109214-001 |  | 21 | 21 | 0 | SC7128C-P3-CL101-CS |  | 2026-02-07 | 2026-04-20 | 2026-04-22 |  | 21 | 21 | 1/8 SR issued 1/15 IRC released 1/22 Material under shipping arrangement 2/12 Material dispatched | ATD UAE port, to be delivered to Qatar, ETD to be updated
[21 empty] | 0 | [8 empty] | 0
[9 empty] | 21 | 21 | 0 | 100% | SUB TOTAL | 0 | 21 | SUB TOTAL |  |  | 0 | 21 | 21 | 0 | SUB TOTAL |  |  |  |  | 0 | 21 | 21
[16 empty] | BALANCE |  |  | 0 | 0 |  |  | BALANCE |  |  |  |  | 0 | 0 | 0
JUNG ANG ENGINEERING | Flexible Hose & Hose Connector (AG) | FOB | 5000108619 | 2025-07-22 | 2025-10-01 | HG4600 | 0 | PC | 2 | 2 | 2 | 100% | PC |  | 2 | INSPECTION LEVEL：0 | N/A | IRC-5000108619-0001 |  | 2 | 2 | 0 | SC7128C-P3-KC109-CS |  | 2026-02-08 | 2026-05-06 | 2026-05-12 |  | 2 | 2 | 11/27 material under manufacturing 12/3 Approximate complete manufacturing after 2 weeks. 12/10 Tentative SR received 12/24 SQR under review 1/15 IRC released 1/22 Material under shipping arrangement 2/12 Material dispatched | ATA Khor Fakkan 4/25
[21 empty] | 0 | [8 empty] | 0
|  |  | 5000108619-1 | 2025-09-24 | 2025-12-30 | HG4600 | 0 | PC | 3 | 3 | 3 | 100% | PC |  | 3 | INSPECTION LEVEL：0 | N/A | IRC-5000108619-0001 |  | 3 | 3 | 0 | SC7128C-P3-KC109-CS |  | 2026-02-08 | 2026-05-06 | 2026-05-12 |  | 3 | 3 |  | ATA Khor Fakkan 4/25
[21 empty] | 0 | [8 empty] | 0
[9 empty] | 5 | 2 | 5 | 40% | SUB TOTAL | 0 | 5 | SUB TOTAL |  |  | 0 | 5 | 2 | 0 | SUB TOTAL |  |  |  |  | 0 | 2 | 2
[16 empty] | BALANCE |  |  | 0 | 0 |  |  | BALANCE |  |  |  |  | 0 | 3 | 3
Armstrong | Trap | FOB | 5000109176 | 2025-08-13 | 2026-03-01 | HG7200 | 0 | PC | 3 | 3 | 0 | 100% | PC |  | 3 | INSPECTION LEVEL：3 | 2026-03-19 | IRC-5000109176-0001 |  | 3 | 3 | 0 | SC7128C-P3-KC170-CS |  | 2026-04-14 | 2026-06-15 |  |  | 3 | 3 | 11/19 Raw material under purchasing 11/27 sub-order (raw material) placed - follow up unpriced PO 12/10 Received un-priced PO 12/30 VIDI, pressure, function test arranged on 14-Jan 1/22 material under painting 1/29 Due to vendor don't have measurment tool for painting, the inspection may postpone 2/23 Final inspection arranged on 19-Mar 3/24 Expedite SQR
[21 empty] | 0 | [8 empty] | 0
[9 empty] | 3 | 3 | 0 | 100% | SUB TOTAL | 0 | 3 | SUB TOTAL |  |  | 0 | 3 | 3 | 0 | SUB TOTAL |  |  |  |  | 0 | 3 | 3
[16 empty] | BALANCE |  |  | 0 | 0 |  |  | BALANCE |  |  |  |  | 0 | 0 | 0
Note on W25: inspection: 63 done; 6 waiting for NOI
Note on W27: inspection: 63 done; 6 waiting for NOI

## Pipeline
[13 empty] | UNIT & PKG STATUS |  |  | INSPECTION STATUS | [6 empty] | SHIPMENT STATUS
Vendor (Actual) | Item Description | Contract Delivery Term | PO No. | PO Issued | PO Delivery Date | Req'n | BM Rev | Unit | Order Q'ty | Dispatch Q'ty | Balance Q'ty | Delivery Rate | Unit | AREA |  | Inspection Type | Inspection Date | IRC NO. | AREA |  | InspectionTotal Q'ty | Inspection Balance Q'ty | SHIP NO | PL NO. (*=Server Upload) | ETD | ETA (Local Port) | ATA (Site) | AREA |  | SHIPPED Q'TY
[14 empty] | SECL (4) | CTCI (8) |  |  |  | SECL (4) | CTCI (8) | [7 empty] | SECL (4) | CTCI (8)
CTA (Manufacturer: TPCO / HYST) | CS SMLS Pipe (Pipeline) | FOB | 5000106212 | 2025-02-26 | 2025-07-01 | HA1100 | 0 | m | 3921.5 | 3921.5 | 0 | 100% | M |  | 3921.5 | INSPECTION LEVEL：1 | 2025-07-23 | IRC-5000106212-001 |  | 3921.5 | 3921.5 | 0 | SC7128C-P3-CA041-V (Test piece) SC7128C-P3-CC060-CS |  | 2025-07-27 2025-08-30 | 2025-07-29 2025-10-15 | 2025-08-02 2025-10-20 |  | 3921.5 | 3921.5 | 4/16 Additional pipe completed manufacture 5/15 Additional pipe under shipping arrangement.
[21 empty] | 0 | [8 empty] | 0
|  |  | 5000106212-1 | 2025-06-06 | 2025-10-25 | HA1100 | 0 | m | 11.5 | 11.5 | 0 | 100% | M |  | 11.5 | INSPECTION LEVEL：1 | 2025-08-08 | IRC-5000106212-002 |  | 11.5 | 11.5 |  | SC7128C-P3-CC048-CS |  | 2025-09-18 | 2025-11-09 | 2025-11-12 |  | 11.5 | 11.5
|  |  | 5000106212-3 | 2026-03-27 | 2026-04-30 | HA1100 | 0 | m | 24 | 24 | 0 | 100% | M |  | 24 | INSPECTION LEVEL：1 | 2026-04-23 | IRC-5000106212-003 |  | 24 | 24 |  | SC7128C-P3-CC217-CS |  | 2026-05-23 | 2026-07-01 |  |  | 24 | 24 |  | space under booking
[9 empty] | 3957 | 3957 | 0 | 100% | SUB TOTAL | 0 | 3957 | SUB TOTAL |  |  | 0 | 3957 | 3957 | 0 | SUB TOTAL |  |  |  |  | 0 | 3921.5 | 3921.5
[16 empty] | BALANCE |  |  | 0 | 0 |  |  | BALANCE |  |  |  |  | 0 | 35.5 | 35.5
TK | Barred tee and Bend | FOB | 5000106249 | 2025-02-26 | 2025-12-30 | HG1600 (Barred tee) | 0 | PC | 2 | 0 | 2 | 0% | PC |  | 2 | INSPECTION LEVEL：1 | 2026-01-02 & 05 | IRC-5000106249-0001 |  |  | 0 | 2 | SC7128C-P3-KC104-CS |  | 2026-01-21 | 2026-02-23 | 2026-02-28 |  |  | 0 | 11/19 Bend mother pipe under manufacturing 12/3 Bend mother pipe under internal inspection 12/24 Barred tee final inspection arranged on 5-Jan 12/30 Mother pipe for bend delivered to TK shop 1/15 Bend under fabrication 3/5 following up with raw materials delivery for bend 4/1 Bend mother pipe arrived TK shop 4/20 revised schedule received - 4/22 Cutting - 5/4 Bending → 5/7 under bending (delayed) - 5/8 Heat treatment - 5/20 Hydrostatic test --> 5/26~29 - 5/25 Machining & NDE - 6/10 FBE coating - 6/15 Final inspection
[21 empty] | 0 | [8 empty] | 0
|  |  | 5000106249 | 2025-02-26 | 2026-05-20 | HG1800 (Bend) | 0 | PC | 20 | 0 | 20 | 0% | PC |  | 20 | INSPECTION LEVEL：1 | F: 2026-06-15 |  |  |  | 0 | 20 |  |  | F: 2026-06-30 |  |  |  |  | 0
[21 empty] | 0 | [8 empty] | 0
[9 empty] | 2 | 0 | 2 | 0% | SUB TOTAL | 0 | 2 | SUB TOTAL |  |  | 0 |  | 0 | 2 | SUB TOTAL |  |  |  |  | 0 | 0 | 0
[16 empty] | BALANCE |  |  | 0 | 2 |  |  | BALANCE |  |  |  |  | 0 | 2 | 2
IGP | Isolation joint | FOB | 5000106445 | 2025-03-12 | 2025-06-30 | HG4900 | 0 | PC | 4 | 2 | 2 | 50% | PC |  | 4 | INSPECTION LEVEL：1 | 2025-08-18 | IRC-5000106445-0001 (Isolation joint) |  | 2 | 2 | 0 | SC7128C-P3-AA072-CS |  | 2026-05-06 | 2026-05-11 | 2026-05-12 |  |  |  | 5/15 Material arrived at site
[16 empty] | INSPECTION LEVEL：1 | 2026-02-23 | IRC-5000106445-0002 (test ring) |  | 2 | 2 | 0 | SC7128C-P3-AA171-CS (test ring) |  | 2026-04-15 | 2026-04-15 | 2026-04-16 |  | 2 | 2
[9 empty] | 4 | 2 | 2 | 50% | SUB TOTAL | 0 | 4 | SUB TOTAL |  |  | 0 |  | 4 | 0 | SUB TOTAL |  |  |  |  | 0 | 2 | 2
[16 empty] | BALANCE |  |  | 0 | 4 |  |  | BALANCE |  |  |  |  | 0 | 2 | 2
Roc-Master Piping Solutions | Anchor flange | FOB | 5000106918 | 2025-03-12 | 2025-08-15 | HG6900 | 0 | PC | 6 | 6 | 0 | 100% | PC |  | 6 | INSPECTION LEVEL：1 | 2025-08-20 | IRC-5000106918-0001 |  | 6 | 6 | 0 | SC7128C-P3-CC065-CS |  | 2025-09-18 | 2025-10-26 | 2025-10-29 |  | 6 | 6 | 10/29 Material arrived at site
[21 empty] | 0 | [8 empty] | 0
|  |  | 5000106918-1 | 2025-08-11 | 2025-10-30 | HG6900 | 0 | PC | 1 | 1 | 0 | 100% | PC |  | 1 | INSPECTION LEVEL：1 | 2025-09-30 | IRC-5000106918-0002 |  | 1 | 1 | 0 | SC7128C-P3-CA082-CS |  | 2025-10-24 | 2025-10-25 | 2025-10-26 |  | 1 | 1
[21 empty] | 0 | [8 empty] | 0
[9 empty] | 7 | 6 | 0 | 85.71% | SUB TOTAL | 0 | 7 | SUB TOTAL |  |  | 0 | 7 | 7 | 0 | SUB TOTAL |  |  |  |  | 0 | 7 | 7
[16 empty] | BALANCE |  |  | 0 | 0 |  |  | BALANCE |  |  |  |  | 0 | 0 | 0
Valvitalia S.p.A. | Through Conduit Gate Valve (Pipeline) | FOB | 5000107304 | 2025-04-29 | 2026-03-31 | HF57AF | 0 | PC | 9 | 0 | 9 | 0% | PC |  | 9 | INSPECTION LEVEL：3 |  |  |  |  | 0 | 9 | [7 empty] | 0 | 6/24 Vendor submit revised DWG 7/10 DWG return to vendor with CODE B 7/17 vendor review the comment and will be updarte MPR 7/22 vendor submit revised DWG 8/4 inform vendor start to purchase valve material. 9/2 vendor placed order for cast and forged material 9/10 PIM will be opened on 18-SEP 10/8 Raw cast and forged material under manufacturing 11/19 Received cast and forged material photo 12/30 Raw main cast material under machining 1/22 All of the raw material proceed to machining process 2/12 Cast bodies will be completed by 15-19 Mar 3/4 Cast bodies postpone the complete date to May 5/14 Valve body will be dispatched from China mills on 15-May 5/20 Vlave body is on the transportation by rail | B/L to be provided
[21 empty] | 0 | [8 empty] | 0
[9 empty] | 9 | 0 | 9 | 0% | SUB TOTAL | 0 | 9 | SUB TOTAL |  |  | 0 |  | 0 | 9 | SUB TOTAL |  |  |  |  | 0 | 0 | 0
[16 empty] | BALANCE |  |  | 0 | 9 |  |  | BALANCE |  |  |  |  | 0 | 9 | 9
Valvitalia (Suzhou) Valves Co., Ltd | Ball Valve (Pipeline) | FOB | 5000107328 | 2025-04-29 | 2025-09-22 | HF56AF | 0 | PC | 1 | 1 | 0 | 100% | PC |  | 1 | INSPECTION LEVEL：3 | 2025-09-12 2025-09-25 | IRC-5000107328-0001 |  | 1 | 1 | 0 | SC7128C-P3-CA081-CS |  | 2025-10-05 | 2025-10-06 | 2025-10-06 |  | 1 | 1 | 2/26 Material arrived at site
[6 empty] | (RLOC, TA) | [14 empty] | 0 | [8 empty] | 0
|  |  | 5000107328 5000107328-1 5000107328-2 | 2025/4/29 2025/5/27 2025/5/27 | 2025-11-30 | HF56AF | 0 | PC | 25 | 25 |  | 100% | PC |  | 25 | INSPECTION LEVEL：3 | 2025-11-07~10 Hydro 2025-12-8 Painting | IRC-5000107328-0002 |  | 25 | 25 | 0 | SC7128C-P3-CC095-CS |  | 2026-01-19 | 2026-02-17 | 2026-02-23 |  | 25 | 25
[21 empty] | 0 | [8 empty] | 0
|  |  | 5000107328 5000107328-1 5000107328-2 | 2025/4/29 2025/5/27 2025/5/27 | 2025-11-30 | HF56AF | 0 | PC | 13 | 13 |  | 100% | PC |  | 13 | INSPECTION LEVEL：3 | 2025-11-07~10 Hydro 2025-12-8 Painting | IRC-5000107328-0002 |  | 13 | 13 | 0 | SC7128C-P3-CC095-CS |  | 2026-01-19 | 2026-02-17 | 2026-02-23 |  | 13 | 13
[21 empty] | 0 | [8 empty] | 0
|  |  | 5000107328 5000107328-1 5000107328-2 | 2025/4/29 2025/5/27 2025/5/27 | 2025-11-30 | HF56AF | 0 | PC | 8 | 8 |  | 100% | PC |  | 8 | INSPECTION LEVEL：3 | 2025-12-9 Hydro 2025-12-26 Painting | IRC-5000107328-0003 |  | 8 | 8 | 0 | SC7128C-P3-CC095-CS |  | 2026-01-19 | 2026-02-17 | 2026-02-23 |  | 8 | 8
[21 empty] | 0 | [8 empty] | 0
[9 empty] | 47 | 25 | 0 | 53.19% | SUB TOTAL | 0 | 47 | SUB TOTAL |  |  | 0 |  | 47 | 0 | SUB TOTAL |  |  |  |  | 0 | 1 | 1
[16 empty] | BALANCE |  |  | 0 | 47 |  |  | BALANCE |  |  |  |  | 0 | 46 | 46
Note on V7: dispatched together with 1st batch
Note on W7: remaining Q'ty to be confirmed by Eng. team
Note on V9: dispatched together with 1st batch
Note on W9: remaining Q'ty to be confirmed by Eng. team

## Electrical
ASSIGNED | ASSIGNED | No. | Material Requisition |  |  | Purchase Order | [8 empty] | Delivery Status |  |  |  |  | Key Milestone |  |  |  | Sub-Order Status | [7 empty] | Inspection | [10 empty] | Shipping & Delivery | [11 empty] | Contact Point |  |  | Main Issue |  | Histroy issue
|  |  | M/R No. | M/R Name | Inspection Level | P/O No. | Rev. | Vendor Name | Origin | Drum Schedule Issue Date | P/O Released | Delivery Date | Delivery Term | Delivery Location | Ordered Q'ty. | Unit | Shipped Q'ty. | Un-Shipped Q'ty. | Delivery Rate | Key Milestone | Plan | Forecast | Actual | Sub-Order Item | Q'ty | Sub-Order Issued |  | Sub-Order Received |  |  | Sub-Vendor | Inspection Activity | I/A No. | Inspection Schedule | [5 empty] | IRC |  |  | Batch No. | Shipment Description | Shipping |  | Material shipped |  | Delivery at Qatar Port |  | Delivery at Site |  | SHIPPING NO. | SHIPPING NO. |  |  |  | Current Status/Remarks | Pending Issue & Countermeasure
Expeditor | ENGINEER | [24 empty] | Forecast | Actual | Forecast | Actual | Q'ty |  |  |  | Schedule | Forecast | Actual | Actual | Punch | Packing | IRC No. | Q'ty | Unit |  |  | Q'ty | Unit | ETD | ATD | ETA | ATA | ETA | ATA | SECL | CTCI | Name | Tel. | email
Shin hye(Cynthia), Lee | Pham Nhu Luan | 1 | ND1020 | Outdoor Lighting Fixture and Others | 1 | 5000105899 | 0 | Warom International Korea | China | N/A | 2025-01-09 | HMP-1: 2025/3/30 HMP-2(anchor bolt): 2025/8/15 HMP-2(anchor bolt): 2025/9/30 Others: 2026/4/30 | FOB | Site | 1584 | sets | 1168 | 416 | 73.7374 | KOM | 2025-02-20 | 2025-02-20 | 2025-02-20 | Steel pipe | 1 | 2025-10-01 | 2025-01-13 | 2025-06-02 | 2025-05-02 | 1 |  | Final inspection for hogh mast pole (10 sets) | N-5000105899-001 | 2025-03-24 | 2025-03-24 | 2025-03-24 | 2025-03-24 | N/A |  | IRC-5000105899-0001 | 20 | sets | 1 | High Mast Pole | 10 | set | 2025-04-18 | 2025-04-18 | 2025-05-29 | 2025-05-29 | 2025-06-03 | 2025-06-01 | SC7128C-P4-CC003-SS | SC7128C-P4-CC001-CS | Wonil Lee (John) / 이원일 차장 | +82-70-4110-7318 | wiksales1@waromkorea.co.kr | 1))4th MOT: space confirmed ATD 5/19 ETA 6/27
[17 empty] | 0 | 0 |  | VPIS Submit | 2025-02-24 | 2025-02-24 | 2025-02-24 | Aluminum ingot | 1 | 2025-10-01 | 2025-01-13 | 2025-06-02 | 2025-05-02 | 1 |  |  | N-5000105899-002 | 2025-03-25 | 2025-03-25 | 2025-03-25 | 2025-03-25 | N/A |  | IRC-5000105899-0002 | [6 empty] | 2025-04-13 | 2025-04-15 | 2025-05-11 | 2025-05-14 | 2025-05-20 | 2025-05-20 | SC7128C-P4-CC004-SS | SC7128C-P4-CC002-CS | Ariya |  | wikmm1@waromkorea.co.kr
[17 empty] | 0 | 0 |  | Key V/P Submit | 2025-02-24 | 2025-02-24 | 2025-02-24 | LED clip for BAT86-240-240G | 123 | 2025-10-01 | 2025-01-13 | 2025-05-03 | 2025-05-03 |  | - | Final inspection for hogh mast pole (4 sets)-Anchor bolt | N-5000105899-005 | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-07-24 | N/A |  | IRC-5000105899-0003 | 1 | Lot | 2 | High Mast Pole (anchor bolts) | 4 | est | 2025-08-17 | 2025-08-18 | 2025-09-19 | 2025-09-18 | 2025-09-20 | 2025-09-20 | SC7128C-P4-CC035-SS | SC7128C-P4-CC034-CS |  |  | exus5@exus.asia
[17 empty] | 0 | 0 |  | Sub-order Issued | 2025-01-10 | 2025-01-10 | 2025-01-13 | [7 empty] | - | Final inspection for hogh mast pole (4 sets)-main pole | N-5000105899-007 N-5000105899-008 | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | N/A |  | IRC-5000105899-0004 IRC-5000105899-0005 | 8 | sets | 3 | High Mast Pole (main poles) | 4 | est | 2025-09-21 | 2025-09-24 | 2025-10-25 | 2025-10-27 | 2025-10-30 | 2025-10-30 | SC7128C-P4-CC068-SS | SC7128C-P4-CC067-CS
[17 empty] | 0 | 0 |  | Receive Main material | 2025-02-06 | 2025-02-05 | 2025-02-05 | [7 empty] | - | Final inspection for SOC 100%+ TOC 50% | N-5000105899-009 N-5000105899-010 | 2025-11-20 2025-11-21 | 2025-11-20 2025-11-21 | 2025-11-20 2025-11-21 | 2025-11-20 2025-11-21 | N/A |  | IRC-5000105899-0006 IRC-5000105899-0007 | 1140 | EA | 4 | SOC 100%+ TOC 50%-1st batch | 921 | EA | 2025-12-13 | 2025-12-14 | 2026-01-14 | 2026-01-13 | 2026-01-21 | 2026-01-18 | SC7128C-P4-CC094-SS | SC7128C-P4-CC093-CS
[17 empty] | 0 | 0 |  | Start Fabrication | 2025-01-10 | 2025-01-10 | 2025-01-10 | [8 empty] | Final inspection for 10M lighting pole anchor bolt | N-5000105899-011 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | N/A |  | IRC-5000105899-0008 | 1 | Lot | 5 | SOC 100%+ TOC 50%-2nd batch | 216 | EA | 2025-12-21 | 2025-12-20 | 2026-01-20 | 2026-01-21 | 2026-01-27 | 2026-01-22 | - | SC7128C-P4-CC112-CS
[20 empty] | Cargo ready (1st)_HMP 10 sets | 2025-03-31 | 2025-04-11 | 2025-04-15 | [8 empty] | Final inspection for SOC additional + TOC 100% | N-5000105899-017&18 | 2026-04-08 2026-04-09 | 2026-04-08 2026-04-09 | 2026-04-08 2026-04-09 | 2026-04-08 2026-04-09 | N/A |  | IRC-5000105899-0009 | 416 | EA | 6 | 10M pole anchor bolt | 28 | EA | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-31 | 2026-04-01 | - | SC7128C-P4-CA145-CS
[20 empty] | Cargo ready (2nd)_HMP 4 sets (anchor bolt) | 2025-08-15 | 2025-08-17 | 2025-08-18 | [19 empty] | 7 | SOC additional + TOC 100% | 416 | EA | 2026-05-17 | 2026-05-19 | 2026-06-27 |  | 2026-07-04 |  | SC7128C-P4-CC216-SS | SC7128C-P4-CC210-CS
[20 empty] | Cargo ready (3rd)_HMP 4 sets (main pole) | 2025-09-30 | 2025-09-21 | 2025-09-24
[20 empty] | Cargo ready (4th)_SOC 100%+ TOC 50% | 2025-11-25 | 2025-12-08 | 2025-12-14
[20 empty] | Cargo ready (5th)_10M pole anchor bolt | 2026-02-28 | 2026-03-30 | 2026-03-30
[20 empty] | Cargo ready (5th)_SOC additional+ TOC 100% | 2026-04-10 | 2026-05-17 | 2026-05-19
Emma Zhan | Williams | 2 | NG1010 | Cathodic Protection Systems (Pipeline) | 1 | 5000105454 | 1 | MEECC (Middle East Engineering & Corrosion Control W.L.L) |  | N/A |  | 2025-06-17 | DDP | Site | [5 empty] | KOM | 2025-02-18 | 2025-02-18 | 2025-02-18 | [8 empty] | Final inspection for Buried materials, Anodes & Cables | N-5000105454-001 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | N/A |  | IRC-5000105454-0001 | 1 | Lot | 1 | Buried materials, Anodes & Cables | 1 | Lot | 2025-09-28 | 2025-09-28 | 2025-09-28 | 2025-09-28 | 2025-09-28 | 2025-09-28 | - | SC7128C-P4-LT083-CS |  |  |  | 2nd PO-Temperary CP: Arrived at site on 3/11
[12 empty] | 2025-07-30 |  |  |  |  | 0 | 0 |  | VPIS Submit | 2025-02-19 | 2025-02-19 | 2025-02-19 | [8 empty] | Final inspection for TR | N-5000105454-002 | 2025-09-05 2025-09-06 | 2025-09-05 2025-09-06 | 2025-09-05 2025-09-06 | 2025-09-05 2025-09-06 | N/A |  | IRC-5000105454-0002 | 1 | Lot | 2 | TR | 1 | Lot | 2025-10-20 | 2025-10-20 | 2025-10-20 | 2025-10-20 | 2025-10-20 | 2025-10-20 | - | SC7128C-P4-LT084-CS
[12 empty] | 2026-02-20 |  |  |  |  | 0 | 0 |  | Key V/P Submit | 2025-03-01 | 2025-04-27 | 2025-03-29 | [8 empty] | Final inspection for J/B | N-5000105454-003 | 2025-09-15 | 2025-09-15 | 2025-09-15 | 2025-09-15 | N/A |  | IRC-5000105454-0003 | 1 | Lot | 3 | J/B | 1 | Lot | 2025-10-20 | 2025-10-20 | 2025-10-20 | 2025-10-20 | 2025-10-20 | 2025-10-20
[17 empty] | 0 | 0 |  | Sub-order Issued | 2025-03-24 | 2025-05-20 | 2025-05-20 | [8 empty] | Final inspection for 2nd PO | N-5000105454-004 | 2026-02-17 | 2026-02-16 | 2026-02-16 | 2026-02-16 | N/A |  | IRC-5000105454-0004 | 1 | Lot | 4 | Temperary CP | 1 | Lot | 2026-03-13 | 2026-03-11 | 2026-03-13 | 2026-03-11 | 2026-03-13 | 2026-03-11 | - | SC7128C-P4-LT178-CS
[17 empty] | 0 | 0 |  | Receive Main material | 2025-03-31 | 2025-05-28 | 2025-05-28 | [7 empty] | -
[17 empty] | 0 | 0 |  | Start Fabrication | 2025-03-31 | 2025-05-29 | 2025-05-29
[20 empty] | Cargo ready (1st)-buried CP materials | 2025-06-17 | 2025-09-30 | 2025-09-28
[20 empty] | Cargo ready (2nd)-TR & JB | 2025-07-30 | 2025-10-30 | 2025-10-20
[20 empty] | Cargo ready-2nd PO | 2026-02-20 | 2026-03-13 | 2026-03-11
Emma Zhan | Pham Nhu Luan | 3 | NB2010 | Cable Tray & Accessory | 1 | 5000107367 | 3 | Suzhou Ontop Mechanical & Electrical Equipment Co., Ltd | China | N/A | 2025-03-10 | 2025-06-15 | FOB | Site | 930 | Meter | 930 | 0 | 100 | KOM | N/A | N/A | N/A | [8 empty] | Inspection for 1st batch (tie-in) | N-5000107367-001 | 2025-06-12 | 2025-06-12 | 2025-06-12 | 2025-06-12 | N/A | N/A | IRC-5000107367-0001 | 930 | meters | 1 | 1st shipment for utility | 930 | Meters | 2025-07-06 | 2025-07-06 | 2025-07-25 | 2025-07-25 | 2025-07-27 | 2025-07-27 | - | SC7128C-P4-CC013-CS |  |  |  | 4th PO: Process-ATD 2/18 ; ATA 5/12 ETD Sharjah, UAE 5/21, ETA Hamad 5/23, MSC FLOSTA III Utility-ATD 4/29 / ETA 6/9
[12 empty] | 2025-08-12 |  | Site | 5778 | Meter | 5778 | 0 | 100 | VPIS Submit | 2025-05-12 | 2025-05-12 | 2025-05-12 | [8 empty] | Inspection for 2nd batch (for process 1st batch) | N-5000107367-002 | 2025-08-14 | 2025-08-14 | 2025-08-14 | 2025-08-14 | N/A | N/A | IRC-5000107367-0002 | 5778 | meters | 2 | 1st shipment for Process | 5778 | Meters | 2025-09-10 | 2025-09-10 | 2025-10-04 | 2025-10-02 | 2025-10-05 | 2025-10-05 | SC7128C-P4-CC061-SS | -
[12 empty] | 2025-12-01 |  | Site | 1199 | Meter | 1199 | 0 | 100 | Key V/P Submit | 2025-05-12 | 2025-05-12 | 2025-05-12 | [8 empty] | Inspection for 3rd batch | N-5000107367-003 | 2025-11-26 | 2025-11-26 | 2025-11-26 | 2025-11-26 | N/A | N/A | IRC-5000107367-0003 | 1199 | meters | 3 | 2nd shipment for Process & utility | 1199 | Meters | 2025-12-08 | 2025-12-08 | 2026-01-09 | 2026-01-08 | 2026-01-16 | 2026-01-11 | SC7128C-P4-CC100-SS | SC7128C-P4-CC099-CS
[12 empty] | 2026/3/10 |  | Site | 2940 | Meter | 0 | 2940 | 0 | Sub-order Issued | 2025-04-15 | 2025-04-21 | 2025-04-21 | [8 empty] | Inspection for 4thatch | N-5000107367-004 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | N/A | N/A | IRC-5000107367-0004 | 2940 | Meters | 4 | 3rd shipment for Process | 2940 | Meters | 2026-02-15 | 2026-02-18 | 2026-05-07 | 2026-05-12 | 2026-05-30 |  | SC7128C-P4-CC133-SS | -
[17 empty] | 0 | 0 |  | Receive Main material | 2025-04-25 | 2025-04-25 | 2025-04-25 | [7 empty] | - | [11 empty] | 5 | 3rd shipment for Utility | ETD: 2026-04-25; ATD: 2026-04-29; ETA: 2026-06-09; ETA: 2026-06-15; SECL: -; CTCI: SC7128C-P4-CC132-CS
[17 empty] | 0 | 0 |  | Start Fabrication | 2025-04-25 | 2025-04-25 | 2025-04-25
[20 empty] | Cargo ready (1st) | 2025-06-15 | 2025-06-15 | 2025-06-15
[20 empty] | Cargo ready (2nd) | 2025-08-12 | 2025-09-10 | 2025-09-10
[20 empty] | Cargo ready (3rd) | 2025-12-01 | 2025-12-09 | 2025-12-08
[20 empty] | Cargo ready (4th) | 2026-03-10 | 2026-02-15 | 2026-02-18
Emma Zhan | Pham Nhu Luan | 4 | NB2000 | POWER & CONTROL CABLE | 1 | 5000108773 | 5 | Doha Cables (Qatar) W.L.L | Qatar | N/A | 2025-07-03 2025-09-22 2025-11-28 2025-12/15 | 2026-01-01 | DDP | Site | 32880 | Meter | 32880 |  | 100 | KOM | N/A | N/A | N/A | [8 empty] | Inspection for 33kV KM power cable | N-5000108773-001 | 2025-12-08 2025-12-15 | 2025-12-08 2025-12-15 | 2025-12-08 2025-12-15 | 2025-12-08 2025-12-15 | N/A | N/A | IRC-5000108773-001 | 32880 | meters | 1 | 1st PO 33kV KM power cable | 32880 | Meters | 2026/1/1 2026/1/6-7 | 2026-01-01 | 2026/1/1 2026/1/6-7 | 2026-01-01 | 2026/1/1 2026/1/6-7 | 2026-01-08 | - | SC7128C-P4-LT122-CS |  |  |  | 1)6th PO: NOI issued, FAT on 7/28-29 Forecast delivery date: 8/8
[12 empty] | 2026-03-15 |  | Site | 20757 | Meter | 20757 |  | 100 | VPIS Submit | 2025-07-14 | 2025-07-14 | 2025-07-14 | [8 empty] | Inspection for 2nd PO | N-5000108773-002 N-5000108773-003 | 2026-01-11 2026-02-15 | 2026-01-11 2026-02-15 | 2026-01-11 2026-02-15 | 2026-01-11 2026-02-15 | N/A | N/A | IRC-5000108773-0002 IRC-5000108773-0003 | 6,702 14,200 | meters | 2 | 2nd PO-1st batch | 6702 | Meters | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2026-01-28 | SC7128C-P4-LT141-SS | SC7128C-P4-LT140-CS
[12 empty] | 2026/3/31 |  | Site | 107101 | Meter | 107101 |  | 100 | Key V/P Submit | 2025-07-25 | 2025-07-25 | 2025-07-31 | [8 empty] | Inspection for 3rd & 4th PO-1st batch | N-5000108773-004 | 2026-03-09 2026-03-10 | 2026-03-09 2026-03-10 | 2026-03-09 2026-03-10 | 2026-03-09 2026-03-10 | N/A | N/A | IRC-5000108773-0006 | 9830 | meters | 3 | 2nd PO-2nd batch | 14200 | Meters | 2026-03-13 | 2026-03-09 | 2026-03-13 | 2026-03-09 | 2026-03-13 | 2026-03-09 | SC7128C-P4-LT173-SS | SC7128C-P4-LT172-CS
[12 empty] | 2026/4/30 |  | Site | 15500 | Meter | 15500 |  | 100 | Sub-order Issued | 2025-07-30 | 2025-07-06 | 2025-07-06 | [8 empty] | Inspection for 3rd & 4th PO-2nd batch | N-5000108773-005 | 2026-03-29 2026-03-30 | 2026-03-29 2026-03-30 | 2026-03-29 2026-03-30 | 2026-03-29 2026-03-30 | N/A | N/A | IRC-5000108773-0007 | 113740 | meters | 4 | 5th PO-1st batch(earthing cable) | 3541 | Meters | 2026-03-13 | 2026-03-09 | 2026-03-13 | 2026-03-09 | 2026-03-13 | 2026-03-09 | - | SC7128C-P4-LT174-CS
[12 empty] | 2026-03-31 |  | Site | 4519 | Meter | 4519 | 0 | 100 | Receive Main material | 2025-07-30 | 2025-07-30 | 2025-07-30 | [7 empty] | - | Inspection for 5th PO (earthing cable) | N-5000108773-006 | 2026-02-22 2026-03-02 | 2026-02-22 2026-03-02 | 2026-02-22 2026-03-02 | 2026-02-22 2026-03-02 | N/A | N/A | IRC-5000108773-0004 IRC-5000108773-0005 | 3,541 1,000 | meters | 5 | 5th PO-2nd batch(bonding cable) | 1000 | Meters | 2026-03-23 | 2026-03-12 | 2026-03-23 | 2026-03-12 | 2026-03-23 | 2026-03-12 | - | SC7128C-P4-LT180-CS
[12 empty] | 2026-08-08 |  | Site | 44970 | Meter | 0 | 44970 | 0 | Start Fabrication | 2025-08-10 | 2025-11-10 | 2025-11-10 | [8 empty] | Inspection for 6th PO | N-5000108773-006 | 2026-07-28 2026-07-29 | 2026-07-28 2026-07-29 | [7 empty] | 6 | 3rd PO-1st batch | 9907 | Meters | 2026-03-31 | 2026-03-29 | 2026-03-31 | 2026-03-29 | 2026-03-31 | 2026-03-29 | SC7128C-P4-LT190-SS | SC7128C-P4-LT189-CS
[20 empty] | Cargo ready-1st PO (33kV KM cable) | 2025-11-30 | 2026-01-03 | 2026-01-08 | [19 empty] | 7 | 3rd PO-2nd batch + 4th PO | 113740 | Meters | 2026-04-18 | 2026-04-18 | 2026-04-18 | 2026-04-18 | 2026-04-18 | 2026-04-18 | SC7128C-P4-LT204-SS SC7128C-P4-LT214-SS | SC7128C-P4-LT203-CS
[20 empty] | Cargo ready-2nd PO | 2026-01-01 | 2026-01-31 | 2026-01-28 | [19 empty] | 8 | 6th PO | Q'ty: 44970; Unit: Meters; ETD: F 2026-08-08
[20 empty] | Cargo ready-3rd -1st batch | 2026-03-31 | 2026-03-31 | 2026-03-29
[20 empty] | Cargo ready-3rd -2nd batch & 4th PO | 2026-04-30 | 2026-04-15 | 2026-04-18
[20 empty] | Cargo ready-5th PO (earthing cable) | 2026-03-31 | 2026-03-10 | 2026-03-09
[20 empty] | Cargo ready-6th PO | 2026-08-08 | 2026-08-08
Emma Zhan | Pham Nhu Luan | 5 | NB4010 ND2010 | Cable Termination Kits Power Material (Welding Socket, LCS & JB) | 3 | 5000108967 | 2 | R. Stahl Pte Ltd. | India | N/A | 2025-07-24 | 2025-12-31 | FOB | Site | 157 | EA | 0 | 157 | 0 | KOM | N/A | N/A | N/A | [8 empty] | Inspection for cable termination kit(1st+2nd PO) | N-5000108967-01 | 2026-03-03 | 2026-03-03 | 2026-03-03 | 2026-03-03 | N/A | N/A | IRC-5000108967-001 | 176 | EA | 1 | 1st shipment for cable termination kit | 176 | EA | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-05-05 | 2026-04-29 | SC7128C-P4-AA186-SS | Included in SC7128C-P4-AA186-SS |  |  |  | 1)Power mateiral: Forecast delivery date is 2026/5/31 Forecast FAT by 5/22, NOI issued Cargo ready by 5/31 3)2nd batch Termination kit, forecasr cargo ready by 7/15
[12 empty] | 2026-01-30 |  |  | 232 | EA | 0 | 232 | 0 | VPIS Submit | 2025-08-15 | 2025-09-04 | 2025-09-04 | [8 empty] | Inspection for power material(1st+2nd PO) | N-5000108967-02 | 2026-05-22 | [8 empty] | 2 | 1st + 2nd shipment for power material | ETD: F 2026-05-31
[17 empty] | 0 | 0 |  | Key V/P Submit | 2025-09-09 | 2025-10-15 | 2025-10-10 | [19 empty] | 3 | 2nd shipment for cable termination kit | ETD: F 2026-07-17
[17 empty] | 0 | 0 |  | Sub-order Issued | 2025-10-30 | 2025-11-15 | 2025-10-28 | [19 empty] | 4
[17 empty] | 0 | 0 |  | Receive Main material | 2025-11-10 | 2025-11-20 | 2025-10-28
[17 empty] | 0 | 0 |  | Start Fabrication-Termination Kits | 2025-11-20 | 2025-11-30 | 2025-10-28
[20 empty] | Start Fabrication-Power material | 2025-11-20 | 2026-03-09 | 2026-03-06
[20 empty] | Cargo ready-Power material (1st+2nd+3rd PO) | 2025-12-31 | 2026-05-31
[20 empty] | Cargo ready-Termination Kits (1st+2nd PO) | 2026-01-30 | 2026-03-31 | 2026-03-31
[20 empty] | Cargo ready-Termination Kitsl (3rd PO) | 2026-01-30 | 2026-07-17
Emma Zhan | Nasus Huang | 6 | K87A.01 | 400V HVAC PDBS | 1 | 5000109026 | 0 | Wholesale Electric Asia Korea LLC. | Korea | N/A | 2025-07-10 | 2025-12-31 | FOB | Site | 1 | EA | 0 | 1 | 0 | KOM | 2025-08-21 | 2025-08-21 | 2025-08-21 | [8 empty] | Final inspection | N-5000109026-001 | 2026-02-10 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-03-02 | N/A | IRC-50000109026-0001 | 1 | EA | 1 | Shipment | 1 | EA | 2026-04-14 | 2026-04-14 | 2026-06-27 |  | 2026-07-04 |  | - | SC7128C-P4-KC182-CS |  |  |  | 1) IRC issued ATD 4/14 ETA 6/27 2)VDB: Expediting vendor submit for as-build
[17 empty] | 0 |  |  | VPIS Submit | 2025-08-25 | 2025-08-25 | 2025-08-27
[17 empty] | 0 | 0 |  | Key V/P Submit | 2025-09-12 | 2025-09-12 | 2025-09-10
[17 empty] | 0 | 0 |  | Sub-order Issued | 2025-10-13 | 2025-12-20 | 2025-12-24
[17 empty] | 0 | 0 |  | Receive Main material | 2025-10-30 | 2026-01-10 | 2026-01-01
[17 empty] | 0 | 0 |  | Start Fabrication | 2025-11-01 | 2026-01-15 | 2026-01-01
[20 empty] | Cargo ready | 2025-12-31 | 2026-04-17 | 2026-04-14
Emma Zhan | Pham Nhu Luan | 7 | NB1060 | Fiber Optical Cable for QSTEC Substation E-1000 | 1 | 5000109274 | 0 | Doha Cables (Qatar) W.L.L | Qatar | N/A | 2025-07-31 | 2025-12-15 | DDP | Site | 4000 | meter | 0 | 4000 | 0 | KOM | N/A | N/A | N/A | [8 empty] | Final inspection | N-5000109274-001 | 2025-12-30 2025-12-31 | 2025-12-30 2025-12-31 | 2025-12-30 2025-12-31 | 2025-12-30 2025-12-31 | N/A | N/A | IRC-5000109274-0001 | 4000 | meters | 1 | Shipment | Q'ty: 4000; Unit: Meters; ETD: 2026-01-20; ATD: 2026-01-20; ETA: 2026-01-20; ATA: 2026-01-27; CTCI: SC7128C-P4-LT128-CS | Delivered on 1/20
[17 empty] | 0 |  |  | VPIS Submit | 2025-09-21 | 2025-09-21 | 2025-09-11
[17 empty] | 0 | 0 |  | Key V/P Submit | 2025-09-21 | 2025-09-21 | 2025-09-11
[17 empty] | 0 | 0 |  | Sub-order Issued | 2025-10-15 | 2025-11-25 | 2025-11-20
[17 empty] | 0 | 0 |  | Receive Main material | 2025-10-20 | 2025-11-30 | 2025-11-30
[17 empty] | 0 | 0 |  | Start Fabrication | 2025-10-22 | 2025-11-30 | 2025-11-30
[20 empty] | Cargo ready | 2025-12-15 | 2026-01-31 | 2026-01-28
Shin hye(Cynthia), Lee | Pham Nhu Luan | 8 | NB1060 | RTD, TELECOM, AND COMMUNICATION CABLE | 1 | 5000109306 | 2 | GAON CABLE Co., Ltd. | Korea | N/A | 2025-07-31 2025-11-18 | 2026-01-30 | FOB | Site | 3144 | meter | 0 | 3144 | 0 | KOM | N/A | N/A | N/A | [8 empty] | Inspection for 1st & 2nd PO | N-5000109306-001 | 2026-01-22 | 2026-01-22 | 2026-01-22 | 2026-01-22 | N/A | N/A | IRC-5000109306-0001 | 12849 | meters | 1 | 1st+2nd PO | 12849 | meters | 2026-02-07 | 2026-02-08 | 2026-05-15 | 2026-04-25 | 2026-05-31 |  | SC7128C-P4-KC127-SS | SC7128C-P4-KC126-CS |  |  |  | ATD 2/8 ; ATA Port 5/1 Carrier plan to discarge cargo to Khor Fakkan, UAE 3rd PO: comparing the price between Gaon and Doha cable
[14 empty] | Site | 9705 | meter | 0 | 9705 | 0 | VPIS Submit | 2025-08-31 | 2025-08-31 | 2025-09-02
[17 empty] | 0 | 0 |  | Key V/P Submit | 2025-08-31 | 2025-08-31 | 2025-09-02
[17 empty] | 0 | 0 |  | Sub-order Issued | 2025-11-15 | 2025-11-30 | 2025-11-30
[17 empty] | 0 | 0 |  | Receive Main material | 2025-11-15 | 2025-11-30 | 2025-11-30
[17 empty] | 0 | 0 |  | Start Fabrication | 2025-11-20 | 2025-11-30 | 2025-11-30
[20 empty] | Cargo ready | 2026-01-15 | 2026-02-07 | 2026-02-08
Emma Zhan | Pham Nhu Luan | 9 | NB3010 | CABLE GLAND | 1 | 5000108966 | 4 | CMP Products Ltd. | UK | N/A | 2025-07-24 | 2026-01-01 | FOB | Site | 483 | EA | 483 | 0 | 1 | KOM | N/A | N/A | N/A | [8 empty] | Inspection for 1st & 2nd PO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | IRC-5000108966-0001 | 483 | EA | 1 | 1st+2nd PO | 483 | EA | 2026-01-24 | 2026-01-24 | 2026-03-28 | 2026-03-19 | 2026-04-30 | 2026-04-22 | Included in SC7128C-P4-EL123-CS | SC7128C-P4-EL123-CS |  |  |  | 3rd PO: cargo is ready, space confirmed ATD 4/12 ETA 6/30 4th PO: forecast delivery date 6/5 5th PO :forecast delivery date 7/31
[12 empty] | 2026-03-05 |  | Site | 1272 | EA | 1272 | 0 | 1 | VPIS Submit | 2025-10-01 | 2025-11-21 | 2025-10-13 | [8 empty] | Inspection for 3rd PO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | IRC-5000108966-0002 | 4572 | EA | 2 | 3rd PO | 4572 | EA | 2026-04-12 | 2026-04-12 | 2026-06-30 |  | 2026-07-20 |  | SC7128C-P4-EC176-SS | SC7128C-P4-EC175-CS
[12 empty] | 2026-06-10 |  | Site | 425 | EA | 0 | 425 |  | Key V/P Submit | 2025-10-15 | 2025-11-21 | 2025-10-13 | [8 empty] | Inspection for 4th PO | N/A | N/A | N/A | N/A | N/A | N/A | N/A
[12 empty] | 2026-07-31 |  | Site | 338 | EA | 0 | 338 | 0 | Sub-order Issued | 2025-11-15 | 2025-11-30 | 2025-11-30
[17 empty] | 0 | 0 |  | Receive Main material | 2025-11-15 | 2025-11-30 | 2025-11-30
[17 empty] | 0 | 0 |  | Start Fabrication | 2025-11-15 | 2025-11-30 | 2025-11-30
[20 empty] | Cargo ready-1st batch | 2026-01-01 | 2026-01-15 | 2026-01-24
[20 empty] | Cargo ready-2nd batch | 2026-03-05 | 2026-03-31 | 2026-03-31
[20 empty] | Cargo ready-3rd batch | 2026-06-10 | 2026-06-05
[20 empty] | Cargo ready-4th batch | 2026-07-31 | 2026-07-31
Emma Zhan | Esa | 10 | NAZO-C | OEM Services for the QSTEC Substation E-1000 | 1 | 5000110284 | 1 | Siemens Energy W.L.L | India | N/A | 2025-10-14 | 2026-09-15 | DDP | Site | 8 | EA | 0 | 8 | 0 | KOM | 2025-11-03 | 2025-11-03 | 2025-11-03 | Telecom | 1 | 2025-11-01 | 2025-10-16 | 2026-07-02 |  |  |  | SCS Panel FAT at QATAR |  | F 2026-07-06 | [23 empty] | Tariff metering panel delivery will be delayed by three weeks due to current transportation issues
[20 empty] | VPIS Submit | 2026-11-04 | 2026-11-04 | 2026-11-04 | Tariff Meter Panel | 1 | 2026-01-31 | 2026-02-02 | 2026-06-16 |  |  |  | OTB FAT at QATAR |  | F 2026-06-14
[20 empty] | Key V/P Submit | 2026-11-16 | 2026-11-16 | 2026-11-16 | Tariff Meter Services | 1 | 2026-01-31 | Clarifying | 2026-06-28 |  |  |  | Telecom Panel FAT at QATAR |  | F 2026-06-21
[17 empty] | 0 | 0 |  | Sub-order Issued | 2026-01-31 | 2026-01-31 | 2026-02-01 | SCS Panel | 2 | 2026-01-31 | 2026-02-02 | 2026-06-16
[17 empty] | 0 | 0 |  | FAT | 2026-07-06 | 2026-07-06 |  | SCS Equipment | 1 | 2026-01-31 | 2026-03-05 | 2026-06-16
[17 empty] | 0 | 0 |  | Cargo ready- SCS and Tariff Meter Panel | 2026-07-13 | 2026-07-13 |  | C&P Modification at QSTECH | 1 | 2026-01-04 | 2026-01-04 | 2026-04-28
[20 empty] | Cargo ready- OTB | 2026-06-21 | 2026-06-21 |  | SCADA Modification at DGCC for QSTECH and addition of ESP | 1 | 2026-02-15 | 2026-03-01 | 2026-07-23
[20 empty] | Cargo ready- Telecom Panel | 2026-06-28 | 2026-06-28

## Instrument
No. | Material Requisition |  | Purchase Order | [11 empty] | Delivery Status |  |  |  |  | Key Milestone |  |  |  | Sub/Order Status | [7 empty] | Inspection | [6 empty] | Shipping & Delivery | [9 empty] | Bond | Contact Point |  |  | Main Issue |  | Histroy issue
| M/R No. | M/R Name | P/O No. | Rev. | Vendor Name | Origin |  | P/O Released | Delivery Date | Delivery Term | Delivery Location | QTY |  |  | Ordered Q'ty. | Unit | Shipped Q'ty. | Un-Shipped Q'ty. | Delivery Rate | Key Milestone | Plan | Forecast | Actual | Sub/Order Item | Q'ty | Sub/Order Issued |  | Sub/Order Received |  |  | Sub-Vendor | Inspection Activity | I/A No. | Inspection Starting Date |  | IRC |  |  | Batch No. | Shipment No. | Shipping |  |  |  | Material shipped |  | Delivery at Site |  | Curr. | Duty | Phone | Mail | Current Status | Pending Issue & Countermeasure
[6 empty] | Contract | Manufacturing |  |  |  |  | SE&A (Ordered/Not Ordered) | CTCI (Ordered/Not Ordered) | Total (Ordered/Not Ordered) | [11 empty] | Forecast | Actual | Forecast | Actual | Q'ty |  |  |  | Forecast | Actual | IRC No. | Q'ty | Unit |  |  | Q'ty (SE&A) | Q'ty (CTCI) | Q'ty (Total) | Unit | ETD | ATD | ETA | ATA
1 | KAR206 | Variable Area Flowmeter | 5000106373 | 1 | KROHNE Korea Co., Ltd. | GE | GE | 2025-02-20 | 2026-03-01 | FOB | GERMANY | 0 | 8/0 | 8/0 | 8 | set | 8 | . | 100 | KOM | NA | NA | NA | H250 RR M40 | 8 | 2025-08-18 | 2025-08-18 | 2025-10-01 | 2025-09-15 | 8 | KROHNE Messtechnik GmbH, Germany | Final&Packing inspection | N-5000106373-001 | 2025-10-30 | 2025-10-30 | IRC-5000106373-0001 | 8 | EA | 1 | SC7128C-P5-EL102-CS | - | 8 | 8 | EA | 2025-12-19 | 2025-12-22 | 2026-02-15 | 2026/2/9 |  |  |  |  | Krohne to submit VDB rev.0
[20 empty] | VPIS Submit | 2025-03-28 | 2025-04-11 | 2025-04-09 | [16 empty] | SC7128C-P5-KA103-CS | Name Plate (DHL#2257899206) |  |  |  | 2026-02-05 | 2026-02-05 | 2026-02-09 | 2026/2/9
[20 empty] | Key V/P Submit | 2025-04-04 | 2025-04-25 | 2025-04-24
[20 empty] | Sub-order Issued | 2025-07-01 | 2025-08-18 | 2025-08-18
[20 empty] | Receive Main material | 2025-10-01 | 2025-10-01 | 2025-09-15
[20 empty] | Start Fabrication | 2025-10-01 | 2025-10-05 | 2025-09-20
[20 empty] | Manufacturing Completion | 2026-01-15 | 2025-11-14 | 2025-10-20
[20 empty] | Final Inspection | 2026-02-01 | 2025-11-17 | 2025-10-30
[20 empty] | Cargo ready | 2026-03-01 | 2025-12-19 | 2025-12-22
2 | KAR206 | Instrument Cable Tray and Fittings | 5000107368 | 2 | Suzhou Ontop Mechanical & Electrical Equipment Co., Ltd | CN | CN | 2025-04-09 2025-12-29 | 2026-06-15 2025-08-15 2026-03-10 | FOB | Job site | 10,071/0 | 10,044/0 | 20,115/0 | 20115 | meter | 6084 | 14031 | 30.2461 | KOM | N/A | N/A | N/A | [8 empty] | Imspection for 1st batch (ite-in) | N-5000107368-001 | 2025-06-12 | 2025-06-12 | IRC-5000107368-001 | 6084 | Meter | 1 | SC7128C-P5-CC014-CS | 0 | 2880 | 2880 | meter | 2025-06-29 | 2025-06-29 | 2025-07-31 | 2025-08-03 |  |  |  |  | 3rd PO: ATD 4/29 ETA port 6/9
[20 empty] | VPIS Submit | 2025-05-12 | 2025-05-12 | 2025-05-12 | [8 empty] | Imspection for 2nd batch (include process and utility) | N-5000107368-002 | 2025-08-13 | 2025-08-13 | IRC-5000107368-002 | 19965 | Meter |  | SC7128C-P5-CC027-CS |  | 1440 | 1440 | meter | 2025-06-29 | 2025-06-29 | 2025-07-31 | 2025-08-03
[20 empty] | Key V/P Submit | 2025-05-12 | 2025-05-12 | 2025-05-12 | [8 empty] | Imspection for 3rd batch (include process and utility) | N-5000107368-003 | 2026-01-31 | 2026-01-31 | IRC-5000107368-0003 | 4434 | Meter |  | SC7128C-P5-CC030-CS |  | 720 | 720 | meter | 2025-07-03 | 2025-07-06 | 2025-07-25 | 2025-07-27
[20 empty] | Sub-order Issued | 2025-04-15 | 2025-04-21 | 2025-04-21 | [16 empty] | SC7128C-P5-CC031-CS |  | 1044 | 1044 | meter | 2025-07-05 | 2025-07-06 | 2025-07-25 | 2025-07-27
[20 empty] | Receive Main material | 2025-04-25 | 2025-04-25 | 2025-04-25 | [15 empty] | 2 | SC7128C-P5-CC062-CS |  | 4584 | 4584 | meter | 2025-09-10 | 2025-09-10 | 2025-10-04 | 2025-10-02
[20 empty] | Start Fabrication | 2025-04-25 | 2025-04-25 | 2025-04-25 | [15 empty] | 3 | SC7128C-P5-CC063-SS | 15381 | 0 | 15381 | meter | 2025-09-10 | 2025-09-10 | 2025-10-04 | 2025-10-02
[20 empty] | Cargo ready (1st fo tie-in) | 2025-06-15 | 2024-06-24 | 2025-06-22 | [15 empty] | 4 | SC7128C-P5-CC134-CS | 0 | 3960 | 3960 | meter | 2026-04-25 | 2026-04-29 | 2026-06-15
[20 empty] | Cargo ready (2nd) | 2025-08-15 | 2025-09-10 | 2025-09-10 | [16 empty] | SC7128C-P5-CC135-SS | 474 | 0 | 474 | meter | 2026-04-25 | 2026-04-29 | 2026-06-15
[20 empty] | Cargo ready (3rd) | 2026-03-10 | 2026-03-08 | 2026-03-08
3 | KAR102 | Temperature Element | 5000107441 | 1 | WIKA Korea Ltd. | KR | KR | 2025-04-24 | 2026-04-01 | FOB | KOREA | 39/0 | 9/0 | 48/0 | 48 | EA | . | 48 | 0 | KOM | NA | NA | NA | [8 empty] | Final Inspection | N-5000107441-001 | 2026-04-22&24 | 2026-04-22&24 |  | 48 | EA | [14 empty] | 40-TW-10021 to be re-manufactured. (300 lbs -> 1500 lbs) Pressure Test / 2” 1500lb items shall be re-tested by 373 bar. (40-TW-10013, 10019, 40002, 40003, 40012AS/BS/CS, 10021) |  | (12/9) Tag# changed 40-TE-40001/40-TW-40001 -> 40-TE-10040/40-TW-10040
[20 empty] | VPIS Submit | 2025-05-23 | 2025-05-30 | 2025-06-03 | [8 empty] | Packing Inspection | N-5000107441-002 | 2026-05-21 | waive |  | 48 | EA
[20 empty] | Key V/P Submit | 2025-06-23 | 2025-07-20 | 2025-07-17
[20 empty] | Sub-order Issued | 2025-08-23 | 2026-01-10 | 2026-01-09
[20 empty] | Receive Main material | 2025-10-23 | 2026-02-27 | 2026-02-27
[20 empty] | Start Fabrication | 2025-10-25 | 2026-03-05 | 2026-03-05
[20 empty] | Manufacturing Completion | 2026-02-25 | 2026-04-15 | 2026-04-15
[20 empty] | Final Inspection | 2026-03-10 | 2026-04-22 | 2026-04-22
[20 empty] | Cargo ready (47EA) | 2026-04-01 | 2026-05-30
[20 empty] | Cargo ready (40-TW-10021) | 2026-04-01 | 2026-07-22
4 | KAR407 | LEVEL GAUGE | 5000107440 | 1 | Samil Industry Co., Ltd. | KR | KR | 2025-04-02 | 2026-02-15 | FOB | KOREA | 10/0 | 5/0 | 15/0 | 15 | set | 5 | 10 | 33% | KOM | NA | NA | NA | Flange (Utility) | 24 | 2025-07-10 | 2025-07-15 | 2025-08-20 | 2025-08-22 | 24 | Kumoh Forge | Fit up (Utility) | N-5000107440-001 | 2025-12-10 | 2025-12-10 |  | 5 | EA | 1 | SC7128C-P5-KC162-CS | - | 5 | 5 | EA | 2026-04-17 | 2026-04-14 | 2026-06-27
[20 empty] | VPIS Submit | 2025-05-23 | 2025-05-23 | 2025-05-26 | Valve (Utility) | 8 | 2025-07-10 | 2025-07-15 | 2025-08-20 | 2025-08-22 | 8 | Dongeun Valve | Final&Packing inspection (Utility) | N-5000107440-002 | 2026-02-04 | 2026-02-09 | IRC-5000107440-0001 | 5 | EA
[20 empty] | Key V/P Submit | 2025-06-23 | 2025-05-30 | 2025-06-05 | Gasket (Utility) | 23 | 2025-08-05 | 2025-08-14 | 2025-09-10 | 2025-09-10 | 23 | Flexitallic | Fit up (Process) | N-5000107440-003 | 2026-04-03 | 2026-04-03 | N/A | 10 | EA
[20 empty] | Sub-order Issued | 2025-08-23 | 2025-07-25 | 2025-07-15 | [8 empty] | Final&Packing inspection (Process) | N-5000107440-004 | 2026-05-20 | 2026-05-20
[20 empty] | Receive Main material | 2025-10-23 | 2025-08-09 | 2025-08-22
[20 empty] | Start Fabrication | 2025-10-25 | 2025-08-10 | 2025-08-22
[20 empty] | Manufacturing Completion | 2026-01-10 | 2026-02-01 | 2026-02-04
[20 empty] | Final Inspection | 2026-01-15 | 2026-02-09 | 2026-02-09
[20 empty] | Cargo ready (Utility) | 2026-02-15 | 2026-03-01 | 2026-03-01
[20 empty] | Cargo ready (Process) | 2026-02-15 | 2026-05-30
5 | KAR303 | PRESSURE GAUGE & TEMPERATURE GAUGE | 5000107447 | 1 | WISE Control Inc. | KR | KR | 2025-04-24 | 2025/12/30 2026/2/1 | FOB | KOREA | 15/0 | 17/0 | 32/0 | 32 | set | 31 | . | 100 | KOM | NA | NA | NA | 2-Way manifold valve | 21 | 2025-11-27 | 2025-12-05 | 2026-01-12 | 2026-01-12 | 21 | Hy-lok korea | Final&Packing inspection (073-PI-0125) | N-5000107447-001 | 2025-12-18 | 2025-12-18 | IRC-5000107447-0001 | 1 | EA | 1 | SC7128C-P5-KA092-CS | - | 1 | 1 | EA | 2025-12-26 | 2025-12-26 | 2025-12-28 | 2025-12-28
[20 empty] | VPIS Submit | 2025-05-23 | 2025-05-23 | 2025-05-13 | 2-Way manifold valve | 1 | 2025-12-01 | 2025-12-05 | 2026-01-15 | 2026-01-15 | 1 | Hy-lok korea | Final&Packing inspection (PG) | N-5000107447-002 | 2026-02-03 | 2026-02-03 ~2026-02-04 | IRC-5000107447-0002 | 27 | EA | 2 | SC7128C-P5-KC154-SS | 14 | - | 14 | EA | 2026-04-17 | 2026-04-14 | 2026-06-10
[20 empty] | Key V/P Submit | 2025-05-30 | 2025-06-09 | 2025-06-10 | Mono Flange valve | 1 | 2025-10-30 | 2025-09-03 | 2026-01-26 | 2025-12-16 | 1 | Hy-lok korea | Final&Packing inspection (TG) | N-5000107447-003 |  |  | IRC-5000107447-0003 | 3 | EA | 3 | SC7128C-P5-KC144-CS | - | 16 | 16 | EA | 2026-04-17 | 2026-04-14 | 2026-06-10
[20 empty] | Sub-order Issued | 2025-07-30 | 2025-12-01 | 2025-12-10 | Mono Flange valve | 1 | 2025-08-30 | 2025-08-13 | 2025-12-19 | 2025-12-19 | 1 | Hy-lok korea | Final&Packing inspection (Pre-commissioning Spares)-PG | N-5000107447-004 | 2026-04-29 | 2026-04-29 | IRC-5000107447-0004 | 1 | SET | 4 | SC7128C-P5-KA224-SS | 1 |  |  | SET | 2026-05-17 | 2026-05-17 | 2026-05-17 | 2026-05-17
[20 empty] | Receive Main material | 2025-09-30 | 2026-01-12 | 2026-01-12 | Mono Flange valve | 2 | 2025-10-30 | 2025-10-24 | 2026-01-26 | 2026-01-26 | 2 | Hy-lok korea | Final&Packing inspection (Pre-commissioning Spares)-TG | N-5000107447-005 | 2026-04-30 | 2026-04-30 | IRC-5000107447-0005 | 1 | SET | 5 | SC7128C-P5-KA224-SS |  | 1 |  | SET | 2026-05-17 | 2026-05-17 | 2026-05-17 | 2026-05-17
[20 empty] | Start Fabrication | 2025-10-10 | 2026-01-13 | 2026-01-13 | Law Material | 1 LOT | 2025-11-27 | 2025-12-10 | 2026-01-26 | 2026-01-26 | 1 LOT | POSCO
[20 empty] | Manufacturing Completion | 2025-12-31 | 2026-01-31 | 2026-01-28
[20 empty] | Final Inspection | 2026-01-10 | 2026-02-03 | 2026-02-03
[20 empty] | Cargo ready (073-PI-0125) | 2025-08-20 | 2025-12-19 | 2025-12-26
[20 empty] | Cargo ready (30EA) | 2026-02-01 | 2026-03-01 | 2026-03-01
[20 empty] | Cargo ready (Pre-commissioning Spares) | 2026-02-01 | 2026-05-17 | 2026-05-17
6 | KAR202 | Orifice Plate | 5000107469 | 3 | Samil Industry Co., Ltd. | KR | KR | 2025-04-24 | 2026-02-01 | FOB | KOREA | 26/0 | 10/0 | 30/0 | 29 | set | 10 | 26 | 38.5 | KOM | NA | NA | NA | Flange (for Utility) | 10 | 2025-09-30 | 2025-10-02 | 2025-12-31 | 2025-11-30 | 10 | Kumoh Forge or Equiv. | Final&Packing inspection (for Utility) | N-5000107469-001 | 2026-01-27 | 2026-01-27 | IRC-5000107469-0001 | 10 | EA | 1 | SC7128C-P5-KL148-CS | - | 10 | 10 | EA | 2026-02-17 | 2026-02-21 | 2026-06-07
[20 empty] | VPIS Submit | 2025-05-28 | 2025-05-28 | 2025-06-02 | Gasket (for Utility) | 20 | 2025-10-02 | 2025-10-02 | 2025-11-05 | 2025-11-05 | 20 | Flexitallic | Final&Packing inspection (for Process Flange&Nipple) | N-5000107469-002 | 2026-04-08 | 2026-04-08 | IRC-5000107469-0002 | 12 | EA | 2 | SC7128C-P5-KA194-SS | 12 |  | 12 | EA | 2026-04-25 | 2026-04-25 | 2026-04-28 | 2026-04-25
[20 empty] | Key V/P Submit | 2025-06-28 | 2025-06-15 | 2025-06-16 | Flange (for Process) | 36 | 2025-12-03 | 2025-12-03 | 2026-02-10 | 2026-02-10 | 36 | Kumoh Forge or Equiv. | Final&Packing inspection (for Utility Nipple Spares) | N-5000107469-003 | 2026-05-11 | N/A (SQR review) | IRC-5000107469-0003 | 5 | EA | 3 | SC7128C-P5-KA225-CS | - | 5 | 5 | EA | 2026-05-15 | 2026-05-14 | 2026-05-17 | 2026-05-14
[20 empty] | Sub-order Issued | 2025-08-30 | 2025-11-15 | 2025-10-02 | Gasket (for Process) | 24 | 2026-01-15 | 2026-01-15 | 2026-01-29 | 2026-02-10 | 24 | Flexitallic | Final&Packing inspection (for Process) | N-5000107469-004 | 2026-05-26 |  |  | 25 | EA
[20 empty] | Receive Main material | 2025-10-30 | 2025-12-15 | 2025-11-30
[20 empty] | Start Fabrication | 2025-11-01 | 2025-12-20 | 2025-12-02
[20 empty] | Manufacturing Completion | 2026-01-10 | 2026-01-22 | 2026-01-22
[20 empty] | Final Inspection | 2026-01-15 | 2026-01-27 | 2026-01-27
[20 empty] | Cargo ready (Utility Main) | 2026-02-01 | 2026-02-17 | 2026-02-21
[20 empty] | Cargo ready (Process-Flange&Nipple) | 2026-02-01 | 2026-04-26 | 2026-04-25
[20 empty] | Cargo ready (Utility-Nipple Spare) | 2026-07-01 | 2026-05-27 | 2026-05-14
[20 empty] | Cargo ready (Process Main) | 2026-02-01 | 2026-06-12
7 | KBR920 | INSTRUMENT CABLE | 5000107926 | 2 | GAON CABLE Co., Ltd | KR | KR | 2025-05-08 | 2025-07-21 | FOB |  | 81252/0 | 101394/0 | 182646/0 | 182646 | meter | 32204 | 150442 | 21.4063 | KOM | NA | NA | NA | [8 empty] | Inspeciton for 1st batch (ite-in) | N-5000107926-001 N-5000107926-002 | 2025-07-03 2025-07-09 | 2025-07-03 2025-07-09 | IRC-5000107926-001 IRC-5000107926-002 | 32204 | Meter | 1 | SC7128C-P5-KC020-CS | 0 | 16100 | 16100 | meter | 2025-07-24 | 2025-07-23 | 2025-08-30 | 2025-09-01 |  |  |  |  | 2nd PO: HMM MIR 0019W, ATA Hamad 5/19 3rd PO ATD 4/29 ETA port 6/28 4th PO: Forecast delivery date: 7/15
[20 empty] | VPIS Submit | 2025-06-02 | 2025-06-02 | 2025-06-02 | [8 empty] | Inspeciton for 2nd batch | N-5000107926-003 | 2026-01-22 | 2026-01-22 | IRC-5000107926-003 | 95402 | Meter |  | SC7128C-P5-KCA033-CS | 0 | 11554 | 11554 | meter | 2025-07-20 | 2025-07-20 | 2025-07-20 | 2025-07-20
[20 empty] | Key V/P Submit | 2025-06-15 | 2025-06-15 | 2025-06-05 | [8 empty] | Inspeciton for 3rd batch | N-5000107926-005&006&007 | 2026-03-24 2026-04-01 | 2026-03-24 2026-04-01 | IRC-5000107926-004-6 | 55040 | Meter |  | SC7128C-P5-KA036-CS | 0 | 3500 | 3500 | meter | 2025-07-24 | 2025-07-23 | 2025-07-24 | 2025-07-23
[20 empty] | Sub-order Issued | 2025-05-12 | 2025-05-12 | 2025-05-12 | [16 empty] | SC7128C-P5-KA042-CS | 0 | 1050 | 1050 | meter | 2025-07-19 | 2025-07-19 | 2025-07-19 | 2025-07-19
[20 empty] | Receive Main material | 2025-05-13 | 2025-05-13 | 2025-05-13 | [15 empty] | 2 | SC7128C-P5-KC124-CS | 0 | 14150 | 14150 | meter | 2026-02-07 | 2026-02-08 | 2026-05-22
[20 empty] | Start Fabrication | 2025-05-15 | 2025-05-15 | 2025-05-15 | [16 empty] | SC7128C-P5-KC125-SS | 81252 | 0 | 81252 | meter | 2026-02-07 | 2026-02-08 | 2026-05-20 | B/L to be revised due to different POD
[20 empty] | Manufacturing Completion | 2025-07-09 | 2025-07-01 | 2025-07-01 | [15 empty] | 3 | SC7128C-P5-KC215-CS |  | 55040 | 55040 | meter | 2026-04-30 | 2026-04-29 | 2026-07-05
[20 empty] | Final Inspection | 2025-07-10 | 2025-07-03 | 2025-07-03
[20 empty] | Cargo ready (Tie-in scope) | 2025-07-21 | 2025-07-21 | 2025-07-20
[20 empty] | Cargo ready (2nd PO) | 2026-01-15 | 2026-02-11 | 2026-02-08
[20 empty] | Cargo ready (3rdPO) | 2026-04-26 | 2026-04-30 | 2026-04-29
[20 empty] | Cargo ready (4thPO) | 2026-07-15 | 2026-07-15
8 | KAR893 | Integrated Telecommunication System | 5000108095 | 1 | Vector InfoTech Pte Ltd | SG | Internation | 2025-05-22 | 2026-03-31 2026-04-40 2026-05-30 | FOB/DDP |  | 0/0 | 2/0 | 2/0 | 2 | Lot | 0 | 2 | 0 | KOM | 2025-06-04 | 2025-06-04 | 2025-06-04 | System Cabinet - Rittal | 6 | 2025-07-15 | 2025-09-29 | 2026-01-16 | 2026-01-16 | 6 | Rittal Pte Ltd | turn around scope-antenna cable | N/A | N/A | N/A | IRC-5000108095-0001 | 1 | Lot | 1 | SC7128C-P4-LT083-CS |  | 1 | 1 | Lot | 2025-10-28 | 2025-10-28 | 2025-10-28 | 2025-10-28 |  |  |  |  | 1)Cabinet Cabinet from SG to IN: Confirmed the WPC is required and will take 1-2 onth for application. 2)Ooredoo the subvendor for Tetra and Cellular is lack of respond and unable to advise the delivery schedule. Delivery schedule was postponed to 11/15 3)FAT of 1st shipment of equiments was done by 4/14 All punches were closed, SQR is unber reviewing Vendor will shipment goods based on DDP term, and resourcing vessel now. Forecast cargo ready 6/2
[20 empty] | VPIS Submit | 2025-06-06 | 2025-06-06 | 2025-06-06 | All Junction Box - Rose | 86 | 2025-07-15 | 2025-10-16 | 2025-12-20 | 2026-01-20 | 86 | Rose | turn around scope-FO cable | N/A | N/A | N/A | IRC-5000108095-0002 | 1 | Lot | 2 | SC7128C-P4-LT084-CS |  | 1 | 1 | Lot | 2025-10-30 | 2025-10-30 | 2025-11-03 | 2025-11-03
[20 empty] | Key V/P Submit | 2025-07-01 | 2025-07-01 | 2025-07-01 | EAS System - Industronic | 1 | 2025-09-24 | 2025-09-24 | 2026-01-29 | 2026-01-29 |  | Industronic | CCTV anchor bolt | N/A | N/A | N/A | IRC-5000108095-0003 | 1 | Lot | 3 | SC7128C-P5-AC098-CS |  | 1 | 1 | Lot | 2025-11-17 | 2025-11-17 | 2026-12-06 | 2026-12-07
[20 empty] | Sub-order Issued | 2025-07-15 | 2025-10-15 | 2025-09-29 | CCTV Cameras | 88 | 2025-10-10 | 2025-10-10 | 2025-12-29 | 2026-12-01 | 2 | Axis & Pelco | Anchor bolt for EAS siren pole | N/A | N/A | N/A | IRC-5000108095-0004 | 1 | Lot | 4 | SC7128C-P5-AA108-CS |  | 1 | 1 | Lot | 2026-01-24 | 2026-01-25 | 2026-01-25 | 2026-01-27
[20 empty] | Receive Main material | 2025-08-30 | 2026-01-16 | 2025-11-17 | ACS Controller | 1 | 2025-11-07 | 2025-10-30 | 2026-01-02 | 2025-11-17 |  | Siemens | Cabinet for RIE & AH (In SG) | N-5000108095-001 | 2026-01-26 to 2026-01-31 | 2026-01-26 to 2026-01-31 | IRC-5000108095-0005 | 5 | Set | 5 | SC7128C-P5-AC151-V |  | 1 | 1 | Lot | 2026-03-14 | 2026-03-14 | 2026-04-10 | 2026-04-03
[20 empty] | Start Fabrication (Cabinet) | 2025-09-12 | 2025-12-23 | 2026-12-23 | [8 empty] | RIE EAS Cabinet & EAS field equipment (In DE) | N-5000108095-002 | 2026-02-10 to 2026-02-12 | 2026-02-10 to 2026-02-12 | IRC-5000108095-0006 | 1 | Set | 6 | SC7128C-P5-AC152-V |  | 1 | 1 | Lot | pending - India BIS certificate to be advised by Emerson |  | TBD
[20 empty] | Manufacturing Completion (Cabinet) | 2025-12-16 | 2026-01-30 | 2026-01-25 | [8 empty] | Inspection for Telecom Cabinet and Field Equipment FA | N-5000108095-003 | 2026-04-06 to 2026-04-14 | 2026-04-06 to 2026-04-14 | SQR reviewing |  |  | 7 | SC7128C-P5-EA153-V |  | 1 | 1 | Lot | 2026-03-31 | 2026-03-31 | 2026-04-06 | 2026-04-03
[20 empty] | Final Inspection (Cabinet) | 2025-12-19 | 2026-01-26 | 2026-01-26 | [8 empty] | Inspection for CO2 Telecom Equipment | N-5000108095-004 | 2026-06-04 |  |  |  |  | 8 | SC7128C-P5-AA232-V |  | 1 | 1 | EA | 2026-05-21 | 2026-05-21 | 2026-05-21 |  | black box to Yokogawa
[20 empty] | Cargo ready (Cabinet) | 2026-01-30 | 2026-03-14 | 2026-03-14
[20 empty] | Cargo ready | 2026-03-24 | 2026-06-02
[20 empty] | Cargo ready-OREDOO | 2026-03-24 | 2026-11-15
[20 empty] | Cargo ready-CO2 items | 2026-06-30 | 2026-07-31
9 | KBR940 | INSTRUMENT JUNCTION BOX AND LCP | 5000108061 | 2 | Phoenix Mecano | SG | India | 2025-05-29 | 2025-07-31 | FOB |  | 222/0 | 95/0 | 317/0 | 317 | EA | 3 | 314 | 0.95 | KOM | NA | NA | NA | Terminal block | [7 empty] | Inspeciton for 1st batch (ite-in) | N-5000108061-001 | 2025-08-08 | 2025-08-08 | IRC-5000108061-0001 | 3 | EA | 1 | SC7128C-P5-AL066-CS | 0 | 3 | 3 | EA | 2025-09-29 | 2025-09-28 | 2025-10-29 | 2025-10-16 |  |  |  |  | NOI issued, FAT 5/29
[20 empty] | VPIS Submit | 2025-06-19 | 2025-06-27 | 2025-06-30 | Plug | [7 empty] | Inspeciton for 2nd batch (ite-in)-splicing box | N/A | N/A | N/A | IRC-5000108061-0002 | 20 | Set | 2 | SC7128C-P5-AA079-CS SC7128C-P5-AL107-CS | 0 | 20 | 20 | EA | 2025-12-02 2025-12-21 | 2025-12-04 2026-01-06 | 2025-12-04 2026-01-10 | 2025-12-04 2026-01-11
[20 empty] | Key V/P Submit | 2025-06-28 | 2025-06-28 | 2025-06-30 | Componets | [7 empty] | Inspeciton for 3rd PO | N-5000108061-002 | 2026-05-29
[20 empty] | Sub-order Issued | 2025-06-27 | 2025-07-06 | 2025-07-06
[20 empty] | Receive Main material | 2025-06-27 | 2025-07-06 | 2025-07-06
[20 empty] | Start Fabrication | 2025-06-27 | 2025-07-18 | 2025-07-14
[20 empty] | Manufacturing Completion | 2025-08-12 | 2025-08-07 | 2025-08-07
[20 empty] | Final Inspection | 2025-08-13 | 2025-08-08 | 2025-08-08
[20 empty] | Cargo ready (Tie-in J/B) | 2025-07-31 | 2025-09-29 | 2025-09-28
[20 empty] | Cargo ready (Tie-in splicing box) | 2025-10-30 | 2025-12-01 | 2025-12-01
[20 empty] | Cargo ready (3rd PO, 100% q'ty) | 2026-03-15 | 2026-06-20
10-1 | KAR701 | Metering Station | 5000108145 | 0 | Emerson Asia Pacific Private Limited | SG | India | 2025-05-08 | 2026-04-30 | FOB |  | 0/0 | 3/0 | 3/0 | 3 | Lot | 0 | 3 | 0 | KOM | 2025-06-30 | 2025-06-30 | 2025-06-30 | CORIOLIS METER | 16 | 2025-08-04 | 2025-08-04 | 2026-04-25 | 2026-04-09 | 8 | Emerson | Inspectio for metering control panel | N-5000108145-002 | 2026-02-02 to 2026-02-07 | 2026-02-02 to 2026-02-07 | IRC-5000108145-001 | 1 | Set | 1 | SC7128C-P5-AC139-V | 0 | 1 | 1 |  | 2026-03-19 | 2026-03-18 | 2026-04-10 | 2026-04-09 | to RIE shop |  |  |  | 1.The cargo ready date of 3 metering skid are postponed to mid of Jul Current delay reason: 1) Valves: ETD Dubai: 6/8  ETA India: 6/10 (postponed due to Eid) 1st batch: -Final Inspection date: 5/22 -Packing: completed by 5/25 2nd batch(Actuated valves): -Target inspection date: 1st week of Jun, NOI will be issued by 5/22 2)PSV (India factory), will delivered to site seperately. -Target DDP: vendor is checking the date, lead time is 20 weeks. 2.FAT schedule: Natural Gas & Propane Skid: 6/20 Ethylene Metering Skid:7/13
[20 empty] | VPIS Submit | 2025-05-08 | 2025-06-27 | 2025-07-02 | Ball Valves | 146 | 2025-08-26 | 2025-09-01 | 2026-06-15 |  | 1 Lot | JC VALVULAS ME FZC | Inspectio for HRVOC & GC | N-5000108145-003 | 2026-02-10 2026-02-11 | 2026-02-10 2026-02-11 | N/A | 3 | EA | 2 | SC7128C-P5-AC221-CS | 0 | 2 | 2 | Set
[20 empty] | Key V/P Submit | 2025-06-30 | 2025-06-30 | 2025-06-30 | GC | 1 | 2025-09-03 | 2025-09-01 | 2026-04-15 | 2026-04-09 | 1 | PAS | Inspectio for Coriolis Meter | N-5000108145-004 | 2026-03-09 to 2026-03-13 | 2026-03-09 to 2026-03-13 | N/A | 1 | EA | 3 | SC7128C-P5-AC222-CS | 0 | 1 | 1 | Set
[20 empty] | Sub-order Issued-Metering | 2025-07-22 | 2025-08-12 | 2025-08-07 | Check Valve |  | 2025-09-10 | 2025-09-02 | 2026-06-15 |  | 1 Lot | JC Valves, Dubai | Inspectio for metering skid (Intermediate Inspection) | N-5000108145-005 | 2026-02-27 | 2026-02-27 | N/A | 3 | Set
[20 empty] | Receive Main material-Metering | 2025-08-06 | 2026-01-13 | 2026-01-13 | Globe Valve |  | 2025-09-10 | 2025-09-02 | 2026-06-15 |  | 1 Lot | JC Valves, Dubai | Inspection for Natural Gas & Propane Metering Skid(Intermediate Inspection) | N-5000108145-007 | 2026-03-10&11 2026-03-17&18 2026-03-24 | 2026-03-10&11 2026-03-17&18 | N/A | 2 | Set
[20 empty] | Start Fabricationl-metering control panel | 2026-01-12 | 2026-01-12 | 2026-01-12 | Thermal Relief Valve |  | 2025-12-15 | 2025-12-12 | 2026-09-30 |  | 1 Lot | Lesser, India | Inspection for Natural Gas & Propane Metering Skid (painting) | N-5000108145-008 | 2026-04-15 | 2026-04-15 | N/A
[20 empty] | Start Fabricationl-Metering | 2025-08-06 | 2026-01-21 | 2026-01-13 | Pressure Safety Valve |  | 2025-12-15 | 2025-12-12 | 2026-09-30 |  | 1 Lot | Lesser, India | Inspection for galvanizing for structure | N-5000108145-009 | 2026-04-18 | 2026-04-18 | N/A
[20 empty] | Manufacturing Completionl-metering control panel | 2026-01-31 | 2026-02-01 | 2026-02-01 | Flow Computer (S600+) |  | 2025-08-26 | 2025-08-26 | 2025-10-24 | 2026-10-20 | 1 Lot | Emerson, USA | Inspection for for structure & piping visual & dimension without shoe support | N-5000108145-014 | 2026-04-27 to 2026-05-07 | 2026-04-27 to 2026-05-07 | N/A
[20 empty] | Manufacturing Completionl-Natural Gas & Propane Skid | 2026-01-01 | 2026-06-07 |  | PT, TT, TW, RTD |  | 2025-08-04 | 2025-08-04 | 2026-06-30 | 2026-05-20 | 14 | Emerson, India | Inspection for ball valve, check valve, Globe Valve | N-5000108145-015 | 2026-05-05 2026-05-06 2026-05-07 | 2026-05-05 2026-05-06 2026-05-07 | N/A
[20 empty] | Manufacturing Completionl-Ethylene Metering Skid | 2026-01-01 | 2026-07-01 |  | Junction Box |  | 2026-01-05 | 2026-01-01 | 2026-04-15 | 2026-04-29 |  |  | Surface Preparation Inspection for ball valve, check valve, Globe Valve | N-5000108145-016 | 2026-05-13 | 2026-05-13 | N/A
[20 empty] | Final Inspectionl-metering control panel | 2026-01-28 | 2026-02-02 | 2026-02-02 | Metering control panel |  | 2025-10-28 | 2025-10-28 | 2025-02-28 | 2025-02-28 | 1 |  | Painting Inspection for ball valve, check valve, Globe Valve | N-5000108145-017 | 2026-05-22 | 2026-05-22 | N/A
[20 empty] | Final Inspectionl-Natural Gas & Propane Skid | 2026-01-10 | 2026-06-20 |  | Metering skid |  | 2025-08-19 | 2025-08-19 | 2026-01-20 | 2026-01-13 | 1 Lot | WIKA | Inspection for metering skids Structure Final Dimension | N-5000108145-018 | 2026-05-12 | 2026-05-12 | N/A
[20 empty] | Final Inspectionl-Ethylene Metering Skid | 2026-01-10 | 2026-07-13 |  | Alcatraz interlocks | 14 | 2026-04-24 | 2026-02-19 | 2026-05-30 |  |  | ALCATRAZ INTERLOCKS BV | Final Galvanizing inspection for Ethylene Metering Skid | N-5000108145-019 | 2026-05-11 | 2026-05-11 | N/A
[20 empty] | Cargo ready-metering control panel | 2026-02-28 | 2026-03-14 | 2026-03-14 | [8 empty] | Calibration witness of coriolis meters in FCRI, India(Propane & NG Metering) |  | F 2026-05-25&26
[20 empty] | Cargo ready-Natural Gas & Propane Skid | 2026-04-30 | 2026-07-03 | [9 empty] | CalibraCalibration witness of coriolis meter in Singapore(Ethylene Metering) |  | F 2026-06-01
[20 empty] | Cargo ready-Ethylene Metering Skid | 2026-04-30 | 2026-07-28 | [9 empty] | Final FAT (Propane & NG Metering) |  | F 2026-06-20
[20 empty] | - | - | - | - | [8 empty] | Final FAT(Ethylene Metering) |  | F 2026-07-13
10-2 | KAR701 | Analyzer | 5000108145 | 0 | Emerson Asia Pacific Private Limited | SG | India | 2025-05-08 | 2026/2/28 2026/5/15 | FOB |  | 0/0 | 3/0 | 3/0 | 3 | Lot | 0 | 3 | 0 | KOM | 2025-06-30 | 2025-06-30 | 2025-06-30 | HRVOC Analyzer | 2 | 2025-09-03 | 2025-09-01 | 2026-04-06 | 2026-04-09 | 2 | PAS, Singapore | Inspection for HRVOC and GC | N-5000108145-003 | 2026-02-10 2026-02-11 | 2026-02-10 2026-02-11 | N/A | [16 empty] | Rack and cabinet: Inspection date: 6/9, NOI issued . Target delivery date: 6/22 (NJB will arrive at vendor shop by end of May) AH will be delivered by early of Sep. (FAT by 8/17) Current delay reason: 1)HVAC -Electrical enclosure: Arrived, photo will be provdied from vendor. -HVAC FAT: 7/8.  ETD Australia: 7/15 (by air)  ETA India: 7/23. 2)PK controller panel: Forecast receiving date 7/31
[20 empty] | VPIS Submit | 2025-05-08 | 2025-06-27 | 2025-07-02 | Wobbe / Density Index | 2 | 2025-08-08 | 2025-08-08 | 2026-03-27 | 2026-04-09 | 2 | Hobre, Netherlands | Inspection for Rack and cabinet | N-5000108145-020 | 2026-06-09&10 2026-06-11&13
[20 empty] | Key V/P Submit | 2025-06-30 | 2025-06-30 | 2025-06-30 | Oxygen Analyzer | 1 | 2025-08-11 | 2025-08-11 | 2025-12-03 | 2025-10-28 | 2 | Emerson, UK | HVAC FAT |  | F 2026-07-08
[20 empty] | Sub-order Issued | 2025-08-04 | 2025-08-15 | 2025-08-11 | ORP Analyzer | 2 | 2025-08-14 | 2025-08-14 | 2026-07-08 |  | 2 | Emerson, USA | Final FAT (AH) |  | F 2026-08-07
[20 empty] | Final Inspectionl-Analyzer-Analyzer Cabinets and Racks | 2026-04-14 | 2026-06-09 |  | HVAC | 1 | 2025-10-15 | 2025-10-08 | 2026-07-23 |  |  | Stolway
[20 empty] | Final Inspectionl-Analyzer House | 2026-04-14 | 2026-08-17 |  | PK controller panel | 1 | 2026-04-30 | 2026-04-08 | 2026-07-31 |  |  | Emerson India
[20 empty] | Cargo ready-Analyzer Cabinets and Racks | 2026-05-15 | 2026-06-22 |  | PK controller accrssories | 147 | 2026-04-30 | 2026-04-07 | 2026-07-31 |  |  | Emerson India
[20 empty] | Cargo ready-Analyzer House | 2026-05-15 | 2026-09-07
11 | KBR933 | Cable Gland (Instrument) | 5000108080 | 1 | CMP Products Ltd. | SG | UK | 2025-05-22 2025-12-08 | 2025-07-31 2026-02-20 | FOB |  | 1701/0 | 993/0 | 2697/0 | 2697 | EA | 28 | 2669 | 1.04 | KOM | NA | NA | NA | [8 empty] | Inspection for 1st batcxh (tie-in) | N/A | N/A | N/A | IRC-5000108080-0001 | 28 | EA | 1 | SC7128C-P5-EA064-CS | 0 | 28 | 28 | EA | 2025-08-20 | 2025-08-20 | 2025-08-25 | 2025-08-25 |  |  |  |  | 2nd PO: space confirmed ATD 4/12 ETA 6/30
[20 empty] | VPIS Submit | 2025-06-27 | 2025-07-09 | 2025-07-09 | [8 empty] | Inspection for 2nd batcxh (SOC+TOC) | N/A | N/A | N/A | IRC-5000108080-0002 | 2192 | EA | 2 | SC7128C-P5-EC149-CS SC7128C-P5-EC150-SS | 1701 | 968 | 2669 | EA | 2026-04-12 | 2026-04-12 | 2026-07-15
[20 empty] | Key V/P Submit | 2025-06-10 | 2025-07-09 | 2025-07-09
[20 empty] | Sub-order Issued | 2025-06-17 | 2025-07-11 | 2025-07-11
[20 empty] | Receive Main material | 2025-07-18 | 2025-07-18 | 2025-07-17
[20 empty] | Start Fabrication | 2025-07-21 | 2025-07-21 | 2025-07-18
[20 empty] | Manufacturing Completion | 2025-07-24 | 2025-07-22 | 2025-07-22
[20 empty] | Final Inspection | 2025-07-25 | 2025-07-24 | 2025-07-24
[20 empty] | Cargo ready-1st PO | 2025-07-30 | 2025-07-30 | 2025-07-30
[20 empty] | Cargo ready-2nd PO | 2026-02-20 | 2026-03-08 | 2026-03-02
12 | KAR213 | Ultrasonic flowmeter | 5000108629 | 1 | INTERCIS | Ire | Ire | 2025-07-28 | 2026-03-01 | FOB | KOREA | 0/0 | 4/0 | 4/0 | 4 | EA | 4 | . | 100 | KOM | NA | NA | NA | Adaptor (3/4" NPT X M20) | 60 | 2026-01-02 | 2026-01-20 | 2026-03-01 |  |  | Shinhwa Tech | Final&Packing inspection (FOB Ireland) | N-50000108629-001 | 2026-02-19,20 | 2026-02-19,20 | IRC-5000108629-0001 | 2 | EA | 1 | SC7128C-P5-KC188-CS | - | 2 | 2 | EA | 2026-04-17 | 2026-04-14 | 2026-05-29
[11 empty] | Ireland | 0/0 | 2/0 | 2/0 | 2 | EA | 2 | . | 100 | VPIS Submit | 2025-07-16 | 2025-07-16 | 2025-07-16 | Tag Plate | 6 | 2026-01-20 | 2026-01-20 | 2026-03-01 |  |  | Shinhwa Tech | Calibration Test (FOB Korea) | N-50000108629-002 | 2026-02-25 | 2026-02-25 | N/A |  |  | 2 | SC7128C-P5-EA179-CS | - | 4 | 4 | EA | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-04-16
[20 empty] | Key V/P Submit | 2025-07-21 | 2025-08-10 | 2025-08-04 | Mounting Bracket for gas | 2 | 2026-01-20 | 2026-01-20 | 2026-03-01 |  |  | Shinhwa Tech | Final&Packing inspection (FOB Korea) | N-50000108629-003 | 2026-03-05 | 2026-03-05 | IRC-5000108629-0002 | 4 | EA
[20 empty] | Sub-order Issued | 2025-09-01 | 2025-11-30 | 2025-11-17 | Sunshade | 14 | 2026-01-20 | 2026-01-20 | 2026-03-01 |  |  | Shinhwa Tech
[20 empty] | Receive Main material | 2025-10-01 | 2026-01-07 | 2026-01-07 | GRP cabinet for Liquid | 2 | 2025-11-17 | 2025-11-17 | 2026-01-07 | 2026-01-07 | 2 | BULK s기
[20 empty] | Start Fabrication | 2025-11-01 | 2026-01-10 | 2026-01-10 | Gate Valve for Gas | 8 | 2025-09-30 | 2025-09-30 | 2026-01-07 | 2026-01-07 | 8 | PK Valve
[20 empty] | Manufacturing Completion | 2025-12-31 | 2026-01-23 | 2026-01-23
[20 empty] | Final Inspection | 2026-02-01 | 2026-02-20 | 2026-02-20
[20 empty] | Cargo ready (FOB Ireland) | 2026-03-01 | 2026-03-10 | 2026-03-10
[20 empty] | Cargo ready (FOB Korea) | 2026-03-10 | 2026-03-20 | 2026-03-20
13 | KAR212 | FIRE & GAS DETECTOR | 5000108715 | 0 | Tyco Qatar Fire & Security WLL | Qatar | Germany, UK, USA | 2025-07-10 | 2025-04-01 | DDP | [9 empty] | KOM | 2025-08-06 | 2025-08-06 | 2025-08-06 | Dräger Flame 1500, Dual M25 cable entry, Aluminum | 26 | 2025-10-22 | 2025-12-22 | 2026-06-15 |  | 26 | [22 empty] | Vendor is preparing GAD and datasheet of process scope (waiting the input from Dräger.
[20 empty] | VPIS Submit | 2025-08-01 | 2025-08-15 | 2025-08-21 | Polytron 8700 IR d 4-20mA HART Marine Grade Copper-Free Aluminium | 39 | 2025-10-22 | 2025-12-22 | 2026-06-15 |  | 39
[20 empty] | Key V/P Submit | 2025-09-09 | 2025-09-15 | 2025-09-17 | Dräger Pulsar 7000 Tx S Range JB Ex e Tx ONLY 4-60m | 12 | 2025-10-22 | 2025-12-22 | 2026-06-15 |  | 12
[20 empty] | Sub-order Issued | 2025-10-14 | 2025-12-30 | 2025-12-22 | Dräger Pulsar 7700 Rx S Range JB Ex e Rx ONLY 4-120m | 12 | 2025-10-22 | 2025-12-22 | 2026-06-15 |  | 12
[20 empty] | Manufacturing Completion | 2026-02-01 | 2026-06-15 |  | Dräger Flame 1500, Dual M25 cable entry, Aluminum | 2 | 2025-10-22 | 2025-12-22 | 2026-06-15 |  | 2
[20 empty] | Final Inspection | 2025-03-08 | 2026-06-20 |  | Polytron 8700 IR d 4-20mA HART Marine Grade Copper-Free Aluminium | 8 | 2025-10-22 | 2025-12-22 | 2026-06-15 |  | 8
[20 empty] | Cargo ready | 2026-04-01 | 2026-06-30 |  | D1xB2X10 20-28Vdc Red/Red 10J Xenon Strobe Beacon | 8 | 2025-10-22 | 2025-12-10 | 2026-05-15 | 2026-04-01 | 8
[20 empty] | - |  |  |  | D1xS1F 11.5-54Vdc Red Alarm Horn Sounder | 15 | 2025-10-22 | 2025-12-10 | 2026-05-15 | 2026-04-01 | 15
[20 empty] | - |  |  |  | GNExCP7-BG Break Glass Manual Signaling Box CP 1-24-150 | 13 | 2025-10-22 | 2025-12-10 | 2026-05-15 | 2026-04-01 | 13
14 | KBR954 | Instrument Tube & Fitting | 5000109996 | 1 | Swegelok | KR | KR | 2025-07-31 | 2026-01-15 | FOB | KOREA | 6557/0 | 1608/0 | 8165/0 | 8165 | EA | 3426 | 4739 | 0.4196 | KOM | 2025-10-15 | 2025-10-20 | 2025-10-16 | [8 empty] | Final&Packing inspection (1ST) | N/A (SQR review) | 2026-01-09 | 2026-01-12 | IRC-5000109996-0001 | 3585 | EA | 1 | SC7128C-P5-KC137-SS | 3011 | - | 3011 | EA | 2026-02-05 | 2026-02-08 | 2026-05-10 | 2026-05-12
[20 empty] | VPIS Submit | 2025-10-30 | 2025-10-30 | 2025-10-17 | [8 empty] | Final&Packing inspection (2ND) | N/A (SQR review) | 2026-04-01 | 2026-04-07 | IRC-5000109996-0002 | 1626 | EA |  | SC7128C-P5-KC136-CS | - | 574 | 574 | EA
[20 empty] | Key V/P Submit | 2025-10-30 | 2025-11-07 | 2025-10-29 | [8 empty] | Final&Packing inspection (3rd) | N/A (SQR review) | 2026-05-05 | 2026-05-19 |  |  |  | 2 | SC7128C-P5-KC209-SS | 1173 | - | 1173 | EA | 2026-05-11 | 2026-05-12 | 2026-07-14
[20 empty] | Sub-order Issued | 2025-11-30 | 2025-11-15 | 2025-10-16 | [8 empty] | Final&Packing inspection (4th) | N/A (SQR review) | 2026-08-05 | [5 empty] | SC7128C-P5-KC208-CS | - | 453 | 453 | EA | 2026-05-11 | 2026-05-12 | 2026-07-14
[20 empty] | Receive Main material | 2025-12-30 | 2025-12-10 | 2025-10-17
[20 empty] | Start Fabrication | 2026-01-15 | 2025-12-10 | 2025-10-20
[20 empty] | Manufacturing Completion | 2026-02-15 | 2026-01-07 | 2026-01-07
[20 empty] | Final Inspection | 2026-03-01 | 2026-01-09 | 2026-01-09
[20 empty] | Cargo ready 1st | 2026-01-15 | 2026-02-07 | 2026-02-08
[20 empty] | Cargo ready 2nd | 2026-03-15 | 2026-05-11 | 2026-05-12
[20 empty] | Cargo ready 3rd | 2026-05-15 | 2026-05-30
[20 empty] | Cargo ready 4th | 2026-08-15 | 2026-08-15
15 | KAR533 | On-Off Valve, Ball( 40-XV-71005S) | 5000110902 | 0 | Flowserve | TW | CN | 2025-10-30 | 2026-03-31 | FCA | CN | 0/0 | 1/0 | 1/0 | 1 | EA | 0 | 1 | 0 | KOM | 2025-10-30 | 2025-10-30 | 2025-10-30 | [8 empty] | Pressure &Torque Test FAT | N-5000110902-002 | 2026-03-23 | 2026-03-23 | N/A | 2 | EA | 1 | SC7128C-P5-CA184-CS | 0 | 1 | 1 | EA | F 2026-06-02 |  | F 2026-06-05 | [5 empty] | 1)Inpsection was completed by 4/27. SQR was submitted.. 2)Shipment will be shipped by Air after Eid. ETD 6/2 ETA 6/2
[20 empty] | VPIS Submit | 2025-12-01 | 2025-12-08 | 2025-12-08 | [8 empty] | Final inspection | N-5000110902-003 | 2026-04-27 | 2026-04-27
[20 empty] | Key V/P Submit | 2025-12-01 | 2025-12-08 | 2025-12-08
[20 empty] | Sub-order Issued | 2025-12-15 | 2025-12-31 | 2026-01-07
[20 empty] | Receive Main material | 2025-12-20 | 2026-03-06 | 2026-03-06
[20 empty] | Start Fabrication | 2025-12-20 | 2026-03-25 | 2026-03-13
[20 empty] | Manufacturing Completion | 2026-03-01 | 2026-03-31 | 2026-03-31
[20 empty] | Final Inspection | 2026-03-07 | 2026-04-27 | 2026-04-27
[20 empty] | Cargo ready | 2026-03-15 | 2026-06-02
16 | KAR533 | On-Off Valve, Ball (40-XV-71024S,40-XV-71002S) | 5000110841 | 0 | Valpres S.r.l. | Italy | Italy | 45934 | 46213 | FCA | Italy | 0/0 | 2/0 | 2/0 | 2 | EA | 0 | 2 | 0 | KOM | 2025-11-27 | 2025-11-27 | 2025-11-27 | BALL 12" | 1 | 2026-01-30 | 2026-01-30 | 2026-05-31 |  |  | BIFFI ITALIA S.R.L. | Material Inspection | N-5000110841-002 | 2026-04-24 | [18 empty] | All the project materials have been collected and are currently in transit. Most of them are expected to arrive at our facility by the end of May, except for some components of the 12” valve, which have been delayed by one week due to the additional witness required on the ball and seats.
[20 empty] | VPIS Submit | 2025-12-10 | 2025-12-26 | 2025-12-22 | SEATS 12" | 1 | 2026-01-30 | 2026-01-30 | 2026-05-31
[20 empty] | Key V/P Submit | 2025-12-10 | 2025-12-10 | 2025-12-10 | BALL 2" | 1 | 2026-01-30 | 2026-01-30 | 2026-05-31
[20 empty] | Sub-order Issued | 2026-01-15 | 2026-01-30 | 2026-02-10 | SEATS 2" | 1 | 2026-01-30 | 2026-01-30 | 2026-05-31
[20 empty] | Receive Main material | 2026-01-20 | 2026-05-31 |  | BODY & CLOSURES 12" | 1 | 2026-02-02 | 2026-02-02 | 2026-05-31
[20 empty] | Start Fabrication | 2026-01-25 | 2026-06-10 |  | BODY & CLOSURES 2" | 1 | 2026-02-02 | 2026-02-02 | 2026-05-31
[20 empty] | Manufacturing Completion | 2026-06-15 | 2026-06-14 |  | STEM & TRUNNION 12" | 1 | 2026-02-02 | 2026-02-02 | 2026-05-31
[20 empty] | Final Inspection | 2026-06-20 | 2026-06-15 |  | STEM & TRUNNION 2" | 1 | 2026-02-02 | 2026-02-02 | 2026-05-31
[20 empty] | Cargo ready | 2026-07-10 | 2026-07-10 |  | SEALS 12" | 1 | 2026-02-02 | 2026-02-02 | 2026-05-31
[20 empty] | - |  |  |  | SEALS 2" | 1 | 2026-02-02 | 2026-02-02 | 2026-05-31
[20 empty] | - |  |  |  | BOLTING 12" | 1 | 2026-01-28 | 2026-01-28 | 2026-05-31
[20 empty] | - |  |  |  | BOLTING 2" | 1 | 2026-01-28 | 2026-01-28 | 2026-05-31
[20 empty] | - |  |  |  | ACTUATOR 12" | 1 | 2025-11-25 | 2025-11-25 | 2026-06-10
[20 empty] | - |  |  |  | ACTUATOR 2" | 1 | 2025-11-25 | 2025-11-25 | 2026-06-10
Note on AL12: 1. SS Splice plate (18H) 180 EA 2. Clamp 180 EA for 20mmH SS Raceway installation.
Note on AL31: 1. SS Splice plate (18H) 180 EA 2. Clamp 180 EA for 20mmH SS Raceway installation.
Note on AL40: 1. SS Splice plate (18H) 180 EA 2. Clamp 180 EA for 20mmH SS Raceway installation.
Note on AL41: 1. SS Splice plate (18H) 180 EA 2. Clamp 180 EA for 20mmH SS Raceway installation.
Note on AL52: 1. SS Splice plate (18H) 180 EA 2. Clamp 180 EA for 20mmH SS Raceway installation.
Note on AL64: 1. SS Splice plate (18H) 180 EA 2. Clamp 180 EA for 20mmH SS Raceway installation.
Note on AL76: 1. SS Splice plate (18H) 180 EA 2. Clamp 180 EA for 20mmH SS Raceway installation.
Note on AL88: 1. SS Splice plate (18H) 180 EA 2. Clamp 180 EA for 20mmH SS Raceway installation.
Note on AL99: 1. SS Splice plate (18H) 180 EA 2. Clamp 180 EA for 20mmH SS Raceway installation.
Note on AL134: 1. SS Splice plate (18H) 180 EA 2. Clamp 180 EA for 20mmH SS Raceway installation.
Note on AL144: 1. SS Splice plate (18H) 180 EA 2. Clamp 180 EA for 20mmH SS Raceway installation.
Note on AL153: 1. SS Splice plate (18H) 180 EA 2. Clamp 180 EA for 20mmH SS Raceway installation.
Note on AL165: 1. SS Splice plate (18H) 180 EA 2. Clamp 180 EA for 20mmH SS Raceway installation.
Note on AL174: 1. SS Splice plate (18H) 180 EA 2. Clamp 180 EA for 20mmH SS Raceway installation.
Note on AL183: 1. SS Splice plate (18H) 180 EA 2. Clamp 180 EA for 20mmH SS Raceway installation.

## BOM schedule
MR No. | MR Description | batch | Area | Description | BOM by | FOB | ROS date | BOM |  |  | MMS releasement | PO/CO issuance | PO schedule date (Level III) | Remark | Lead time, not including logistic (for reference)
[8 empty] | SOC to TOC (For PO) | SOC to TOC (For Fab.) | Eng to Pro
ND1020 | Lighting Fixture and Others | 1 | ESP | High Mast Pole x10 | SOC + TOC | 2025-03-15 | 2025-06-23 | N/A |  | done | done | 2025-01-09 | 2025-02-10 |  | 12-18 weeks
|  | 2 | ESP | High Mast Pole x4 | SOC + TOC | TBC | TBC |  |  | 2025-06-19 | TBC | TBC
|  | 3 | ESP | 100% | SOC + TOC | 2025-09-30 | 2026-02-01 | 2025-06-20 | 2025-11-01 | 2025-11-15 | 2025-11-22 | 2025-11-29
NB2010 | Cable tray | 1 | RLOC | turnaround period | TOC | 2025-06-15 | 2025-08-15 | N/A | N/A | done | done | 2025-03-10 | 2025-06-27 |  | 6-8 weeks
|  | 2 | ESP | TOC 70% | TOC | 2025-06-15 | 2026-01-29 | N/A | N/A | done | done | 2025-03-10
|  | 3 | ESP | TOC 100% | TOC |  |  | N/A | N/A | 2025-11-30 | 2025-12-07 | 2025-12-14
|  | 4 | ESP | SOC 70% (Perforated) + 100% (Ladder) | SOC | 2025-10-01 | 2025-11-15 | 2025-06-20 | 2025-06-30 | 2025-07-07 | 2025-07-14 | 2025-07-21 |  | Perforated Tray
|  | 5 | ESP | SOC 100% (Perforated) | SOC | 2026-02-07 | 2026-03-24 | 2025-06-20 | 2025-06-30 | 2025-07-01 | 2025-07-08 | 2025-07-15 |  | Ladder Tray
NB3010 | Cable Gland | 1 | ESP | 40% | SOC + TOC | 2025-11-15 | 2026-01-08 | 2025-06-20 | 2025-07-30 |  |  | 2025-06-27 | 2025-06-27 | TBE issued, awaiting for BOM for PO | 8-10 weeks
|  | 2 | ESP | 100% | SOC + TOC |  |  | 2025-06-20 | 2025-11-15 | 2025-06-27 | 2025-07-04 | 2025-07-11
NB4010 | MV & LV Cable | 1 | ESP | 70% | SOC + TOC | DDP 15-Jan-26 | 2026-02-15 | 2025-06-20 | 2025-07-30 |  |  | 2025-06-30 | 2025-06-27 | TBE issued, awaiting for BOM for PO | 10-12 weeks
|  | 2 | KM | tie-in | TOC |  |  | N/A | N/A | 2025-08-30 | 2025-09-06 | 2025-09-13
|  | 3 | ESP | 100% | SOC + TOC |  |  | 2025-06-20 | 2025-11-15 | 2025-11-17 | 2025-11-24 | 2025-12-01
N13A.01A | RTD, TELECOM, AND COMMUNICATION CABLE | 1 | ESP | 70% | SOC + TOC | 2025-12-01 | 2026-02-27 | N/A | N/A | 2025-06-26 | 2025-06-26 | 2025-07-03 | 2025-06-27 | TBE on-going | 14-16 weeks
|  | 2 | ESP | 100% | SOC + TOC |  |  | 2025-06-20 | 2025-12-31 | 2026-01-07 | 2026-01-14 | 2026-01-21
NB4010 | CABLE TERMINATION KITS | 1 | ESP | 70% | SOC + TOC | 2025-12-01 | 2026-02-27 | 2025-06-20 | 2025-07-10 | 2025-06-27 | 2025-07-04 | 2025-06-27 | 2025-06-27 | TBE issued, awaiting for BOM for PO | 18 weeks
|  | 2 | ESP | 100% | SOC + TOC |  |  | 2025-06-20 | 2025-12-15 | 2025-12-22 | 2025-12-29 | 2026-01-05
ND2010 | POWER MATERIAL (WELDING SOCKET & PLUG, LCS) | 1 | ESP | 70% | SOC + TOC | 2025-12-01 | 2026-02-27 | 2025-06-20 | 2025-08-01 | 2025-06-27 | 2025-07-04 | 2025-06-27 | 2025-06-27 | TBE issued, awaiting for BOM for PO | 14 weeks
|  | 2 | ESP | 100% | SOC + TOC |  |  | 2025-06-20 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21
KBR910 | Instrument Cable Tray & Fitting | 1 | RLOC + RLIC | turnaround period + tie-in | TOC | 2025-06-15 | 2025-08-15 | done |  | done | done | 2025-04-09 | 2025-07-28 |  | 6-8 weeks
|  | 2 | ESP | 80% | SOC + TOC | 2025-06-15 | 2026-01-26 | done |  | 2025-06-12 | 2025-06-12 | 2025-06-30 |  | under TBE
|  | 3 | ESP | 100% | SOC + TOC |  |  | 2025-09-15 |  | 2025-09-22 | 2025-09-29
KBR920 | Instrument Cable | 1 | RLOC | turnaround period + tie-in | TOC | 2025-07-21 | 2025-08-15 | done |  | done | done | 2025-05-08 | 2025-07-31 |  | 8-12 weeks
|  | 2 | ESP | 60% | SOC + TOC |  | 2026-03-29 | done |  | 2025-06-18 | 2025-06-25 | 2025-07-02
|  | 3 | ESP | 100% | SOC + TOC |  |  | 2025-10-01 |  | 2025-10-08 | 2025-10-15 | 2025-10-22
KBR940 | INSTRUMENT JUNCTION BOX AND LCP | 1 | RLOC | turnaround period / JB x2 +LP x1 | TOC | 2025-07-31 | 2025-10-01 | done |  | done | done | 2025-05-29 | 2025-07-26
|  | 2 | ESP | 80% | SOC + TOC |  | 2025-05-23 | 2025-06-25 |  | 2025-07-02 | 2025-07-09 | 2025-07-16
|  | 3 | ESP | 100% | SOC + TOC |  |  | 2025-10-07 |  | 2025-10-14 | 2025-10-21 | 2025-10-28
KBR954 | Instrument Tube & Fitting | 1 | RLOC | tie-in | TOC | TBD | TBD | N/A |  | 2025-07-02 | 2025-07-09 | 2025-07-16 | 2025-07-31 | AR approved, BOM for 1st order only 30m (vendor is not willing to take this order) --> PO based on 80% BOM | 12-30 weeks
|  | 2 | ESP | 80% | SOC + TOC |  | 2026-08-05 | 2025-07-02 |  | 2025-07-09 | 2025-07-16 | 2025-07-23 | 2025-07-31 | PO issuance based on 80% BOM
|  | 3 | ESP | 100% | SOC + TOC |  |  | 2025-10-08 |  | 2025-10-15 | 2025-10-22 | 2025-10-29
KBR933 | Instrument Cable Glands | 1 | RLOC | tie-in | ISBL+OSBL | 2025-07-31 | 2025-08-15 | done |  | done | done | 2025-05-22 | 2025-08-09 |  | 8-10 weeks
|  | 2 | ESP | 80% | SOC + TOC |  | 2026-05-18 | 2025-06-25 |  | 2025-07-02 | 2025-07-09 | 2025-07-16
|  | 3 | ESP | 100% | SOC + TOC |  |  | 2025-10-07 |  | 2025-10-14 | 2025-10-21 | 2025-10-28
Formulas:
Eng to Pro = [SOC to TOC (For Fab.)]+7+7
Eng to Pro = [SOC to TOC (For Fab.)]+7
MMS releasement = [Eng to Pro]+7
PO/CO issuance = [MMS releasement]+7
FOB = [ROS date]-45
Note on H9: 2026-01-29 → 2025-11-15
Note on H10: 2026-01-29 → 2026-03-24
Note on H11: 2026-01-21 → 2026-01-08
Note on H13: 2026-01-21 → 2026-02-15
Note on H16: 2026-01-21 → 2026-02-27
Note on H18: 2026-01-21 → 2026-02-27
Note on H20: 2026-01-21 → 2026-02-27

## E&I Bulk status
RLP ESP Electrical and Instrument Bulk Material Procurement Status
Discipline | PO No | Description | Vendor | Country | Batch (order %) | SAP PO | Delivery | ETA site | ROS | Remark
Electrical | 5000105899 | Outdoor Lighting Fixture and Others | Warom | China | 1st batch (HMP and lightings) | 2025-01-09 | 2025-05-14 | 2025-05-20 | 2025-06-01
Electrical | 5000105899 | Outdoor Lighting Fixture and Others | Warom | China | 2nd HMP | 2025-01-09 | 2025-09-24 | 2025-10-30 | -
Electrical | 5000105899 | Outdoor Lighting Fixture and Others | Warom | China | 3rd batch (100% SOC + 50% TOC) | 2025-01-09 | 2025-12-14 | 2026-01-22 | -
Electrical | 5000105899 | Outdoor Lighting Fixture and Others | Warom | China | 4th batch (remaining 50% TOC) | 2026-03-17 | 2026-05-19 | 2026-07-15 |  | SAP CO has been completed
Electrical | 5000108773 | POWER & CONTROL CABLE | Doha Cables | Qatar | KM power cable (33kV) | 2025-07-03 | 2026-01-01 | 2026-01-01 | 2026-01-20 | Forecast delivery on 1/1&6&7
Electrical | 5000108773 | POWER & CONTROL CABLE | Doha Cables | Qatar | 2nd batch (70%) | 2025-11-04 | 1st: 2026/1/28 2nd: 2026/3/9 | 1st: 2026/1/28 2nd: 2026/3/9 | 2026-02-28 | FAT on 1/12&2/15
Electrical | 500010877302 | POWER & CONTROL CABLE | Doha Cables | Qatar | 3rd batch (95%) | 2026-01-08 | 2026-03-29 | 2026-03-29 | 2026-04-07 | SAP CO has been completed
Electrical | 500010877302 | POWER & CONTROL CABLE | Doha Cables | Qatar | 4th batch (96%) | 2026-01-08 | 2026-04-18 | 2026-04-18 | 2026-04-07 | SAP CO has been completed
Electrical | 5000108773 | POWER & CONTROL CABLE | Doha Cables | Qatar | 5th batch (Earthing cable) | 2026-03-28 | 2026-03-09 | 2026-03-09 | 2026-01-31 | SAP CO has been completed
Electrical | 5000108773 | POWER & CONTROL CABLE | Doha Cables | Qatar | 6th batch | TBD | F 2026-08-08 | F 2026-08-15 | TBD | CO is processing
Electrical | 500010930601 | RTD, TELECOM, AND COMMUNICATION CABLE | Gaon Cable | Korea | 1st + 2nd batch (100%) | 2026-12-24 | 2026-02-08 | TBD | 2026-02-28 | Sailing through South India at low speed, waiting final decision from HMM
Electrical | 500010930601 | RTD, TELECOM, AND COMMUNICATION CABLE | Gaon Cable | Korea | Additional |  |  |  |  | CO is processing
Electrical | 5000109274 | Fiber Optical Cable for QSTEC Substation E-1000 | Doha Cables | Qatar | 100% | 2025-07-31 | 2026-01-28 | 2026-01-28 | 2026-01-20 | IRC issued
Electrical | 5000108966 | CABLE GLAND | CMP Products | UK | 46% | 2025-07-24 | 2026-01-24 | 2026-03-15 | 2026-04-10 | Shipment arranging
Electrical | 5000108966 | CABLE GLAND | CMP Products | UK | 44% | 2026-04-01 | 2026-04-12 | 2026-06-10 | 2026-04-10 | SAP CO has been completed
Electrical | 5000108966 | CABLE GLAND | CMP Products | UK | 10% | TBD | F 2026-06-05 |  |  | MMS is updating
Electrical | 5000108966 | CABLE GLAND | CMP Products | UK | Remaining | TBD | F 2026-07-31 |  |  | MMS is updating
Electrical | 5000108967 | Power Material (Welding Socket, LCS & JB) and Cable Termination Kits | R. Stahl Pte Ltd. | Singapore | 60% | 2025-07-24 | 2026-04-28 (termination kit) F 2026-05-31 (power material) | 2026-04-28 (termination kit) | 2026-04-10
Electrical | 500010896701 | Power Material (Welding Socket, LCS & JB) and Cable Termination Kits | R. Stahl Pte Ltd. | Singapore | 40% | 2026-03-26 | F 2026-07-17 (termination kit) F 2026-05-31 (power material) |  | 2026-04-10 | SAP CO has been completed
Electrical | 500010896701 | Power Material (Welding Socket, LCS & JB) and Cable Termination Kits | R. Stahl Pte Ltd. | Singapore | Additional | TBD |  |  |  | MMS is updating
Electrical | 5000107367 | Cable Tray & Accessory | Suzhou Ontop | China | 1st batch (40%) | 2025-03-10 | 2025-07-06 | 2025-07-27 | 2025-10-10
Electrical | 5000107367 | Cable Tray & Accessory | Suzhou Ontop | China | 2nd batch (80%) | 2025-08-02 | 2025-09-10 | 2025-10-05 | -
Electrical | 500010736702 | Cable Tray & Accessory | Suzhou Ontop | China | 3rd batch (100%) | 2025-12-29 | 2025-12-08 | 2026-01-11 | - | CO completed
Electrical | 500010736703 | Cable Tray & Accessory | Suzhou Ontop | China | 4th batch (additional) | 2026-02-14 | 2026-02-18 | TBD | - | SAP CO has been completed
Instrument | 5000107368 | Instrument Cable Tray and Fittings | Suzhou Ontop | China | 1st batch for tie-in | 2025-04-09 | 2025-06-29 | 2025-08-04 | 2025-08-15
Instrument | 5000107368 | Instrument Cable Tray and Fittings | Suzhou Ontop | China | 2nd batch (70%) | 2025-07-23 | 2025-09-10 | 2025-10-05 | -
Instrument | 5000107368 | Instrument Cable Tray and Fittings | Suzhou Ontop | China | 3rd batch (100%) | 2026-03-14 | 2026-04-23 | 2026-06-10 | - | SAP CO has been completed
Instrument | 5000108080 | Cable Gland (Instrument) | CMP Products | Singapore | 1st batch for tie-in | 2025-05-29 | 2025-08-20 | 2025-08-24 | -
Instrument | 500010808001 | Cable Gland (Instrument) | CMP Products | Singapore | 2nd batch (100%) | 2026-01-08 | 2026-04-12 | 2026-07-15 | -
Instrument | 5000109996 | Instrument Tube & Fitting | Swagelok Korea | Korea | 1st batch (70% SOC + 80% TOC) | 2025-10-10 | 2026-02-07 | 2026-05-12 | -
Instrument | 5000109996 | Instrument Tube & Fitting | Swagelok Korea | Korea | 2nd batch (100%) | 2026-05-20 | 2026-05-13 | 2026-07-10 | - | SAP CO has been completed
Instrument | 5000109996 | Instrument Tube & Fitting | Swagelok Korea | Korea | 3rd batch (100%) | TBD | TBD | TBD | - | TBE
Instrument | 5000107926 | INSTRUMENT CABLE | Gaon Cable | Korea | 1st batch for tie-in | 2025-05-08 | 2025-07-24 | 2025-09-01 | 2025-10-10
Instrument | 500010792601 | INSTRUMENT CABLE | Gaon Cable | Korea | 2nd batch (80% SOC + 60% TOC) | 2026-01-26 | 2026-02-08 | 2026-05-15 | - | Sailing through South India at low speed, waiting final decision from HMM
Instrument | 500010792602 | INSTRUMENT CABLE | Gaon Cable | Korea | 3rd batch | 2026-03-17 | 2026-04-29 | 2026-07-04 | - | SAP CO has been completed
Instrument | 500010792602 | INSTRUMENT CABLE | Gaon Cable | Korea | 4th batch (remaining % TOC + EE FO cable) |  |  |  | - | CO is processing
Instrument | 5000108061 | INSTRUMENT JUNCTION BOX AND LCP | Phoenix Mecano | Singapore | 1st batch for tie-in | 2025-05-29 | 2025-09-28 | 2025-10-23 | -
Instrument | 5000108061 | INSTRUMENT JUNCTION BOX AND LCP | Phoenix Mecano | Singapore | 2nd batch (accessories only) | 2026-01-10 | 2025-12-02 | 2025-12-04 | 2025-12-15 | PO to be included for 3rd batch.
Instrument | 5000108061 | INSTRUMENT JUNCTION BOX AND LCP | Phoenix Mecano | Singapore | 3rd batch (100%) | 2026-01-10 | F 2026-06-20 |  | -